## I2
|  | Estimate | Iteration 2 (burndown)
|  |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4
|  |  | T | W | T | F | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T
(1A) Error Handling Framwork
Finalize Requirements | RS,SM, EV | 20 | 16 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design system error handling | MK | 20 | 20 | 20 | 15 | 13 | 13 | 13 | 10 | 5 | 0 | 0 | 0 | 0
Design data error/exception handling | UP | 14 | 14 | 14 | 14 | 14 | 13 | 12 | 11 | 11 | 7 | 3 | 1 | 0
Design database component of error threshold | MK | 8 | 8 | 8 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Data modeling for error thresholds | SO | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0
Build database component of error threshold | DL | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Documents Partition Exchange Strategy | MK |  | 2 M: 15; 2 T: 9; 3 W: 5; 3 T: 3
Unit test database component of error threshold | SR | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
(1B) Application Support Framework
Review impact to admin panel (cycle 1) design changes | UP | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 7 | 5 | 5 | 5
Usability review of change (business) | RS | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Usability review of change (prod support) | UP | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Build/modify views in admin panel | JS | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 60
Design notification | MK | 6 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Table design for notification | SO | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Build notification component | TA | 15 | 15 | 15 | 15 | 15 | 15 | 14.5 | 14.5 | 14.5 | 14.5 | 13 | 12 | 12
Configure notification component (business) | SM | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Configure notification component (prod support) | MK | 6 | 6 | 6 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
(2B) Externalized Filtering Framework (EFF)
Review EI-2 components for EFF | MK, UP | 20 | 20 | 18 | 2 | 10 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0
Refine & standardize components of EFF (EI-2) | MK, UP | 30 | 30 | 30 | 20 | 18 | 17 | 17 | 17 | 16 | 15 | 14 | 14 | 14
Table design | SO | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Build EFF | TA, AL | 16 | 16 | 16 | 20 | 19 | 18 | 17 | 13.5 | 10 | 8 | 6 | 10 | 10
Design & Build pre-validation routine | TH | 16 | 9 | 5 | 2 | 15 | 11 | 7 | 4 | 0.5 | 0 | 0 | 0 | 0
Test EFF based on sample filter critieria | MC, SR | 8 | 8 | 8 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 9.5 | 9.5
(1C) Audit Logging
Identify existing logging features | UP | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 1
System req new (7.1) tables | UP | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5
Desing for new 7.1 tables | SO | 4 | 4 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
(2A) Data Assembly Framework (Joins & Summation)
Design Joins | MK, UP,SZ | 20 | 12 | 10 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0
Design Summation | MK, UP | 14 | 14 | 14 | 14 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 9 | 9
Data modeling (Joins & Summation) | SO | 37.5 | 37.5 | 36.5 | 34.5 | 33.5 | 32.5 | 30.5 | 28.5 | 27.5 | 26.5 | 25.5 | 24.5 | 24.5
Build joins framework | MK, UP | 8 | 8 | 8 | 8 | 6 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0
Build summation framework | TA, AL | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 13 | 13 | 13 | 13
Integrate (joins & summation) | MK, TA | 12 | 12 | 12 | 12 | 15 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Requirments and Design for CI-3
Req for FinAcc | RS, SM, EV | 120 | 106 | 104 | 98 | 90 | 84 | 74 | 64 | 54 | 44 | 36 | 31 | 31
Approach to datadictionary maintenance | SO, SM, RS | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8
Design ETL load for FinAcc | MK | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
Req for Credit App | MM, SM | 16 | 10 | 8 | 7 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4
Req for FinAcc change | MM, SM, RS | 46 | 38 | 34 | 26 | 20 | 16 | 12 | 12 | 10 | 8 | 8 | 8 | 8
Req for FinAcc bal | EV, SM, RS | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 40 | 30 | 20 | 12 | 12
List of re-usable components | UP | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 3
Data type and precission consistency base on data mapping | SO | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 9 | 9 | 8 | 8
Data modeling FinAcc | SO | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Test Bed shakedown
Big SIT | SR, MC | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
Small SIT | SR, MC | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Misc
Setup of new dev resource tools | TA, AL | 4 | 3 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1
Edjucation/training of new dev resource | TA, AL, YK | 6 | 5 | 4 | 3 | 4 | 8 | 6.5 | 5.5 | 4.5 | 4 | 4 | 4 | 4
| Hours Remaining | 742.5 | 693.5 | 667.5 | 589.5 | 585 | 554 | 528 | 501.5 | 460.5 | 432 | 392.5 | 366 | 344
| Planned Avg. hrs/day | 38
| Day |  | 2012-10-02 | 2012-10-03 | 2012-10-04 | 2012-10-05 | 2012-10-09 | 2012-10-10 | 2012-10-11 | 2012-10-12 | 2012-10-15 | 2012-10-16 | 2012-10-17 | 2012-10-18 | 2012-10-19 | 2012-10-22 | 2012-10-23 | 2012-10-24 | 2012-10-25 | 2012-10-26 | 2012-10-29 | 2012-10-30
| Day # | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| Acutals | 742.5 | 693.5 | 667.5 | 589.5 | 585 | 554 | 528 | 501.5 | 460.5 | 432 | 392.5 | 366 | 344 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| Actual Avg. hrs/last 3 days | #N/A | #N/A | #N/A | 51 | 36 | 38 | 21 | 28 | 31 | 32 | 36 | 32 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
| Forecast | 742.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 315 | 286 | 257 | 228 | 199 | 170 | 141 | 112 | <= Hrs OT/improvement needed to get back on track
| Ideal Plan | 742.5 | 704.5 | 666.5 | 628.5 | 590.5 | 552.5 | 514.5 | 476.5 | 438.5 | 400.5 | 362.5 | 324.5 | 286.5 | 248.5 | 210.5 | 172.5 | 134.5 | 96.5 | 58.5 | 20.5 | 0
WARNING: Team Under Performing! | bar: 2012-10-02 to 2012-10-05
Note on N12: New Task
Note on L16: Design considerations for admin panel need to be addressed
Note on J27: Had a additional task that wasn’t part of the initial estimation… the task is to design, build and incorporate the same in bridging the Jojns and Filters to the ETL Tasks
Note on H30: Increase because of framework integration
Note on K30: Modification of Orginal Control Framework (additional 3 hours invested)
Note on O30: Modification of Orginal Control Framework (additional 1.5 hours invested)
Note on P30: Morel Effort required for Documentation and creation of Autosys Test Jobs
Note on I31: Added build component to this task, missed in original EFF build estimate
Note on I32: added 4 hours to test pre-validation routine
Note on I64: Aiken keeps on asking questions
Note on J64: Getting Yuri and Aiken up to speed. Addition hands on required with Informatica
Note on O64: AutoSys 'Trainging' (additional 2 hours invested)