## Baseline NPV
Outsourcing NPV without M&A components
A. INVESTMENT RELATED |  |  | initial | year | year | year | year | year
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | Value | Remarks
A.1 | Transtion and transformation
| a. | Transition | 0: -50000; 1: -10000 | minus | Both internally (e.g. create retained organization) and charged by external outsourcing partner
| b. | Transformation | 1: -75000; 2: -25000 | minus | Both internally and charged by external outsourcing partner
| c. | Desinvestments/write offs | [6 empty] | minus | Internally (e.g. obsolete hardware)
A.2 | Value of asset transfer to supplier
| a. | Software | [6 empty] | plus | e.g. value of software client is able to transfer to external outsourcing partner
| b. | Hardware | 0: 25000 | plus | e.g. value of hardware owned by client transferred to external outsourcing partner
| c. | Facility | [6 empty] | plus | e.g. value of facilities the external outsourcing partner is willing to buy from client
A.3 | Exit or retransition costs
| a. | Exit or retranstition costs | 5: -30000 | minus | Both internally and from external outsourcing partner
| b. | Asset transfer in case of retransition | [6 empty] | minus | Retransition: insourcing from external outsourcing partner
A4. | Investments in 'do noting' scenario
| a. | Software | [6 empty] | plus | Investments to replace end-of-life software owned by client instead of 'as a service'
| b. | Hardware | [6 empty] | plus | Investments to replace end-of-life hardware owned by client instead of leasing or renting
| c. | Facility | 2: 5000; 5: 5000 | plus | e.g. upgrading client-owned datacenter
A.5 | Total |  | -25000 | -85000 | -20000 | 0 | 0 | -25000
B. OPERATIONS RELATED |  |  | initial | year | year | year | year | year
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | Value | Remarks
B.1 | Benefits related to outsourcing
| a. | Costs transferred to external outsourcing partner |  | 120000 | 120000 | 120000 | 120000 | 120000 | plus | All operational cost the client is able to transfer to the external outsourcing partner as part of the contract
| b. | Monitary value quality improvements |  | 25000 | 30000 | 35000 | 35000 | 35000 | plus | e.g. improved first-time-right, performance, time-to-market
| c. | Other benefits |  | 2000 | 5000 | 7500 | 7500 | 7500 | plus | e.g. access to scarce expertise, access to proprietary solutions, flexibility
| Sub total |  | 0 | 147000 | 155000 | 162500 | 162500 | 162500
B.2 | Operations costs related to outsourcing
| a. | Costs related to retained organization | 4000 | 10000 | 12000 | 12000 | 12000 | 12000 | plus
| b. | Cost invoiced by supplier for contract |  | 105000 | 100000 | 100000 | 95000 | 95000 | plus
| c. | Other cost of client company | 1: 2000; 2: 1000 | plus | e.g. training and coaching redundant but untransferable employees
| d. | Other cost invoiced by supplier | 2: 1000 | plus | e.g. improvement projects not part of the base contract
| e. | Any other costs | [6 empty] | plus
B.3 | Sub total |  | 4000 | 117000 | 114000 | 112000 | 107000 | 107000
B.4 | Net Operations result (B.1 minus B.2) |  | -4000 | 30000 | 41000 | 50500 | 55500 | 55500
C. CASH FLOW |  |  | initial | year | year | year | year | year
|  |  | 0 | 1 | 2 | 3 | 4 | 5
C.1 | Investments + initial operations costs year 0 |  | 29000 | 85000 | 20000 | 0 | 0 | 25000
C.2 | Operations costs (excl. interest and depreciation) |  |  | 117000 | 114000 | 112000 | 107000 | 107000
C.3 | Total expenditures |  | 29000 | 202000 | 134000 | 112000 | 107000 | 132000
C.4 | Operational benefits |  |  | 147000 | 155000 | 162500 | 162500 | 162500
C.5 | Net cash flow (C.4 minus C.3) |  | -29000 | -55000 | 21000 | 50500 | 55500 | 30500
| Cumulative net cash flow |  | -29000 | -84000 | -63000 | -12500 | 43000 | 73500
|  |  |  | 12 | 12 | 12 | 2.7027 | 0
Time horizon (in years) |  |  | 0: 5
Payback period (in months) |  |  | 0: 38.7027
Weighted Average Cost of Capital (WACC) | bar: 0
Net Present Value when calculating with WACC |  |  | 0: 36352.3365
Internal Rate Of Return (IRR) |  |  | 0: 24.4%
D. Net Present Value of Cash Flow |  |  | initial | year | year | year | year | year
|  |  | 0 | 1 | 2 | 3 | 4 | 5
D.1. | Net present value cash flow = (1/(1+ WACC)**t) * C.5 |  | -29000 | -50458.7156 | 17675.2799 | 38995.2657 | 39317.5992 | 19822.9073
D.2 | Cumulative net present value cash flow |  | -29000 | -79458.7156 | -61783.4357 | -22788.17 | 16529.4292 | 36352.3365
Notes: | Only the actual cashflows are taken into account in this example. To calculate accounting profits, non-cash inflows/outflows (e.g. depreciation) should be included in de calculation. The tax shield provided by depreciation is also left out.

## NPV with M&A components
Outsourcing NPV with M&A components
A. OPTION VALUE CLIENT COMPANY |  |  | initial | year | year | year | year | year
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | Value | Remarks
A.1 | Investments of 'do nothing' scenario
| a. | Software | [6 empty] | plus | Investments to replace end-of-life software owned by client instead of 'as a service'
| b. | Hardware | [6 empty] | plus | Investments to replace end-of-life hardware owned by client instead of leasing or renting
| c. | Facility | 2: 5000; 5: 5000 | plus | e.g. upgrading client-owned datacenter
A.2 | Value co-created with outsourcing partner
| a. | Co-create new value proposition |  |  | 15000 | 25000 | 25000 | 25000 | plus
| b. | Access to new customer segments/channels | [6 empty] | plus
| c. | Other quantitative co-creation benefits | [6 empty] | plus
A.3 | Quantitative effect of improved quality
| a. | Improved performance/availability |  | 25000 | 30000 | 35000 | 35000 | 35000 | plus | Both internally and from eexternal outsourcing partner
| b. | Time-to-market improvement | [6 empty] | plus
| c. | Service mix flexibility |  | 5000 | 7500 | 10000 | 10000 | 10000 | plus | e.g. access to broader and deeper IT service portfolio without the need to invest
| d. | Other quantitative operational benefits | [6 empty] | plus
A4. | Quantitative effect of risk transfer
| a. | Personnel |  | 7500 | 10000 | 12500 | 15000 | 15000 | plus | e.g. investering in, on hind sight, the wrong skills, knowledge; hiring too many/few resources.
| b. | Software | [6 empty] | plus | e.g. investing in the wrong, too much, too little software
| c. | Hardware |  | 2500 | 5000 | 7500 | 7500 | 7500 | plus | e.g. investing in the wrong, too much, too little hardware
| d. | Facilities | 2: 7500; 5: 10000 | plus | e.g. investing in the wrong, too much, too little floor or rack space
A.5 | Total |  | 0 | 40000 | 80000 | 90000 | 92500 | 107500
B. INTRINSIC VALUE CLIENT COMPANY |  |  | initial | year | year | year | year | year
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | Value | Remarks
B.1 | Value of asset transfer and return on re-investment
| a. | People | 0: -500 | plus or minus | Value of the knowledge, skill sets and experience of the transferred team members
| b. | Software | [6 empty] | plus | Value of the software transferred to the external outsourcing partner
| c. | Hardware | 0: 25000 | plus | Value of the hardware transferred to the external outsourcing partner
| d. | Facilities | [6 empty] | plus | Value of the facilities transferred to the external outsourcing partner
| e. | Return on re-investing @ WACC from year 2 onwards |  |  | 2205 | 2205 | 2205 | 2205 | plus | The return on money obtained from the external outsourcing partner for the asset transfer
B.2 | Transtion and transformation
| a. | Transition | 0: -50000; 1: -10000 | minus | Both internally (e.g. create retained organization) and charged by external outsourcing partner
| b. | Transformation | 1: -75000; 2: -25000 | minus | Both internally and charged by external outsourcing partner
| c. | Desinvestments/write offs | [6 empty] | minus | Internally (e.g. obsolete hardware)
| d. | Interest cost @ 1/2 WACC |  | -2250 | -6075 | -7200 | -7200 | -7200 | minus | Assuming loaning from a bank @ 1/2 the WACC and repaying none of the principle amount
B.3 | Operations benefits and costs
| a. | Costs transferred to supplier |  | 120000 | 120000 | 120000 | 120000 | 120000 | plus | All operational cost the client is able to transfer to the external outsourcing partner as part of the contract
| b. | Costs related to retained organization | -4000 | -10000 | -12000 | -12000 | -12000 | -12000 | minus
| c. | Cost invoiced by outsourcing partner for contract |  | -105000 | -100000 | -100000 | -95000 | -95000 | minus
| d. | Other cost of client company | 1: -2000; 2: -1000 | minus | e.g. training and coaching redundant but untransferable employees; termination fees
| e. | Other cost invoiced by supplier | 2: -1000 | minus | e.g. improvement projects not part of the base contract
| f. | Any other costs | [6 empty] | minus
B.4 | Total |  | -29500 | -84250 | -22870 | 3005 | 8005 | 8005
C. EXIT COSTS |  |  | initial | year | year | year | year | year
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | Value
C.1 | Exit/transition or retransition
| a. | Exit or retranstition costs | 5: -30000 | minus | Both internally and from external outsourcing partner
| b. | Asset transfer in case of retransition | [6 empty] | minus | Retransition: insourcing from external outsourcing partner
C.2 | Total |  | 0 | 0 | 0 | 0 | 0 | -30000
D. VALUE RELATED TO SOURCING RISK |  |  | initial | year | year | year | year | year
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | Value
D.1 | Sourcing-specific risks
| a. | Strategic risk (‘lock-in’) |  |  | -2500 | -2500 | -5000 | -7500 | minus
| b. | Operational Risk |  | -3500 | -1500 | -500 | -250 | -150 | minus
| c. | Reputation/Legal Risk |  | -2500 | -1000 | -500 | -500 | -1500 | minus
D.2 | Total |  | 0 | -6000 | -5000 | -3500 | -5750 | -9150
E. CASH FLOW |  |  | initial | year | year | year | year | year
|  |  | 0 | 1 | 2 | 3 | 4 | 5
E.1 | Net cash flow (A.5 + B.4 + C.2 + D.2) |  | -29500 | -50250 | 52130 | 89505 | 94755 | 76355
| Cumulative net cash flow |  | -29500 | -79750 | -27620 | 61885 | 156640 | 232995
|  |  |  | 12 | 12 | 3.703 | 0 | 0 | 0
Time horizon (in years) |  |  | 0: 5
Payback period (in months) |  |  | 0: 27.703
Weighted Average Cost of Capital (WACC) | bar: 0
Net Present Value when calculating with WACC |  |  | 0: 154142.4849
Internal Rate Of Return (IRR) |  |  | 0: 63.02%
D. Net Present Value of Cash Flow |  |  | initial | year | year | year | year | year
|  |  | 0 | 1 | 2 | 3 | 4 | 5
D.1. | Net present value cash flow = (1/(1+ WACC)**t) * E.1 |  | -29500 | -46100.9174 | 43876.778 | 69114.2824 | 67126.8309 | 49625.511
D.2 | Cumulative net present value cash flow |  | -29500 | -75600.9174 | -31724.1394 | 37390.143 | 104516.9739 | 154142.4849
Notes: | Only the actual cashflows are taken into account in this example. To calculate accounting profits, non-cash inflows/outflows (e.g. depreciation) should be included in de calculation. The tax shield provided by depreciation is also left out.

## Graphs
| Without M&A Components | With M&A Components
Payback period (in months) | 38.7027 | 27.703
Net Present Value when calculating with WACC | 36352.3365 | 154142.4849
Internal Rate Of Return (IRR) | 24.4% | 63.02%
Without M&A Components | initial | year | year | year | year | year
| 0 | 1 | 2 | 3 | 4 | 5
Net Cash flow | -29000 | -55000 | 21000 | 50500 | 55500 | 30500
Cumulative net cash flow | -29000 | -84000 | -63000 | -12500 | 43000 | 73500
Net present value cash flow = (1/(1+ WACC)**t) * initiql investment | -29000 | -50458.7156 | 17675.2799 | 38995.2657 | 39317.5992 | 19822.9073
Cumulative net present value cash flow | -29000 | -79458.7156 | -61783.4357 | -22788.17 | 16529.4292 | 36352.3365
With M&A Components | initial | year | year | year | year | year
| 0 | 1 | 2 | 3 | 4 | 5
Net Cash flow | -29500 | -50250 | 52130 | 89505 | 94755 | 76355
Cumulative net cash flow | -29500 | -79750 | -27620 | 61885 | 156640 | 232995
Net present value cash flow = (1/(1+ WACC)**t) * initiql investment | -29500 | -46100.9174 | 43876.778 | 69114.2824 | 67126.8309 | 49625.511
Cumulative net present value cash flow | -29500 | -75600.9174 | -31724.1394 | 37390.143 | 104516.9739 | 154142.4849