## Pre-Cutover
Step | Activity | Due Date | Owner | Notes
1 | Schedule non-functional testing
2 | Conduct team meeting to review cutover plan
3 | Confirm secure servers
4 | Send out cutover meeting notice
5 | Ensure all parties have replied to meeting notice
6 | Client approval of cutover schedule
7 | Test 301 redirects in pre-production
8 | Request CDN change
9 | Test CDN change in pre-production
10 | Change DNS records
11 | Check DNS servers
12 | Request TTL to 10 minutes
13 | Ensure SEO has been approved
14 | Ensure Analytics has been approved
15 | Test domain mapping in pre-production
16 | Create master cutover ticket - Domain mapping (Ticket #123) - Remove authentication (Ticket #234) - CDN Change in Production (Ticket #345) - 301s (Ticket #456) - Purge CDN cache (Ticket #567)
17 | Go/No-Go Decision

## Cut Over Schedule
Activity | Ticket | Start Time | End Time | Duration | Owner
Implement Domain Mapping | Tick-123 | 6:00 | 9:00 | :180 | Infrastructure Mgr.
Call Begins |  | 9:00 | 9:05 | :05 | Agency
Remove Authentication | Tick-234 | 9:05 | 9:10 | :10 | Host Provider
Implement CDN change | Tick-345 | 9:10 | 10:10 | :60 | Infrastructure Mgr.
Confirm DNS Change is live |  | 10:10 | 10:25 | :15 | CDN
Implement 301s | Tick-456 | 10:25 | 10:40 | :15 | Infrastructure Mgr.
Purge CDN cache | Tick-567 | 10:40 | 10:45 | :05 | Infrastructure Mgr.
Perform sanity check and remind participants to clear browser cache |  | 10:45 | 11:45 | :60 | QA All
End to End Testing |  | 10:45 | 11:45 | :60 | QA All
Read out all reported findings |  | 11:45 | 12:00 | :15 | Agency
Stay-alive / Back-out decision |  | 12:00 | 12:00 | :00 | Client

## Contact List
Name | Company | Role | E-Mail