| Legend | Exceeds expectations = 30; Meets Expectations = 20; Below expectations = 10 |
| --- | --- |
| Process | Select the most appropriate legend value from above for each assessed |
|  | checkpoint below. Sum the Total Achieved Points and divide into Total |
|  | Points Possible for Final Percentage Grade. Internal Auditing and/or |  |
|  | PMO determine Legend expectations. |  |  |  |  |
|  | Project is considered a "high" Project Fraud risk if "Final Percentage Grade" |
|  | is less than 70%. |  |  |  |  |  |  |
|  | Checklist Categories are considered "high" risk if category score is below 70%. |
| Business Case Justification |  |  |  |  |
|  | Problem Opportunity |  |  | ________ |  |  |
|  | Gap Assessment Completed |  |  | ________ |  |  |
|  | High Level Benefit Analysis |  |  | ________ |  |  |
|  | Customer Needs Assessed |  |  | ________ |  |  |
|  | Strategic Alignment Determined |  |  | ________ |  |  |
|  | Project Priorities |  |  |  | ________ |  |  |
|  | Project Interdependencies |  |  | ________ |  |  |
|  | Market Impact-High Level |  |  | ________ |  |  |
|  | Risk/Impact of no action |  |  | ________ |  |  |
|  | Alternative Options to Project |  |  | ________ |  |  |
|  | Score |  |  |  |  | ________ |  |  |
| Project Charter |  |  |  |  |  |  |
|  | Project Demographics |  |  | ________ |  |  |
|  | Problem/Opportunity Statement |  |  | ________ |  |  |
|  | Project Objective |  |  |  | ________ |  |  |
|  | Magnitude |  |  |  | ________ |  |  |
|  | Deliverables |  |  |  | ________ |  |  |
|  | Level of Authority |  |  |  | ________ |  |  |
|  | Change Management Plan |  |  | ________ |  |  |
|  | Financial Resources |  |  |  | ________ |  |  |
|  | Expected Activities |  |  |  | ________ |  |  |
|  | Project Interdependencies |  |  | ________ |  |  |
|  | Project Intradependencies |  |  | ________ |  |  |
|  | Value/Priority |  |  |  | ________ |  |  |
|  | Assumptions |  |  |  | ________ |  |  |
|  | Risks |  |  |  |  | ________ |  |  |
|  | Constraints |  |  |  | ________ |  |  |
|  | Sponsor Approval |  |  |  | ________ |  |  |
|  | Score |  |  |  |  | ________ |  |  |
| Project Infrastructure |  |  |  |  |  |  |
|  | Assumptions List |  |  |  | ________ |  |  |
|  | Responsibility Matrix |  |  |  | ________ |  |  |
|  | Task Description Worksheet |  |  | ________ |  |  |
|  | Task Estimating Worksheet |  |  | ________ |  |  |
|  | Work Breakdown Structure List |  |  | ________ |  |  |
|  | Project Scope Change Log |  |  | ________ |  |  |
|  | Score |  |  |  |  | ________ |  |  |
| Work Breakdown Structure Review |  |  |  |  |
|  | All tasks to accomplish the project |  | ________ |  |  |
|  | are identified |  |  |  |  |  |  |
|  | WBS is structured as information |  | ________ |  |  |
|  | will be used |  |  |  |  |  |  |
|  | Levels of detail allow for realistic |  |  | ________ |  |  |
|  | estimating |  |  |  |  |  |  |  |
|  | Levels of detail allow assignment to single |  | ________ |  |  |
|  | organizational control unit |  |  |  |  |  |
|  | Level of detail is limited to level of control |  | ________ |  |  |
|  | The result of each lowest level is a |  | ________ |  |  |
|  | deliverable |  |  |  |  |  |  |
|  | An action verb initiates each WBS |  | ________ |  |  |
|  | description |  |  |  |  |  |  |
|  | Score |  |  |  |  | ________ |  |  |
| Estimate Review |  |  |  |  |  |  |
|  | Review the definition of the project |  | ________ |  |  |
|  | Review the ground rules, constraints, |  | ________ |  |  |
|  | and assumptions |  |  |  |  |  |  |
|  | Focus on the sources of the data |  | ________ |  |  |
|  | Determine whether the estimating |  | ________ |  |  |
|  | methodology is acceptable |  |  |  |  |  |
|  | Review the resources to be used and |  | ________ |  |  |
|  | the activity costs |  |  |  |  |  |  |
|  | Compare estimate against best practices |  | ________ |  |  |
|  | industry standards |  |  |  |  |  |  |
|  | Analyze activity and resource cost drivers |  | ________ |  |  |
|  | Ensure that estimate incorporates risk |  | ________ |  |  |
|  | Score |  |  |  |  | ________ |  |  |
| Project Scheduling |  |  |  |  |  |  |
|  | Master Schedule developed in detail? |  | ________ |  |  |
|  | Project Sponsor and Customer agree |  | ________ |  |  |
|  | on Master Schedule? |  |  |  |  |  |
|  | Master Schedule achievable? |  |  | ________ |  |  |
|  | Agreement among all functional |  |  | ________ |  |  |
|  | organizations for the execution of the |  |  |  |  |
|  | defined project tasks? |  |  |  |  |  |
|  | Project Network Schedule been developed |  | ________ |  |  |
|  | that includes all project tasks? |  |  |  |  |  |
|  | Critical Path identified? |  |  | ________ |  |  |
|  | Does the Critical Path satisfy the Master Schedule | ________ |  |  |
|  | with sufficient contingency for surprises? |  |  |  |  |
|  | Are all team members committed to the planned | ________ |  |  |
|  | approach to project execution? |  |  |  |  |  |
|  | Have detailed schedules been developed for | ________ |  |  |
|  | the individual tasks of the project? |  |  |  |  |
|  | Are the performing organizations signed up and | ________ |  |  |
|  | committed to executing these tasks as described? |  |  |  |
|  | Have project risks been evaluated at all levels | ________ |  |  |
|  | with appropriate risk management actions |  |  |  |  |
|  | incorporated into the planning for project execution? | ________ |  |  |
|  | Score |  |  |  |  | ________ |  |  |
| Project Risk Management Model |  |  |  |  |
|  | Risk Identification |  |  |  | ________ |  |  |
|  | Risk Quantification |  |  |  | ________ |  |  |
|  | Risk Response Development |  |  | ________ |  |  |
|  | Risk Response Control |  |  | ________ |  |  |
|  | Score |  |  |  |  | ________ |  |  |
| Management Evaluation |  |  |  |  |  |
|  | Are the project goals and objectives realistic? | ________ |  |  |
|  | Is the resource allocation plan realistic? |  | ________ |  |  |
|  | Is the project budget reasonable? |  | ________ |  |  |
|  | Is the project schedule feasible? |  | ________ |  |  |
|  | Is the project organization structure sound? | ________ |  |  |
|  | Are the control systems adequate? |  | ________ |  |  |
|  | Are project management tools being |  | ________ |  |  |
|  | applied to the project on a regular basis? |  |  |  |  |
|  | Is the risk management plan being followed |  | ________ |  |  |
|  | and updated? |  |  |  |  |  |  |
|  | Are management reserves adequate? |  | ________ |  |  |
|  | Score |  |  |  |  | ________ |  |  |
| Organizational Evaluation |  |  |  |  |  |
|  | Does the project organization contribute to the | ________ |  |  |
|  | project goals and objectives? |  |  |  |  |  |
|  | Does the project manager exercise adequate | ________ |  |  |
|  | authority? |  |  |  |  |  |  |  |
|  | Do the project team members know their |  | ________ |  |  |
|  | roles within the project matrix? |  |  |  |  |  |
|  | Does the customer (internal or external) |  | ________ |  |  |
|  | understand the project organization? |  |  |  |  |
|  | Is there adequate communication within the | ________ |  |  |
|  | project matrix? |  |  |  |  |  |  |
|  | Is the project team kept abreast of ongoing |  | ________ |  |  |
|  | developments within the project? |  |  |  |  |
|  | Do documented project status meeting minutes | ________ |  |  |
|  | exist? |  |  |  |  |  |  |  |
|  | Score |  |  |  |  | ________ |  |  |

| Project Control |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Where is the project relative to the schedule? | ________ |  |  |
|  | Where is the project relative to cost? |  | ________ |  |  |
|  | Where is the project with respect to meeting | ________ |  |  |
|  | specifications? |  |  |  |  |  |  |
|  | Where is the project with respect to overall |  | ________ |  |  |
|  | objectives and goals? |  |  |  |  |  |
|  | Where are the WBS elements with respect to | ________ |  |  |
|  | the project schedule? |  |  |  |  |  |
|  | Where are the WBS elements with respect to | ________ |  |  |
|  | costs? |  |  |  |  |  |  |  |
|  | Where are the WBS elements with respect to | ________ |  |  |
|  | meeting technical requirements? |  |  |  |  |
|  | Where are the WBS elements with respect to | ________ |  |  |
|  | project goals and objectives? |  |  |  |  |  |
|  | Project areas execution expectations? |  | ________ |  |  |
|  | What concerns are developing within the | ________ |  |  |
|  | project? |  |  |  |  |  |  |  |
|  | What risks and opportunities are evolving from | ________ |  |  |
|  | the project? |  |  |  |  |  |  |
|  | Is the project still in line with organizational |  | ________ |  |  |
|  | objectives? |  |  |  |  |  |  |
|  | Is the client/customer satisfied? |  |  | ________ |  |  |
|  | Is the project team satisfied? |  |  | ________ |  |  |
|  | Have outside sources examined project progress? | ________ |  |  |
|  | Is the project team functioning well? |  | ________ |  |  |
|  | Is the project still a strategic fit for the |  | ________ |  |  |
|  | organization? |  |  |  |  |  |  |
|  | Does the project remain profitable? |  | ________ |  |  |
|  | Are there any potential showstoppers on |  | ________ |  |  |
|  | the project horizon? |  |  |  |  |  |  |
|  | Score |  |  |  |  | ________ |  |  |
| Tota | tal Score |  |  |  | ________ |  |  |
|  | Fina Grade (Total Achieved Score / Total Possible Score as a %) |  |  |  |
|  |  |  |  |  | ________ |  |  |