## intro
Relocating the Library of the Accounting profession
Kepner Tregoe Decision Analysis
Kepner Tregoe decision analysis is a method whereby the decision variables in a decision are identified, documented, and assessed in a quantitative fashion for the various alternatives in the decision.
The method first ensures that the alternatives meet the Must Have requirements (those choices that do meet these requirements are out of the analysis )
Then, the method rates the alternatives on desirables which are weighted as to their importance (e.g., is customer service more important than the business school)
Finally, the method assess any risks associated with the alternative
Given the above quantitative information, a decision is made on the final choice

## todo
Todo
1 | Rate the desirables from 1-10
2 | Note whether all must haves are met
3 | Note any risks in school (e.g., politics of NY based library)
4 | Provide a summary in the details area for each desirable based on response
5 | Based on summary, rate the university desirables
6 | Re-assess the risk areas based on summary
7 | Send to Library team for review of analysis
8 | Write a concluding paragraph explaining decision

## decision
Selecting a Vendor
Decision Analysis
I. | Must Have |  | Vendor A | Vendor B
1 | System must be developed in Visual Basic/SQL Server |  | Y | Y
2 | System must cost less than $1,000,000 |  | Y | Y
Scores (1 - 10 x Rating)
[5 empty] | Score | Score
II. | Desirable | Weight | Vendor A | Vendor B | Vendor A | Vendor B
1 | Financial Stability | 8 | 80 | 64 | 10 | 8
2 | Referential Experience | 9 | 72 | 63 | 8 | 7
3 | Ability to Meet Deadlines | 7 | 28 | 56 | 4 | 8
4 | Software Documentation Guidelines | 5 | 40 | 40 | 8 | 8
5 |  |  | 0 | 0
6 |  |  | 0 | 0
7 |  |  | 0 | 0
| Final Score |  | 220 | 223
III. | Risks |  | Vendor A | Vendor B