## Strategic PM Checklist
# | Strategic Project Management Questions | Assessment / Comments
High-level Planning
1 | Does the team understand that planning never ends and continuous improvement throughout all project phases is necessary for success?
2 | Is the project even necessary, or would operational process improvements suffice to meet the business needs?
3 | Is the project sponsor clearly identified and actively engaged in all planning activities for the project?
4 | Have estimated timelines been identified for each project phase?
5 | Have estimated costs been identified for each project phase?
6 | Have all expenses been identified?
7 | Have resources, by roles, been clearly identified and documented for each project phase?
8 | Have project 'quick hits' been identified that to show incremental value?
9 | Are plans in place to celebrate the attainment of quick hits and business value to reward and motivate the team?
10 | Do project team members have the requisite skill sets to quantify, track and achieve business benefits?
11 | Are team members thinking strategically about the project, as opposed to simply thinking on-time and within budget?
12 | Are project team members apprised of pending organizational changes due to mergers, acquisitions and ongoing reorganizations?
13 | Do team members fully understand the quantitative metrics the project is trying to achieve?
14 | Do team members fully understand the qualitative metrics the project is trying to achieve?
15 | Have time zone differences been taken into account for all meetings other key events?
16 | Has the corporate culture been taken into account, even across functional and geographic boundaries?
17 | Have regulatory requirements in the different operating regions been addressed?
18 | Is the team being flexible and adaptive to changing business circumstances?
19 | Have all training requirements been identified and training plans developed across business units?
20 | Have real decision-maker been identified and incorporated into the project?
21 | Has business readiness been incorporated into the overall approach for the changes the project will bring to the organization?
22 | Are there plans to prepare the business to be ready for the change and are they willing to change existing behaviors and processes?
Project Alignment to Corporate Strategy
23 | Can all team members recite the corporate mission statement verbatim?
24 | Do all team member know the strategic objectives of the company and/or department?
25 | Does a business plan exist that outlines the strategic objectives?
26 | Does the project align directly to the strategic objectives and mission?
27 | Are the project benefits prioritized, focusing first on the business objectives that add true value to the organization?
Project Plan
28 | Does a team understand that a plan is worthless, but planning is indispensable? (the plan will change!)
29 | Is the plan focused on quality and not quantity?
30 | Are project management teams spending too much time managing the plan, and not the team?
31 | Is the plan being treated as a 'living' document, even after approval or signoff?
32 | Even though the plan is constantly evolving, are measures being taken to avoid scope creep?
33 | Is the best and most appropriate project management methodology being deployed given the corporate culture and business requirements?
34 | Are all the key deliverables identified?
35 | Have all in-and out-of-scope items been documented?
36 | Have all the known project dependencies and constraints been identified?
37 | Are business case development activities incorporated into the planning phases?
38 | Are activities for benefits realization identified and documented?
39 | Are activities for metrics reporting identified for the useful life of the project?
40 | Are the project timelines realistic?
41 | Does project closure only happen once the business benefits have been attained?
42 | Have regulatory impacts been identified?
43 | Have all impacted business processes been identified and communicated to the business?
44 | Does the project plan incorporate organizational change management activities?
45 | Is the success criteria for this project clearly captured?
46 | Has the project sponsor reviewed and approved the project plan?
Business Case
47 | Are project leaders being included in the business case development activities?
48 | Is the current business situation clearly articulated?
49 | Is the problem/opportunity statement clear and concise?
50 | Does the project clearly align to enterprise priorities and strategic objectives?
51 | Have all assumptions and estimates been clearly documented, especially regarding forecasts?
52 | Is there clear justification for why the company should invest in this project?
53 | Have all of the business benefits been captured from the following categories: cost savings, business growth, time-related, performance-related, quality-related?
54 | Have all the considered solution options been documented?
55 | Were all the pros and cons for each solution option clearly documented?
56 | Is the preferred solution option clearly defined?
57 | Are realistic cash flow models developed to support project ROI?
58 | Is the time-value-of-money incorporated into the cash flow models?
59 | Is the appropriate discount rate (WACC) being used?
60 | Has each benefit been subjected to sensitivity analysis?
61 | Have baseline (current state) metrics been captured?
62 | Have future state benefit metrics been forecasted realistically?
63 | Are the key ROI financial metrics calculated, to include NPV, IRR and payback period? Are they realistic?
64 | Are the key non-ROI metrics or benefits included?
65 | Has each benefit been assessed for risk?
66 | Have the benefits been signed off by the target business owner(s)?
67 | Has the business case been reviewed and approved by the project sponsor?
68 | Has the business case been validated with senior leadership?
69 | Is the business case treated as a living document?
Benefits Realization
70 | Are the business benefits clearly identified and prioritized?
71 | Are there benefit realization plans for each of the identified benefits?
72 | Is the benefits realization plan an extension of the business case?
73 | Are there clearly established dates to achieve the benefits?
74 | Are measurement systems identified and implemented to track benefits?
75 | Are benefit reporting procedures clearly identified and adhered to?
76 | Are benefit owners identified?
77 | Are benefit owners accountable for achieving the benefits?
78 | Are management teams ready to take corrective action if benefits are not being achieved or on track?
79 | Have the benefit beneficiaries been identified and communicated to?
80 | Have risk elements been identified for each of the forecasted benefits?
81 | Do the benefit realization plans have strong stakeholder support and commitment?
82 | Are the dependencies clearly established to attaining all of the business benefits?
83 | Are the baselines from which to measure success clearly documented?
Stakeholder Management
84 | Have all stakeholder roles and responsibilities been clearly identified?
85 | Has the list of stakeholders been validated with the project sponsor?
86 | Does the list include potential external stakeholders?
87 | Are project leaders managing up the chain of command and not just down?
88 | Are project leaders being proactive in mobilizing and re-mobilizing commitment from the stakeholders?
89 | Are project leaders encouraging senior stakeholders to get 'in the trenches' to support the project and motivate the team?
90 | Are any of the stakeholders 'checking out?' If so, are proactive measures being taken to get them back on board?
91 | Are all stakeholders properly engaged from the outset in defining, agreeing and working together to achieve the benefits?
92 | Can all the stakeholders answer the question, "What's in it for me?"
93 | Have approximate time commitments per stakeholder group, by project phase, been captured and communicated?
94 | Has the list of stakeholders been updated based on clarification of the requirements?
95 | Has a RASCI diagram been completed to clearly define the various roles?
96 | Are the stakeholders being leveraged appropriately in order to achieve and optimize the intended benefits?
Communication Strategy
97 | Have all the potential communications audiences been identified?
98 | Has the objective of each communication been clearly identified?
99 | Has a stakeholder meeting schedule and cadence been established?
100 | Are stakeholders receiving the right amount of information, and not too much or not enough?
101 | Are Voice of the Customer (VoC) sessions being conducted?
102 | Is business value being determined from the perspective of the customer?
103 | Have the person(s) been identified for communicating information to senior stakeholders?
104 | Are the communication methods and frequency appropriate?
105 | Have the person(s) been identified for communicating information to external stakeholders?
106 | Has the frequency been established as to how often information will be communicated to internal and external stakeholders?
107 | Is the project team continuously improving communication methods and channels?
108 | Are appropriate escalations being performed, or is the project team constantly 'crying wolf' or not escalating enough?
109 | Are escalation plans in place?
Project Handoff to Business Operations
110 | Are key members of the business (customers of the project) playing active roles in the project?
111 | Are proactive measures being taken to ensure the business if fully prepared for the change that the project will deliver?
112 | Have specific scenarios that require testing by the business been identified?
113 | Are User Acceptance Test (UAT) plans and procedures in place?
114 | Have business owner been clearly identified to perform user acceptance testing?
115 | Has a deployment/cutover/Go Live plan been developed and distributed?
116 | Is the deployment plan integrated with business/operations and IT activities?
117 | Does the deployment plan include roll back procedures?
118 | Are procedures in place for measurement and reporting of deployment success metrics?
119 | Is there a clear transition plan to operations personnel?
120 | Have all the impacted future state business processes been identified?
121 | Has an operational owner been identified for each business process?
122 | If processes will require support, have support resources been identified?
123 | Is there thorough process documentation for the business users to leverage?
124 | Are training plans in place and have initial training dates been identified?
125 | Have initial transition costs been identified?
126 | Are there processes for monitoring and reporting production issues?
127 | Have continuous improvement processes been identified that extend beyond project closure?
Lessons Learned
128 | Are lessons learned sessions being conducted throughout the project, and not just at the conclusion?
129 | Are the lessons learned predictable, lacking in depth and add very little value to the cause, or are they meaningful that can improve the overall project?
130 | Is positive change resulting from the lessons learned sessions?
131 | Have lessons learned from other projects been leveraged?
132 | Is there a centralized repository for all project lessons learned documentation?
133 | Was the project successful?
134 | Did the project achieve its intended benefits?
135 | Did the project contribute to the company's bottom line?
136 | Did the project increase the company's competitive posture?
137 | Are plans in place to continue monitoring and reporting on the key project metrics?
138 | Were all stakeholders involved in the preparation of a formal lessons learned closeout presentation?
139 | How can the project be leveraged to continue building business value for the company?
140 | Have the lessons learned documentation been posted to a centralized repository for other project teams to leverage?