## Who Does What
Task | Duration | Start | Finish | Predecessors | Resource Names
Start | 1 day? | 2012-06-06 08:00 | 2012-06-06 17:00
Feasibility Study | 23.5 days? | 2012-06-07 08:00 | 2012-07-10 12:00
Decide to outsource or handle in-house | 1 day? | 2012-06-07 08:00 | 2012-06-07 17:00 | 1 | Mgt
Set objectives | 0.5 days? | 2012-06-07 08:00 | 2012-06-07 12:00 | 1 | Mgt,Customer
Define scope | 2 days | 2012-06-07 13:00 | 2012-06-11 12:00 | 4 | Mgt,Customer
Elicit and gather information processing requirements | 5 days | 2012-06-11 13:00 | 2012-06-18 12:00 | 5 | Contractor1
Analyze and establish information processing needs | 2 days | 2012-06-18 13:00 | 2012-06-20 12:00 | 6,3 | Contractor1
Define proposed IT infrastructure | 2 days | 2012-06-20 13:00 | 2012-06-22 12:00 | 7 | Contractor1
Define support infrastructure | 2 days | 2012-06-20 13:00 | 2012-06-22 12:00 | 7 | Contractor1
Define organizational structure | 2 days | 2012-06-20 13:00 | 2012-06-22 12:00 | 7 | Contractor1
Define the deliverables | 1 day | 2012-06-20 13:00 | 2012-06-21 12:00 | 7 | Contractor1
Define the security arrangements | 2 days | 2012-06-20 13:00 | 2012-06-22 12:00 | 7 | Contractor1
Estimate the cost of IT infrastructure | 3 days | 2012-06-22 13:00 | 2012-06-27 12:00 | 8 | Contractor1
Estimate the cost of support infrastructure | 3 days | 2012-06-22 13:00 | 2012-06-27 12:00 | 9 | Contractor1
Estimate the cost of annual maintenance costs | 1 day | 2012-06-27 13:00 | 2012-06-28 12:00 | 13,14 | Contractor1
Estimate the operational costs | 2 days | 2012-06-27 13:00 | 2012-06-29 12:00 | 13,14 | Contractor1
Define upgrade path and replacement criteria | 1 day? | 2012-06-22 13:00 | 2012-06-25 12:00 | 8,9,10,11,12 | Contractor1
Prepare report | 3 days | 2012-06-29 13:00 | 2012-07-04 12:00 | 15,16,17 | Contractor1
QC on the report | 1 day | 2012-07-04 13:00 | 2012-07-05 12:00 | 18 | Contractor1
Present the report | 1 day? | 2012-07-05 13:00 | 2012-07-06 12:00 | 19 | Contractor1
Implement feedback and submit the report finally | 2 days | 2012-07-06 13:00 | 2012-07-10 12:00 | 20 | Contractor1
Project Approval | 8 days? | 2012-07-10 13:00 | 2012-07-20 12:00
Compare with competing projects | 2 days | 2012-07-10 13:00 | 2012-07-12 12:00 | 21 | Mgt
Technical appraisal | 3 days | 2012-07-12 13:00 | 2012-07-17 12:00 | 23 | Mgt
Financial appraisal | 3 days | 2012-07-12 13:00 | 2012-07-17 12:00 | 23 | Finance
Technical approval | 2 days | 2012-07-17 13:00 | 2012-07-19 12:00 | 24 | Mgt
Financial approval | 2 days | 2012-07-17 13:00 | 2012-07-19 12:00 | 25 | Finance
Project approval | 1 day? | 2012-07-19 13:00 | 2012-07-20 12:00 | 26,27 | Mgt
Project Planning | 8 days? | 2012-07-20 13:00 | 2012-08-01 12:00
Floor plan | 5 days | 2012-07-20 13:00 | 2012-07-27 12:00 | 28 | Architect
Deployment plan | 3 days | 2012-07-20 13:00 | 2012-07-25 12:00 | 28 | Architect
Software Development plan | 5 days | 2012-07-20 13:00 | 2012-07-27 12:00 | 28 | PM
Installation and commissioning plan | 1 day? | 2012-07-20 13:00 | 2012-07-23 12:00 | 28 | PM
Data preparation plan | 2 days | 2012-07-20 13:00 | 2012-07-24 12:00 | 28 | PM
Training plan | 1 day? | 2012-07-20 13:00 | 2012-07-23 12:00 | 28 | PM
Quality assurance plan | 3 days | 2012-07-20 13:00 | 2012-07-25 12:00 | 28 | PM
Procurement plan | 2 days | 2012-07-20 13:00 | 2012-07-24 12:00 | 28 | PM
Networking plan | 4 days | 2012-07-20 13:00 | 2012-07-26 12:00 | 28 | PM
Risk management plan | 1 day? | 2012-07-20 13:00 | 2012-07-23 12:00 | 28 | PM
Overall project schedule | 5 days | 2012-07-20 13:00 | 2012-07-27 12:00 | 28 | PM
Review project plans | 1 day? | 2012-07-27 13:00 | 2012-07-30 12:00 | 40,30,31,32,33,34,35,36,37,38,39 | QA
Implement review feedback | 1 day? | 2012-07-30 13:00 | 2012-07-31 12:00 | 41 | PM
Approve project plans | 1 day? | 2012-07-31 13:00 | 2012-08-01 12:00 | 42 | Mgt
Sizing | 4 days? | 2012-07-20 13:00 | 2012-07-26 12:00
Webserver | 0.5 days | 2012-07-20 13:00 | 2012-07-20 17:00 | 28 | Contractor1
Database server | 0.5 days | 2012-07-20 13:00 | 2012-07-20 17:00 | 28 | Contractor1
Email server | 0.5 days | 2012-07-20 13:00 | 2012-07-20 17:00 | 28 | Contractor1
Security server | 0.5 days | 2012-07-20 13:00 | 2012-07-20 17:00 | 28 | Contractor1
App server | 0.5 days | 2012-07-20 13:00 | 2012-07-20 17:00 | 28 | Contractor1
Networking hardware | 1 day? | 2012-07-20 13:00 | 2012-07-23 12:00 | 28 | Contractor1
Power requirements | 1 day? | 2012-07-20 13:00 | 2012-07-23 12:00 | 28 | Contractor1
Application Software | 2 days | 2012-07-20 13:00 | 2012-07-24 12:00 | 28 | Contractor1
Make or buy decisions | 2 days | 2012-07-24 13:00 | 2012-07-26 12:00 | 45,46,47,48,49,50,51,52 | Contractor1,Mgt
QC of sizing exercise | 1 day? | 2012-07-24 13:00 | 2012-07-25 12:00 | 45,46,47,48,49,50,51,52 | Contractor1
Feedback and submit sizing report | 1 day? | 2012-07-25 13:00 | 2012-07-26 12:00 | 54 | Contractor1
Recruitment of People for Operations | 18 days? | 2012-08-01 13:00 | 2012-08-27 12:00 | 55
Define the eligibility criteria for all positions | 3 days | 2012-08-01 13:00 | 2012-08-06 12:00 | 43 | PM
Determine the number and classes of people required | 3 days | 2012-08-06 13:00 | 2012-08-09 12:00 | 57 | PM
Raise Requisition on HR for recruitment | 1 day | 2012-08-09 13:00 | 2012-08-10 12:00 | 58 | PM
Scrutinize and Short List applicants for interview | 3 days | 2012-08-10 13:00 | 2012-08-15 12:00 | 59 | HR,PM
Assist HR in conducting Interviews | 2 days | 2012-08-15 13:00 | 2012-08-17 12:00 | 60 | PM
Finalize Candidates | 1 day | 2012-08-17 13:00 | 2012-08-20 12:00 | 61 | PM,HR
Appointment of selected candidates | 2 days | 2012-08-20 13:00 | 2012-08-22 12:00 | 62 | HR
Conduct Induction Training of recruitees | 2 days | 2012-08-22 13:00 | 2012-08-24 12:00 | 63 | HR
Allocate people to project | 1 day? | 2012-08-24 13:00 | 2012-08-27 12:00 | 64 | HR
Procurement | 22.5 days? | 2012-07-26 13:00 | 2012-08-27 17:00
Procurement of Servers | 0.5 days? | 2012-08-27 13:00 | 2012-08-27 17:00 | 43,56 | Purchase,PM
Procurement of Workstations | 0.5 days? | 2012-08-01 13:00 | 2012-08-01 17:00 | 55,43 | Purchase,PM
Procurement of Networking cables | 0.5 days? | 2012-08-01 13:00 | 2012-08-01 17:00 | 55,43 | Purchase,PM
Procurement of Networking hardware | 0.5 days? | 2012-08-01 13:00 | 2012-08-01 17:00 | 55,43 | Purchase,PM
Procurement of System Software | 1 day? | 2012-08-01 13:00 | 2012-08-02 12:00 | 55,43 | Purchase,PM
Preparation of specifications for Application Software | 2 days? | 2012-08-01 13:00 | 2012-08-03 12:00 | 55,43 | PM
Procurement of Application Software | 1 day? | 2012-08-01 13:00 | 2012-08-02 12:00 | 55,43 | Purchase,PM
Finalize Subcontractors | 1 day? | 2012-07-26 13:00 | 2012-07-27 12:00 | 55,53 | Purchase,PM
Facility / Data Center Preparation | 46 days | 2012-07-26 13:00 | 2012-09-28 12:00
Facility Design | 5 days | 2012-07-26 13:00 | 2012-08-02 12:00 | 55 | Architect
Finalize Subcontractor for facility construction | 3 days | 2012-08-02 13:00 | 2012-08-07 12:00 | 76 | Purchase,Mgt
Facility Construction | 30 days | 2012-08-07 13:00 | 2012-09-18 12:00 | 77 | Contractor 2
Electrification of the Facility | 5 days | 2012-09-18 13:00 | 2012-09-25 12:00 | 78 | Contractor 2
Provide Environmental controls | 5 days | 2012-09-18 13:00 | 2012-09-25 12:00 | 78 | Contractor 3
Provide Data Communication facilities | 3 days | 2012-09-18 13:00 | 2012-09-21 12:00 | 78 | Contractor 4
Inspect and takeover Facility / Data Center | 3 days | 2012-09-25 13:00 | 2012-09-28 12:00 | 79,80,81 | Purchase,PM
Installing the servers | 36 days? | 2012-08-27 13:00 | 2012-10-16 12:00
Site preparationn for the data center | 3 days | 2012-08-27 13:00 | 2012-08-30 12:00 | 65 | Contractor 5
Receive and QC Servers | 3 days | 2012-08-30 13:00 | 2012-09-04 12:00 | 84,67 | Contractor 5
Server deployment | 2 days | 2012-09-04 13:00 | 2012-09-06 12:00 | 85 | Contractor 5
Test the servers | 3 days | 2012-09-06 13:00 | 2012-09-11 12:00 | 86 | Contractor 5
Connect servers to the network | 1 day? | 2012-10-15 13:00 | 2012-10-16 12:00 | 87,118 | Contractor 5
Installing the Workstations | 24 days | 2012-10-16 13:00 | 2012-11-19 12:00 | 88
Site preparationn for the Worksations | 4 days | 2012-10-16 13:00 | 2012-10-22 12:00 | 65 | Contractor 5
Receive and QC Workstations | 5 days | 2012-10-22 13:00 | 2012-10-29 12:00 | 90 | Contractor 5
Workstation deployment | 6 days | 2012-10-29 13:00 | 2012-11-06 12:00 | 91 | Contractor 5
Test the Workstations | 5 days | 2012-11-06 13:00 | 2012-11-13 12:00 | 92 | Contractor 5
Connect Workstations to the network | 4 days | 2012-11-13 13:00 | 2012-11-19 12:00 | 93 | Contractor 5
Install System Software | 34 days? | 2012-10-16 13:00 | 2012-12-03 12:00
Install RDBMS | 1 day? | 2012-11-19 13:00 | 2012-11-20 12:00 | 71,65,94 | Contractor 5
Cursory Testing of RDBMS | 1 day? | 2012-11-20 13:00 | 2012-11-21 12:00 | 96 | Contractor 5
Install Email Exchange Software | 2 days | 2012-10-16 13:00 | 2012-10-18 12:00 | 88,71 | Contractor 5
Cusrsory Testing of Email Exchange Software | 1 day? | 2012-10-18 13:00 | 2012-10-19 12:00 | 98 | Contractor 5
Install Middle Tier Software | 1 day? | 2012-10-16 13:00 | 2012-10-17 12:00 | 88,71 | Contractor 5
Cursory Testing of Middle Tier Software | 1 day? | 2012-10-17 13:00 | 2012-10-18 12:00 | 100 | Contractor 5
Install Configuration Management Software | 1 day? | 2012-10-16 13:00 | 2012-10-17 12:00 | 88,71 | Contractor 5
Cursory Testing of Configuration Management Software | 1 day? | 2012-10-17 13:00 | 2012-10-18 12:00 | 102 | Contractor 5
Install Security Software | 1 day? | 2012-11-21 13:00 | 2012-11-22 12:00 | 97,99,101,103,71 | Contractor 5
Cursory Testing of Security Software | 1 day? | 2012-11-22 13:00 | 2012-11-23 12:00 | 104 | Contractor 5
Install Network Monitoring Software | 1 day? | 2012-11-23 13:00 | 2012-11-26 12:00 | 105,71 | Contractor 5
Cursory Testing of Network Monitoring Software | 1 day? | 2012-11-26 13:00 | 2012-11-27 12:00 | 106 | Contractor 5
Install Backup/Restore Software | 1 day? | 2012-11-27 13:00 | 2012-11-28 12:00 | 107,71 | Contractor 5
Cursory Testing of Backup/Restpre Software | 1 day? | 2012-11-28 13:00 | 2012-11-29 12:00 | 108 | Contractor 5
Install Administrative Utilities | 1 day? | 2012-11-29 13:00 | 2012-11-30 12:00 | 109,71 | Contractor 5
Cursory Testing of Administrative Utilities | 1 day? | 2012-11-30 13:00 | 2012-12-03 12:00 | 110 | Contractor 5
Networking | 66.5 days? | 2012-07-27 13:00 | 2012-10-29 17:00
Receive Networking Cables | 1 day? | 2012-09-28 13:00 | 2012-10-01 12:00 | 82,69,65 | Contractor 4
Receive Networking Hardware | 1 day? | 2012-09-28 13:00 | 2012-10-01 12:00 | 82,70 | Contractor 4
Finalize Networking Subcontractor | 1 day? | 2012-07-27 13:00 | 2012-07-30 12:00 | 74 | Contractor 4
Install the router | 1 day? | 2012-10-01 13:00 | 2012-10-02 12:00 | 114,115 | Contractor 4
Install the network switches | 1 day? | 2012-10-01 13:00 | 2012-10-02 12:00 | 114,115 | Contractor 4
Laying of the network cables | 10 days | 2012-10-01 13:00 | 2012-10-15 12:00 | 115,113 | Contractor 4
Connecting cables to the equipment | 5 days | 2012-10-15 13:00 | 2012-10-22 12:00 | 118 | Contractor 4
Establishing connectivity to the Internet | 1 day? | 2012-10-22 13:00 | 2012-10-23 12:00 | 116,119,117 | Contractor 4
Testing the network | 4 days | 2012-10-23 13:00 | 2012-10-29 12:00 | 120 | Contractor 4,Network Engineer
handover the network to network administrators | 0.5 days? | 2012-10-29 13:00 | 2012-10-29 17:00 | 121 | Contractor 4,PM
Receive and Deploy Application Software | 98 days? | 2012-08-03 13:00 | 2012-12-19 12:00
Finalize Subcontractor | 1 day | 2012-08-03 13:00 | 2012-08-06 12:00 | 74,72,73 | Purchase,PM
Assist Subcontractor in finalizing Requirements | 9 days | 2012-08-06 13:00 | 2012-08-17 12:00 | 124 | Dev Team,PM
Review and approve Software Design | 3 days | 2012-08-17 13:00 | 2012-08-22 12:00 | 125 | PM
Development of application software | 50 days | 2012-08-22 13:00 | 2012-10-31 12:00 | 126 | Dev Team
Review Quality Records of software development | 3 days | 2012-10-31 13:00 | 2012-11-05 12:00 | 127 | QA
Prepare Acceptance Test Plan and Test Cases | 5 days | 2012-08-22 13:00 | 2012-08-29 12:00 | 126 | Dev Team,QA
Conduct Acceptance Testing of Application Software | 3 days | 2012-08-29 13:00 | 2012-09-03 12:00 | 129 | Dev Team
Accept Delivery of Application Software | 2 days | 2012-12-03 13:00 | 2012-12-05 12:00 | 111,130,128 | QA,PM
Install Database on the server | 1 day? | 2012-12-05 13:00 | 2012-12-06 12:00 | 131,97 | Dev Team
Install Server Components of the Application Software | 1 day? | 2012-12-05 13:00 | 2012-12-06 12:00 | 131,101 | Dev Team
Install Workstation Components, if any, on the Workstations | 2 days | 2012-12-05 13:00 | 2012-12-07 12:00 | 131,68 | Dev Team
Cursory Testing of installed Application Software | 2 days | 2012-12-07 13:00 | 2012-12-11 12:00 | 132,133,134,122 | Dev Team
Define Roles and Responsibilities of Configuration Management | 2 days | 2012-12-11 13:00 | 2012-12-13 12:00 | 135 | Dev Team,PM
Configure Security in the Configuration Management Tool | 3 days | 2012-12-13 13:00 | 2012-12-18 12:00 | 136 | Dev Team
Initiate Configuration Management of Application Software | 1 day | 2012-12-18 13:00 | 2012-12-19 12:00 | 137 | Dev Team,PM
Master data preparation | 27 days? | 2012-08-22 13:00 | 2012-09-28 12:00
Create Master data tables | 2 days | 2012-08-27 13:00 | 2012-08-29 12:00 | 126,65 | Dev Team
Identify data preparation agencies | 1 day | 2012-08-22 13:00 | 2012-08-23 12:00 | 126 | PM,Purchase
Select the agency for preparing the data | 1 day | 2012-08-23 13:00 | 2012-08-24 12:00 | 141 | PM,Purchase
Place work order | 1 day | 2012-08-24 13:00 | 2012-08-27 12:00 | 142 | PM,Purchase
Provide master data | 3 days | 2012-08-27 13:00 | 2012-08-30 12:00 | 143 | PM,Purchase
Receive data | 10 days | 2012-08-30 13:00 | 2012-09-13 12:00 | 144 | Dev Team
Inward QC of received data | 2 days | 2012-09-13 13:00 | 2012-09-17 12:00 | 145 | Dev Team
Load the data in master data tables | 3 days | 2012-09-17 13:00 | 2012-09-20 12:00 | 146 | Dev Team
Verify master data | 2 days | 2012-09-20 13:00 | 2012-09-24 12:00 | 147 | QA
Make payments to the agency | 1 day | 2012-09-24 13:00 | 2012-09-25 12:00 | 148 | PM,Purchase
Close the work order | 1 day? | 2012-09-25 13:00 | 2012-09-26 12:00 | 149 | Purchase
Handover data to maintenance team | 2 days | 2012-09-26 13:00 | 2012-09-28 12:00 | 150 | PM
Data Migration | 17 days | 2012-08-22 13:00 | 2012-09-14 12:00
Study the existing data formats | 3 days | 2012-08-22 13:00 | 2012-08-27 12:00 | 126 | Dev Team
Study the new data format | 2 days | 2012-08-22 13:00 | 2012-08-24 12:00 | 126 | Dev Team
Map the data migration path | 3 days | 2012-08-27 13:00 | 2012-08-30 12:00 | 153,154 | Dev Team
Develop software to migrate data | 5 days | 2012-08-30 13:00 | 2012-09-06 12:00 | 155 | Dev Team
Quality control of the software | 2 days | 2012-09-06 13:00 | 2012-09-10 12:00 | 156 | QA
Perform data migration using the software | 3 days | 2012-09-10 13:00 | 2012-09-13 12:00 | 157 | Dev Team
Data entry for newly created fields | 5 days | 2012-08-30 13:00 | 2012-09-06 12:00 | 155 | Contractor 6
Load missing data into master data tables | 2 days | 2012-09-06 13:00 | 2012-09-10 12:00 | 159 | Dev Team
Perform quality control actvities | 2 days | 2012-09-10 13:00 | 2012-09-12 12:00 | 160 | Dev Team
Handover data to maintenance team | 1 day | 2012-09-13 13:00 | 2012-09-14 12:00 | 160,158 | PM
Define Systems and Procedures | 15.5 days? | 2012-12-05 13:00 | 2012-12-26 17:00
Define Processes for Managing the IT Infrastructure | 2 days | 2012-12-05 13:00 | 2012-12-07 12:00 | 131,65 | Process Group
Review the Processes for Managing the IT Infrastructure | 1 day | 2012-12-07 13:00 | 2012-12-10 12:00 | 164 | QA
Define Procedures for Support Activities | 2 days | 2012-12-05 13:00 | 2012-12-07 12:00 | 131 | Process Group
Review Procedures for Support Activities | 1 day? | 2012-12-07 13:00 | 2012-12-10 12:00 | 166 | Process Group
Rollout Procedures for Support Activities | 0.5 days? | 2012-12-10 13:00 | 2012-12-10 17:00 | 165,167 | PM,Process Group
Define SLAs for support Activities | 1 day? | 2012-12-11 08:00 | 2012-12-11 17:00 | 168 | Process Group
Define Disaster Management Procedures | 2 days | 2012-12-12 08:00 | 2012-12-13 17:00 | 169 | Process Group
Review Disaster Management Proccedures | 1 day? | 2012-12-14 08:00 | 2012-12-14 17:00 | 170 | QA
Rollout Disaster Management Procedures | 0.5 days? | 2012-12-17 08:00 | 2012-12-17 12:00 | 171 | PM,Process Group
Define Backup/Restore Procedures | 2 days | 2012-12-12 08:00 | 2012-12-13 17:00 | 169 | Process Group
Review Backup/Restore Procedures | 2 days | 2012-12-14 08:00 | 2012-12-17 17:00 | 173 | QA
Rollout Backup/Restore Procedures | 0.5 days? | 2012-12-18 08:00 | 2012-12-18 12:00 | 174 | PM,Process Group
Define Safety and Security Procedures | 2 days | 2012-12-17 13:00 | 2012-12-19 12:00 | 172 | Process Group
Review Safety and Security Procedures | 1 day? | 2012-12-19 13:00 | 2012-12-20 12:00 | 176 | QA
Rollout Safety and Security Procedures | 0.5 days? | 2012-12-20 13:00 | 2012-12-20 17:00 | 177 | PM,Process Group
Define System Audit Procedures | 2 days | 2012-12-21 08:00 | 2012-12-24 17:00 | 178 | Process Group
Review System Audit Procedures | 1 day? | 2012-12-25 08:00 | 2012-12-25 17:00 | 179 | QA
Rollout System Audit Procedures | 0.5 days? | 2012-12-26 08:00 | 2012-12-26 12:00 | 180 | PM,Process Group
Systems and procedures rolled out | 0.5 days? | 2012-12-26 13:00 | 2012-12-26 17:00 | 168,172,175,181,177 | Process Group,PM
End user training | 12 days | 2012-12-27 08:00 | 2013-01-11 17:00
Prepare training materials | 5 days | 2012-12-27 08:00 | 2013-01-02 17:00 | 182 | Trg Grp
Plan the training | 1 day | 2013-01-03 08:00 | 2013-01-03 17:00 | 184 | Trg Grp
Arrange faciltiies | 3 days | 2013-01-04 08:00 | 2013-01-08 17:00 | 185 | Trg Grp
Conduct training | 2 days | 2013-01-09 08:00 | 2013-01-10 17:00 | 186 | Trg Grp
Obtain feedback and analyse | 1 day | 2013-01-11 08:00 | 2013-01-11 17:00 | 187 | Trg Grp,PM
System Administration Training | 10.5 days? | 2012-11-19 13:00 | 2012-12-03 17:00
Prepare training materials | 5 days | 2012-11-19 13:00 | 2012-11-26 12:00 | 88,94,122 | Trg Grp
Plan the training | 1 day? | 2012-11-26 13:00 | 2012-11-27 12:00 | 190 | Trg Grp
Arrange faciltiies | 3 days | 2012-11-27 13:00 | 2012-11-30 12:00 | 191 | Trg Grp
Conduct training | 1 day? | 2012-11-30 13:00 | 2012-12-03 12:00 | 192 | Trg Grp
Obtain feedback and analyse | 0.5 days? | 2012-12-03 13:00 | 2012-12-03 17:00 | 193 | Trg Grp,PM
Network administration training | 10.5 days? | 2012-10-30 08:00 | 2012-11-13 12:00
Prepare training materials | 5 days | 2012-10-30 08:00 | 2012-11-05 17:00 | 122 | Trg Grp
Plan the training | 2 days | 2012-11-06 08:00 | 2012-11-07 17:00 | 196 | Trg Grp
Arrange faciltiies | 2 days | 2012-11-08 08:00 | 2012-11-09 17:00 | 197 | Trg Grp
Conduct training | 1 day? | 2012-11-12 08:00 | 2012-11-12 17:00 | 198 | Trg Grp
Obtain Feedback and Analyze | 0.5 days? | 2012-11-13 08:00 | 2012-11-13 12:00 | 199 | Trg Grp,PM
Manager training | 9.5 days? | 2012-12-27 08:00 | 2013-01-09 12:00
Prepare training materials | 4 days | 2012-12-27 08:00 | 2013-01-01 17:00 | 182 | Trg Grp
Plan the training | 2 days | 2013-01-02 08:00 | 2013-01-03 17:00 | 202 | Trg Grp
Arrange faciltiies | 2 days | 2013-01-04 08:00 | 2013-01-07 17:00 | 203 | Trg Grp
Conduct training | 1 day? | 2013-01-08 08:00 | 2013-01-08 17:00 | 204 | Trg Grp
Obtain feedback and analyse | 0.5 days? | 2013-01-09 08:00 | 2013-01-09 12:00 | 205 | Trg Grp,PM
Maintenance team training | 13.5 days? | 2012-12-27 08:00 | 2013-01-15 12:00
Prepare course material | 4 days | 2012-12-27 08:00 | 2013-01-01 17:00 | 182 | Trg Grp
Prepare training material | 4 days | 2013-01-02 08:00 | 2013-01-07 17:00 | 208 | Trg Grp
Schedule the traiing program | 1 day? | 2013-01-08 08:00 | 2013-01-08 17:00 | 209 | Trg Grp
Conduct class room training | 2 days | 2013-01-09 08:00 | 2013-01-10 17:00 | 210 | Trg Grp
Conduct hands-on training | 2 days | 2013-01-11 08:00 | 2013-01-14 17:00 | 211 | Trg Grp
Obtain feedback and analyze | 0.5 days? | 2013-01-15 08:00 | 2013-01-15 12:00 | 212 | Trg Grp,PM
Procure Consumables for intial Operation | 11 days? | 2012-12-27 08:00 | 2013-01-10 17:00
Enumerate Consumables required for Initial Operation | 3 days | 2012-12-27 08:00 | 2012-12-31 17:00 | 182 | PM
Raise Requisition on Purchase for procurement | 2 days | 2013-01-01 08:00 | 2013-01-02 17:00 | 215 | PM
Assist Purchase in finalizing the vendors | 4 days | 2013-01-03 08:00 | 2013-01-08 17:00 | 216 | PM
Receive and inspect the consumables | 1 day | 2013-01-09 08:00 | 2013-01-09 17:00 | 217 | QA
Arrange safe storage for the consumables | 1 day? | 2013-01-10 08:00 | 2013-01-10 17:00 | 218 | PM
Conduuct Trial Runs | 12.5 days? | 2013-01-15 13:00 | 2013-01-31 17:00
Ensure that the system is ready | 2 days? | 2013-01-15 13:00 | 2013-01-17 12:00 | 138,151,162,188,194,200,206,213,219 | PM
Initiate trial runs by the end users | 0.5 days? | 2013-01-17 13:00 | 2013-01-17 17:00 | 221 | PM,End Users
Collate feedback | 1 day? | 2013-01-18 08:00 | 2013-01-18 17:00 | 222 | PM
Analyze the feedback and short list points for implementation in the system | 1 day? | 2013-01-21 08:00 | 2013-01-21 17:00 | 223 | PM
Implement short listed feedback in the system | 4 days | 2013-01-22 08:00 | 2013-01-25 17:00 | 224 | PM
Initiate a second round of trial run | 1 day? | 2013-01-28 08:00 | 2013-01-28 17:00 | 225 | PM,End Users
Ensure that the system is mature | 3 days | 2013-01-29 08:00 | 2013-01-31 17:00 | 226 | PM
Changeover to new system | 15 days | 2013-02-01 08:00 | 2013-02-21 17:00
Clean out the garbage from the system | 2 days | 2013-02-01 08:00 | 2013-02-04 17:00 | 227 | Dev Team
Ensure that the system is clean | 2 days | 2013-02-05 08:00 | 2013-02-06 17:00 | 229 | Dev Team,PM
Ensure that all operations people are in place | 1 day | 2013-02-07 08:00 | 2013-02-07 17:00 | 230 | Dev Team,PM
Ensure that all systems and procedures are implemented | 1 day | 2013-02-08 08:00 | 2013-02-08 17:00 | 231 | Dev Team,PM
Ensure that handholding staff is ready | 1 day | 2013-02-11 08:00 | 2013-02-11 17:00 | 232 | Dev Team,PM
Ensure that all concerned people are trained | 1 day | 2013-02-12 08:00 | 2013-02-12 17:00 | 233 | Dev Team,PM
Declare the start the changeover date of the new system | 1 day | 2013-02-13 08:00 | 2013-02-13 17:00 | 234 | PM
Changeover to new system | 1 day | 2013-02-14 08:00 | 2013-02-14 17:00 | 235 | PM,Maintenance Team
Closely monitor the usage and performance | 5 days | 2013-02-15 08:00 | 2013-02-21 17:00 | 236 | PM,Maintenance Team
Initiate Maintenance | 6 days? | 2013-02-22 08:00 | 2013-03-01 17:00
Handover hardware to hardware maintenance team | 1 day? | 2013-02-22 08:00 | 2013-02-22 17:00 | 237 | PM,Maintenance Team
Handover Application Software to software maintenance team' | 3 days | 2013-02-25 08:00 | 2013-02-27 17:00 | 239 | PM,Maintenance Team
Handover nwetwork maintenance to networking team | 1 day? | 2013-02-28 08:00 | 2013-02-28 17:00 | 240 | PM,Maintenance Team
Obtain signoff from all maintenance teams | 1 day? | 2013-03-01 08:00 | 2013-03-01 17:00 | 241 | PM,Maintenance Team
Project Closure | 14 days? | 2013-03-04 08:00 | 2013-03-21 17:00
Release Resources | 1 day? | 2013-03-04 08:00 | 2013-03-04 17:00 | 242 | PMO
Document Project Experience | 3 days | 2013-03-05 08:00 | 2013-03-07 17:00 | 244 | PM
Conduct Project Postmortem | 2 days | 2013-03-08 08:00 | 2013-03-11 17:00 | 245 | PMO,PM
Update skills databse | 2 days | 2013-03-12 08:00 | 2013-03-13 17:00 | 246 | PM,HR
Conduct performance appriasals of the team members | 4 days | 2013-03-14 08:00 | 2013-03-19 17:00 | 247 | PM,HR
Handover Project Records to PMO | 1 day? | 2013-03-20 08:00 | 2013-03-20 17:00 | 248 | PM,PMO
Release PM | 1 day? | 2013-03-21 08:00 | 2013-03-21 17:00 | 249 | PMO
End | 1 day? | 2013-03-22 08:00 | 2013-03-22 17:00 | 250
For the MicroSoft Project 2000 Version of this IT Project Schedule
click on the link below.
www.chemuturi.com/jrosspubitpm.html
The above is a schedule for a typical IT Project consisting of 251 activities/tasks
in Ms Excel format for those who may not use Ms Project in their organization.
You may export this data into the scheduling tool your organization uses and
customize it to fit your particular project.
For illustrative purposes, all the predecessor relationships are defined
with the type applicable to each activity and resources have been allocated.