{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Who Does What"],"read":"whole","date_system":"1900"}

{"sheet":"Who Does What","index":0,"n_rows":273,"n_cols":6,"rows_kept":273}
["Task","Duration","Start","Finish","Predecessors","Resource Names"]
["Start","1 day?","2012-06-06T08:00:00","2012-06-06T17:00:00"]
["Feasibility Study","23.5 days?","2012-06-07T08:00:00","2012-07-10T12:00:00"]
["Decide to outsource or handle in-house","1 day?","2012-06-07T08:00:00","2012-06-07T17:00:00","1","Mgt"]
["Set objectives","0.5 days?","2012-06-07T08:00:00","2012-06-07T12:00:00","1","Mgt,Customer"]
["Define scope","2 days","2012-06-07T13:00:00","2012-06-11T12:00:00","4","Mgt,Customer"]
["Elicit and gather information processing requirements","5 days","2012-06-11T13:00:00","2012-06-18T12:00:00","5","Contractor1"]
["Analyze and establish information processing needs","2 days","2012-06-18T13:00:00","2012-06-20T12:00:00","6,3","Contractor1"]
["Define proposed IT infrastructure","2 days","2012-06-20T13:00:00","2012-06-22T12:00:00","7","Contractor1"]
["Define support infrastructure","2 days","2012-06-20T13:00:00","2012-06-22T12:00:00","7","Contractor1"]
["Define organizational structure","2 days","2012-06-20T13:00:00","2012-06-22T12:00:00","7","Contractor1"]
["Define the deliverables","1 day","2012-06-20T13:00:00","2012-06-21T12:00:00","7","Contractor1"]
["Define the security arrangements","2 days","2012-06-20T13:00:00","2012-06-22T12:00:00","7","Contractor1"]
["Estimate the cost of IT infrastructure","3 days","2012-06-22T13:00:00","2012-06-27T12:00:00","8","Contractor1"]
["Estimate the cost of support infrastructure","3 days","2012-06-22T13:00:00","2012-06-27T12:00:00","9","Contractor1"]
["Estimate the cost of annual maintenance costs","1 day","2012-06-27T13:00:00","2012-06-28T12:00:00","13,14","Contractor1"]
["Estimate the operational costs","2 days","2012-06-27T13:00:00","2012-06-29T12:00:00","13,14","Contractor1"]
["Define upgrade path and replacement criteria","1 day?","2012-06-22T13:00:00","2012-06-25T12:00:00","8,9,10,11,12","Contractor1"]
["Prepare report","3 days","2012-06-29T13:00:00","2012-07-04T12:00:00","15,16,17","Contractor1"]
["QC on the report","1 day","2012-07-04T13:00:00","2012-07-05T12:00:00","18","Contractor1"]
["Present the report","1 day?","2012-07-05T13:00:00","2012-07-06T12:00:00","19","Contractor1"]
["Implement feedback and submit the report finally","2 days","2012-07-06T13:00:00","2012-07-10T12:00:00","20","Contractor1"]
["Project Approval","8 days?","2012-07-10T13:00:00","2012-07-20T12:00:00"]
["Compare with competing projects","2 days","2012-07-10T13:00:00","2012-07-12T12:00:00","21","Mgt"]
["Technical appraisal","3 days","2012-07-12T13:00:00","2012-07-17T12:00:00","23","Mgt"]
["Financial appraisal","3 days","2012-07-12T13:00:00","2012-07-17T12:00:00","23","Finance"]
["Technical approval","2 days","2012-07-17T13:00:00","2012-07-19T12:00:00","24","Mgt"]
["Financial approval","2 days","2012-07-17T13:00:00","2012-07-19T12:00:00","25","Finance"]
["Project approval","1 day?","2012-07-19T13:00:00","2012-07-20T12:00:00","26,27","Mgt"]
["Project Planning","8 days?","2012-07-20T13:00:00","2012-08-01T12:00:00"]
["Floor plan","5 days","2012-07-20T13:00:00","2012-07-27T12:00:00","28","Architect"]
["Deployment plan","3 days","2012-07-20T13:00:00","2012-07-25T12:00:00","28","Architect"]
["Software Development plan","5 days","2012-07-20T13:00:00","2012-07-27T12:00:00","28","PM"]
["Installation and commissioning plan","1 day?","2012-07-20T13:00:00","2012-07-23T12:00:00","28","PM"]
["Data preparation plan","2 days","2012-07-20T13:00:00","2012-07-24T12:00:00","28","PM"]
["Training plan","1 day?","2012-07-20T13:00:00","2012-07-23T12:00:00","28","PM"]
["Quality assurance plan","3 days","2012-07-20T13:00:00","2012-07-25T12:00:00","28","PM"]
["Procurement plan","2 days","2012-07-20T13:00:00","2012-07-24T12:00:00","28","PM"]
["Networking plan","4 days","2012-07-20T13:00:00","2012-07-26T12:00:00","28","PM"]
["Risk management plan","1 day?","2012-07-20T13:00:00","2012-07-23T12:00:00","28","PM"]
["Overall project schedule","5 days","2012-07-20T13:00:00","2012-07-27T12:00:00","28","PM"]
["Review project plans","1 day?","2012-07-27T13:00:00","2012-07-30T12:00:00","40,30,31,32,33,34,35,36,37,38,39","QA"]
["Implement review feedback","1 day?","2012-07-30T13:00:00","2012-07-31T12:00:00","41","PM"]
["Approve project plans","1 day?","2012-07-31T13:00:00","2012-08-01T12:00:00","42","Mgt"]
["Sizing","4 days?","2012-07-20T13:00:00","2012-07-26T12:00:00"]
["Webserver","0.5 days","2012-07-20T13:00:00","2012-07-20T17:00:00","28","Contractor1"]
["Database server","0.5 days","2012-07-20T13:00:00","2012-07-20T17:00:00","28","Contractor1"]
["Email server","0.5 days","2012-07-20T13:00:00","2012-07-20T17:00:00","28","Contractor1"]
["Security server","0.5 days","2012-07-20T13:00:00","2012-07-20T17:00:00","28","Contractor1"]
["App server","0.5 days","2012-07-20T13:00:00","2012-07-20T17:00:00","28","Contractor1"]
["Networking hardware","1 day?","2012-07-20T13:00:00","2012-07-23T12:00:00","28","Contractor1"]
["Power requirements","1 day?","2012-07-20T13:00:00","2012-07-23T12:00:00","28","Contractor1"]
["Application Software","2 days","2012-07-20T13:00:00","2012-07-24T12:00:00","28","Contractor1"]
["Make or buy decisions","2 days","2012-07-24T13:00:00","2012-07-26T12:00:00","45,46,47,48,49,50,51,52","Contractor1,Mgt"]
["QC of sizing exercise","1 day?","2012-07-24T13:00:00","2012-07-25T12:00:00","45,46,47,48,49,50,51,52","Contractor1"]
["Feedback and submit sizing report","1 day?","2012-07-25T13:00:00","2012-07-26T12:00:00","54","Contractor1"]
["Recruitment of People for Operations","18 days?","2012-08-01T13:00:00","2012-08-27T12:00:00","55"]
["Define the eligibility criteria for all positions","3 days","2012-08-01T13:00:00","2012-08-06T12:00:00","43","PM"]
["Determine the number and classes of people required","3 days","2012-08-06T13:00:00","2012-08-09T12:00:00","57","PM"]
["Raise Requisition on HR for recruitment","1 day","2012-08-09T13:00:00","2012-08-10T12:00:00","58","PM"]
["Scrutinize and Short List applicants for interview","3 days","2012-08-10T13:00:00","2012-08-15T12:00:00","59","HR,PM"]
["Assist HR in conducting Interviews","2 days","2012-08-15T13:00:00","2012-08-17T12:00:00","60","PM"]
["Finalize Candidates","1 day","2012-08-17T13:00:00","2012-08-20T12:00:00","61","PM,HR"]
["Appointment of selected candidates","2 days","2012-08-20T13:00:00","2012-08-22T12:00:00","62","HR"]
["Conduct Induction Training of recruitees","2 days","2012-08-22T13:00:00","2012-08-24T12:00:00","63","HR"]
["Allocate people to project","1 day?","2012-08-24T13:00:00","2012-08-27T12:00:00","64","HR"]
["Procurement","22.5 days?","2012-07-26T13:00:00","2012-08-27T17:00:00"]
["Procurement of Servers","0.5 days?","2012-08-27T13:00:00","2012-08-27T17:00:00","43,56","Purchase,PM"]
["Procurement of Workstations","0.5 days?","2012-08-01T13:00:00","2012-08-01T17:00:00","55,43","Purchase,PM"]
["Procurement of Networking cables","0.5 days?","2012-08-01T13:00:00","2012-08-01T17:00:00","55,43","Purchase,PM"]
["Procurement of Networking hardware","0.5 days?","2012-08-01T13:00:00","2012-08-01T17:00:00","55,43","Purchase,PM"]
["Procurement of System Software","1 day?","2012-08-01T13:00:00","2012-08-02T12:00:00","55,43","Purchase,PM"]
["Preparation of specifications for Application Software","2 days?","2012-08-01T13:00:00","2012-08-03T12:00:00","55,43","PM"]
["Procurement of Application Software","1 day?","2012-08-01T13:00:00","2012-08-02T12:00:00","55,43","Purchase,PM"]
["Finalize Subcontractors","1 day?","2012-07-26T13:00:00","2012-07-27T12:00:00","55,53","Purchase,PM"]
["Facility / Data  Center Preparation","46 days","2012-07-26T13:00:00","2012-09-28T12:00:00"]
["Facility Design","5 days","2012-07-26T13:00:00","2012-08-02T12:00:00","55","Architect"]
["Finalize Subcontractor for facility construction","3 days","2012-08-02T13:00:00","2012-08-07T12:00:00","76","Purchase,Mgt"]
["Facility Construction","30 days","2012-08-07T13:00:00","2012-09-18T12:00:00","77","Contractor 2"]
["Electrification of the Facility","5 days","2012-09-18T13:00:00","2012-09-25T12:00:00","78","Contractor 2"]
["Provide Environmental controls","5 days","2012-09-18T13:00:00","2012-09-25T12:00:00","78","Contractor 3"]
["Provide Data Communication facilities","3 days","2012-09-18T13:00:00","2012-09-21T12:00:00","78","Contractor 4"]
["Inspect and takeover Facility / Data Center","3 days","2012-09-25T13:00:00","2012-09-28T12:00:00","79,80,81","Purchase,PM"]
["Installing the servers","36 days?","2012-08-27T13:00:00","2012-10-16T12:00:00"]
["Site preparationn for the data center","3 days","2012-08-27T13:00:00","2012-08-30T12:00:00","65","Contractor 5"]
["Receive and QC Servers","3 days","2012-08-30T13:00:00","2012-09-04T12:00:00","84,67","Contractor 5"]
["Server deployment","2 days","2012-09-04T13:00:00","2012-09-06T12:00:00","85","Contractor 5"]
["Test the servers","3 days","2012-09-06T13:00:00","2012-09-11T12:00:00","86","Contractor 5"]
["Connect servers to the network","1 day?","2012-10-15T13:00:00","2012-10-16T12:00:00","87,118","Contractor 5"]
["Installing the Workstations","24 days","2012-10-16T13:00:00","2012-11-19T12:00:00","88"]
["Site preparationn for the Worksations","4 days","2012-10-16T13:00:00","2012-10-22T12:00:00","65","Contractor 5"]
["Receive and QC Workstations","5 days","2012-10-22T13:00:00","2012-10-29T12:00:00","90","Contractor 5"]
["Workstation deployment","6 days","2012-10-29T13:00:00","2012-11-06T12:00:00","91","Contractor 5"]
["Test the Workstations","5 days","2012-11-06T13:00:00","2012-11-13T12:00:00","92","Contractor 5"]
["Connect Workstations to the network","4 days","2012-11-13T13:00:00","2012-11-19T12:00:00","93","Contractor 5"]
["Install System Software","34 days?","2012-10-16T13:00:00","2012-12-03T12:00:00"]
["Install RDBMS","1 day?","2012-11-19T13:00:00","2012-11-20T12:00:00","71,65,94","Contractor 5"]
["Cursory Testing of RDBMS","1 day?","2012-11-20T13:00:00","2012-11-21T12:00:00","96","Contractor 5"]
["Install Email Exchange Software","2 days","2012-10-16T13:00:00","2012-10-18T12:00:00","88,71","Contractor 5"]
["Cusrsory Testing of Email Exchange Software","1 day?","2012-10-18T13:00:00","2012-10-19T12:00:00","98","Contractor 5"]
["Install Middle Tier Software","1 day?","2012-10-16T13:00:00","2012-10-17T12:00:00","88,71","Contractor 5"]
["Cursory Testing of Middle Tier Software","1 day?","2012-10-17T13:00:00","2012-10-18T12:00:00","100","Contractor 5"]
["Install Configuration Management Software","1 day?","2012-10-16T13:00:00","2012-10-17T12:00:00","88,71","Contractor 5"]
["Cursory Testing of Configuration Management Software","1 day?","2012-10-17T13:00:00","2012-10-18T12:00:00","102","Contractor 5"]
["Install Security Software","1 day?","2012-11-21T13:00:00","2012-11-22T12:00:00","97,99,101,103,71","Contractor 5"]
["Cursory Testing of Security Software","1 day?","2012-11-22T13:00:00","2012-11-23T12:00:00","104","Contractor 5"]
["Install Network Monitoring Software","1 day?","2012-11-23T13:00:00","2012-11-26T12:00:00","105,71","Contractor 5"]
["Cursory Testing of Network Monitoring Software","1 day?","2012-11-26T13:00:00","2012-11-27T12:00:00","106","Contractor 5"]
["Install Backup/Restore Software","1 day?","2012-11-27T13:00:00","2012-11-28T12:00:00","107,71","Contractor 5"]
["Cursory Testing of Backup/Restpre Software","1 day?","2012-11-28T13:00:00","2012-11-29T12:00:00","108","Contractor 5"]
["Install Administrative Utilities","1 day?","2012-11-29T13:00:00","2012-11-30T12:00:00","109,71","Contractor 5"]
["Cursory Testing of Administrative Utilities","1 day?","2012-11-30T13:00:00","2012-12-03T12:00:00","110","Contractor 5"]
["Networking","66.5 days?","2012-07-27T13:00:00","2012-10-29T17:00:00"]
["Receive Networking Cables","1 day?","2012-09-28T13:00:00","2012-10-01T12:00:00","82,69,65","Contractor 4"]
["Receive Networking Hardware","1 day?","2012-09-28T13:00:00","2012-10-01T12:00:00","82,70","Contractor 4"]
["Finalize Networking Subcontractor","1 day?","2012-07-27T13:00:00","2012-07-30T12:00:00","74","Contractor 4"]
["Install the router","1 day?","2012-10-01T13:00:00","2012-10-02T12:00:00","114,115","Contractor 4"]
["Install the network switches","1 day?","2012-10-01T13:00:00","2012-10-02T12:00:00","114,115","Contractor 4"]
["Laying of the network cables","10 days","2012-10-01T13:00:00","2012-10-15T12:00:00","115,113","Contractor 4"]
["Connecting cables to the equipment","5 days","2012-10-15T13:00:00","2012-10-22T12:00:00","118","Contractor 4"]
["Establishing connectivity to the Internet","1 day?","2012-10-22T13:00:00","2012-10-23T12:00:00","116,119,117","Contractor 4"]
["Testing the network","4 days","2012-10-23T13:00:00","2012-10-29T12:00:00","120","Contractor 4,Network Engineer"]
["handover the network to network administrators","0.5 days?","2012-10-29T13:00:00","2012-10-29T17:00:00","121","Contractor 4,PM"]
["Receive and Deploy Application Software","98 days?","2012-08-03T13:00:00","2012-12-19T12:00:00"]
["Finalize Subcontractor","1 day","2012-08-03T13:00:00","2012-08-06T12:00:00","74,72,73","Purchase,PM"]
["Assist Subcontractor in finalizing Requirements","9 days","2012-08-06T13:00:00","2012-08-17T12:00:00","124","Dev Team,PM"]
["Review and approve Software Design","3 days","2012-08-17T13:00:00","2012-08-22T12:00:00","125","PM"]
["Development of application software","50 days","2012-08-22T13:00:00","2012-10-31T12:00:00","126","Dev Team"]
["Review Quality Records of software development","3 days","2012-10-31T13:00:00","2012-11-05T12:00:00","127","QA"]
["Prepare Acceptance Test Plan and Test Cases","5 days","2012-08-22T13:00:00","2012-08-29T12:00:00","126","Dev Team,QA"]
["Conduct Acceptance Testing of Application Software","3 days","2012-08-29T13:00:00","2012-09-03T12:00:00","129","Dev Team"]
["Accept Delivery of Application Software","2 days","2012-12-03T13:00:00","2012-12-05T12:00:00","111,130,128","QA,PM"]
["Install Database on the server","1 day?","2012-12-05T13:00:00","2012-12-06T12:00:00","131,97","Dev Team"]
["Install Server Components of the Application Software","1 day?","2012-12-05T13:00:00","2012-12-06T12:00:00","131,101","Dev Team"]
["Install Workstation Components, if any, on the Workstations","2 days","2012-12-05T13:00:00","2012-12-07T12:00:00","131,68","Dev Team"]
["Cursory Testing of installed Application Software","2 days","2012-12-07T13:00:00","2012-12-11T12:00:00","132,133,134,122","Dev Team"]
["Define Roles and Responsibilities of Configuration Management","2 days","2012-12-11T13:00:00","2012-12-13T12:00:00","135","Dev Team,PM"]
["Configure Security in the Configuration Management Tool","3 days","2012-12-13T13:00:00","2012-12-18T12:00:00","136","Dev Team"]
["Initiate Configuration Management of Application Software","1 day","2012-12-18T13:00:00","2012-12-19T12:00:00","137","Dev Team,PM"]
["Master data preparation","27 days?","2012-08-22T13:00:00","2012-09-28T12:00:00"]
["Create Master data tables","2 days","2012-08-27T13:00:00","2012-08-29T12:00:00","126,65","Dev Team"]
["Identify data preparation agencies","1 day","2012-08-22T13:00:00","2012-08-23T12:00:00","126","PM,Purchase"]
["Select the agency for preparing the data","1 day","2012-08-23T13:00:00","2012-08-24T12:00:00","141","PM,Purchase"]
["Place work order","1 day","2012-08-24T13:00:00","2012-08-27T12:00:00","142","PM,Purchase"]
["Provide master data","3 days","2012-08-27T13:00:00","2012-08-30T12:00:00","143","PM,Purchase"]
["Receive data","10 days","2012-08-30T13:00:00","2012-09-13T12:00:00","144","Dev Team"]
["Inward QC of received data","2 days","2012-09-13T13:00:00","2012-09-17T12:00:00","145","Dev Team"]
["Load the data in master data tables","3 days","2012-09-17T13:00:00","2012-09-20T12:00:00","146","Dev Team"]
["Verify master data","2 days","2012-09-20T13:00:00","2012-09-24T12:00:00","147","QA"]
["Make payments to the agency","1 day","2012-09-24T13:00:00","2012-09-25T12:00:00","148","PM,Purchase"]
["Close the work order","1 day?","2012-09-25T13:00:00","2012-09-26T12:00:00","149","Purchase"]
["Handover data to maintenance team","2 days","2012-09-26T13:00:00","2012-09-28T12:00:00","150","PM"]
["Data Migration","17 days","2012-08-22T13:00:00","2012-09-14T12:00:00"]
["Study the existing data formats","3 days","2012-08-22T13:00:00","2012-08-27T12:00:00","126","Dev Team"]
["Study the new data format","2 days","2012-08-22T13:00:00","2012-08-24T12:00:00","126","Dev Team"]
["Map the data migration path","3 days","2012-08-27T13:00:00","2012-08-30T12:00:00","153,154","Dev Team"]
["Develop software to migrate data","5 days","2012-08-30T13:00:00","2012-09-06T12:00:00","155","Dev Team"]
["Quality control of the software","2 days","2012-09-06T13:00:00","2012-09-10T12:00:00","156","QA"]
["Perform data migration using the software","3 days","2012-09-10T13:00:00","2012-09-13T12:00:00","157","Dev Team"]
["Data entry for newly created fields","5 days","2012-08-30T13:00:00","2012-09-06T12:00:00","155","Contractor 6"]
["Load missing data into master data tables","2 days","2012-09-06T13:00:00","2012-09-10T12:00:00","159","Dev Team"]
["Perform quality control actvities","2 days","2012-09-10T13:00:00","2012-09-12T12:00:00","160","Dev Team"]
["Handover data to maintenance team","1 day","2012-09-13T13:00:00","2012-09-14T12:00:00","160,158","PM"]
["Define Systems and Procedures","15.5 days?","2012-12-05T13:00:00","2012-12-26T17:00:00"]
["Define Processes for Managing the IT Infrastructure","2 days","2012-12-05T13:00:00","2012-12-07T12:00:00","131,65","Process Group"]
["Review the Processes for Managing the IT Infrastructure","1 day","2012-12-07T13:00:00","2012-12-10T12:00:00","164","QA"]
["Define Procedures for Support Activities","2 days","2012-12-05T13:00:00","2012-12-07T12:00:00","131","Process Group"]
["Review Procedures for Support Activities","1 day?","2012-12-07T13:00:00","2012-12-10T12:00:00","166","Process Group"]
["Rollout Procedures for Support Activities","0.5 days?","2012-12-10T13:00:00","2012-12-10T17:00:00","165,167","PM,Process Group"]
["Define SLAs for support Activities","1 day?","2012-12-11T08:00:00","2012-12-11T17:00:00","168","Process Group"]
["Define Disaster Management Procedures","2 days","2012-12-12T08:00:00","2012-12-13T17:00:00","169","Process Group"]
["Review Disaster Management Proccedures","1 day?","2012-12-14T08:00:00","2012-12-14T17:00:00","170","QA"]
["Rollout Disaster Management Procedures","0.5 days?","2012-12-17T08:00:00","2012-12-17T12:00:00","171","PM,Process Group"]
["Define Backup/Restore Procedures","2 days","2012-12-12T08:00:00","2012-12-13T17:00:00","169","Process Group"]
["Review Backup/Restore Procedures","2 days","2012-12-14T08:00:00","2012-12-17T17:00:00","173","QA"]
["Rollout Backup/Restore Procedures","0.5 days?","2012-12-18T08:00:00","2012-12-18T12:00:00","174","PM,Process Group"]
["Define Safety and Security Procedures","2 days","2012-12-17T13:00:00","2012-12-19T12:00:00","172","Process Group"]
["Review Safety and Security Procedures","1 day?","2012-12-19T13:00:00","2012-12-20T12:00:00","176","QA"]
["Rollout Safety and Security Procedures","0.5 days?","2012-12-20T13:00:00","2012-12-20T17:00:00","177","PM,Process Group"]
["Define System Audit Procedures","2 days","2012-12-21T08:00:00","2012-12-24T17:00:00","178","Process Group"]
["Review System Audit Procedures","1 day?","2012-12-25T08:00:00","2012-12-25T17:00:00","179","QA"]
["Rollout System Audit Procedures","0.5 days?","2012-12-26T08:00:00","2012-12-26T12:00:00","180","PM,Process Group"]
["Systems and procedures rolled out","0.5 days?","2012-12-26T13:00:00","2012-12-26T17:00:00","168,172,175,181,177","Process Group,PM"]
["End user training","12 days","2012-12-27T08:00:00","2013-01-11T17:00:00"]
["Prepare training materials","5 days","2012-12-27T08:00:00","2013-01-02T17:00:00","182","Trg Grp"]
["Plan the training","1 day","2013-01-03T08:00:00","2013-01-03T17:00:00","184","Trg Grp"]
["Arrange faciltiies","3 days","2013-01-04T08:00:00","2013-01-08T17:00:00","185","Trg Grp"]
["Conduct training","2 days","2013-01-09T08:00:00","2013-01-10T17:00:00","186","Trg Grp"]
["Obtain feedback and analyse","1 day","2013-01-11T08:00:00","2013-01-11T17:00:00","187","Trg Grp,PM"]
["System Administration Training","10.5 days?","2012-11-19T13:00:00","2012-12-03T17:00:00"]
["Prepare training materials","5 days","2012-11-19T13:00:00","2012-11-26T12:00:00","88,94,122","Trg Grp"]
["Plan the training","1 day?","2012-11-26T13:00:00","2012-11-27T12:00:00","190","Trg Grp"]
["Arrange faciltiies","3 days","2012-11-27T13:00:00","2012-11-30T12:00:00","191","Trg Grp"]
["Conduct training","1 day?","2012-11-30T13:00:00","2012-12-03T12:00:00","192","Trg Grp"]
["Obtain feedback and analyse","0.5 days?","2012-12-03T13:00:00","2012-12-03T17:00:00","193","Trg Grp,PM"]
["Network administration training","10.5 days?","2012-10-30T08:00:00","2012-11-13T12:00:00"]
["Prepare training materials","5 days","2012-10-30T08:00:00","2012-11-05T17:00:00","122","Trg Grp"]
["Plan the training","2 days","2012-11-06T08:00:00","2012-11-07T17:00:00","196","Trg Grp"]
["Arrange faciltiies","2 days","2012-11-08T08:00:00","2012-11-09T17:00:00","197","Trg Grp"]
["Conduct training","1 day?","2012-11-12T08:00:00","2012-11-12T17:00:00","198","Trg Grp"]
["Obtain Feedback and Analyze","0.5 days?","2012-11-13T08:00:00","2012-11-13T12:00:00","199","Trg Grp,PM"]
["Manager training","9.5 days?","2012-12-27T08:00:00","2013-01-09T12:00:00"]
["Prepare training materials","4 days","2012-12-27T08:00:00","2013-01-01T17:00:00","182","Trg Grp"]
["Plan the training","2 days","2013-01-02T08:00:00","2013-01-03T17:00:00","202","Trg Grp"]
["Arrange faciltiies","2 days","2013-01-04T08:00:00","2013-01-07T17:00:00","203","Trg Grp"]
["Conduct training","1 day?","2013-01-08T08:00:00","2013-01-08T17:00:00","204","Trg Grp"]
["Obtain feedback and analyse","0.5 days?","2013-01-09T08:00:00","2013-01-09T12:00:00","205","Trg Grp,PM"]
["Maintenance team training","13.5 days?","2012-12-27T08:00:00","2013-01-15T12:00:00"]
["Prepare course material","4 days","2012-12-27T08:00:00","2013-01-01T17:00:00","182","Trg Grp"]
["Prepare training material","4 days","2013-01-02T08:00:00","2013-01-07T17:00:00","208","Trg Grp"]
["Schedule the traiing program","1 day?","2013-01-08T08:00:00","2013-01-08T17:00:00","209","Trg Grp"]
["Conduct class room training","2 days","2013-01-09T08:00:00","2013-01-10T17:00:00","210","Trg Grp"]
["Conduct hands-on training","2 days","2013-01-11T08:00:00","2013-01-14T17:00:00","211","Trg Grp"]
["Obtain feedback and analyze","0.5 days?","2013-01-15T08:00:00","2013-01-15T12:00:00","212","Trg Grp,PM"]
["Procure Consumables for intial Operation","11 days?","2012-12-27T08:00:00","2013-01-10T17:00:00"]
["Enumerate Consumables required for Initial Operation","3 days","2012-12-27T08:00:00","2012-12-31T17:00:00","182","PM"]
["Raise Requisition on Purchase for procurement","2 days","2013-01-01T08:00:00","2013-01-02T17:00:00","215","PM"]
["Assist Purchase in finalizing the vendors","4 days","2013-01-03T08:00:00","2013-01-08T17:00:00","216","PM"]
["Receive and inspect the consumables","1 day","2013-01-09T08:00:00","2013-01-09T17:00:00","217","QA"]
["Arrange safe storage for the consumables","1 day?","2013-01-10T08:00:00","2013-01-10T17:00:00","218","PM"]
["Conduuct Trial Runs","12.5 days?","2013-01-15T13:00:00","2013-01-31T17:00:00"]
["Ensure that the system is ready","2 days?","2013-01-15T13:00:00","2013-01-17T12:00:00","138,151,162,188,194,200,206,213,219","PM"]
["Initiate trial runs by the end users","0.5 days?","2013-01-17T13:00:00","2013-01-17T17:00:00","221","PM,End Users"]
["Collate feedback","1 day?","2013-01-18T08:00:00","2013-01-18T17:00:00","222","PM"]
["Analyze the feedback and short list points for implementation in the system","1 day?","2013-01-21T08:00:00","2013-01-21T17:00:00","223","PM"]
["Implement short listed feedback in the system","4 days","2013-01-22T08:00:00","2013-01-25T17:00:00","224","PM"]
["Initiate a second round of trial run","1 day?","2013-01-28T08:00:00","2013-01-28T17:00:00","225","PM,End Users"]
["Ensure that the system is mature","3 days","2013-01-29T08:00:00","2013-01-31T17:00:00","226","PM"]
["Changeover to new system","15 days","2013-02-01T08:00:00","2013-02-21T17:00:00"]
["Clean out the garbage from the system","2 days","2013-02-01T08:00:00","2013-02-04T17:00:00","227","Dev Team"]
["Ensure that the system is clean","2 days","2013-02-05T08:00:00","2013-02-06T17:00:00","229","Dev Team,PM"]
["Ensure that all operations people are in place","1 day","2013-02-07T08:00:00","2013-02-07T17:00:00","230","Dev Team,PM"]
["Ensure that all systems and procedures are implemented","1 day","2013-02-08T08:00:00","2013-02-08T17:00:00","231","Dev Team,PM"]
["Ensure that handholding staff is ready","1 day","2013-02-11T08:00:00","2013-02-11T17:00:00","232","Dev Team,PM"]
["Ensure that all concerned people are trained","1 day","2013-02-12T08:00:00","2013-02-12T17:00:00","233","Dev Team,PM"]
["Declare the start the changeover date of the new system","1 day","2013-02-13T08:00:00","2013-02-13T17:00:00","234","PM"]
["Changeover to new system","1 day","2013-02-14T08:00:00","2013-02-14T17:00:00","235","PM,Maintenance Team"]
["Closely monitor the usage and performance","5 days","2013-02-15T08:00:00","2013-02-21T17:00:00","236","PM,Maintenance Team"]
["Initiate Maintenance","6 days?","2013-02-22T08:00:00","2013-03-01T17:00:00"]
["Handover hardware to hardware maintenance team","1 day?","2013-02-22T08:00:00","2013-02-22T17:00:00","237","PM,Maintenance Team"]
["Handover Application Software to software maintenance team'","3 days","2013-02-25T08:00:00","2013-02-27T17:00:00","239","PM,Maintenance Team"]
["Handover nwetwork maintenance to networking team","1 day?","2013-02-28T08:00:00","2013-02-28T17:00:00","240","PM,Maintenance Team"]
["Obtain signoff from all maintenance teams","1 day?","2013-03-01T08:00:00","2013-03-01T17:00:00","241","PM,Maintenance Team"]
["Project Closure","14 days?","2013-03-04T08:00:00","2013-03-21T17:00:00"]
["Release Resources","1 day?","2013-03-04T08:00:00","2013-03-04T17:00:00","242","PMO"]
["Document Project Experience","3 days","2013-03-05T08:00:00","2013-03-07T17:00:00","244","PM"]
["Conduct Project Postmortem","2 days","2013-03-08T08:00:00","2013-03-11T17:00:00","245","PMO,PM"]
["Update skills databse","2 days","2013-03-12T08:00:00","2013-03-13T17:00:00","246","PM,HR"]
["Conduct performance appriasals of the team members","4 days","2013-03-14T08:00:00","2013-03-19T17:00:00","247","PM,HR"]
["Handover Project Records to PMO","1 day?","2013-03-20T08:00:00","2013-03-20T17:00:00","248","PM,PMO"]
["Release PM","1 day?","2013-03-21T08:00:00","2013-03-21T17:00:00","249","PMO"]
["End","1 day?","2013-03-22T08:00:00","2013-03-22T17:00:00","250"]
[]
[]
[]
[]
[]
[]
["For the MicroSoft Project 2000 Version of this IT Project Schedule "]
["click on the link below."]
[]
[]
["www.chemuturi.com/jrosspubitpm.html "]
[]
[]
[]
["The above  is a  schedule for a typical IT Project consisting of 251 activities/tasks"]
["in Ms Excel format for those who may not use Ms Project in their organization. "]
["You may export this data into the scheduling tool your organization uses and"]
["customize it to fit your particular project."]
[]
["For illustrative purposes, all the predecessor relationships are defined"]
["with the type applicable to each activity and resources have been allocated."]