## Instructions
Instructions:
# Requirements
1 | Enter the primary functionality of the new system in column A on each of the Estimate and the Validate Estimate tabs. |  | low | medium | high
2 | Estimate the complexity of each piece of functionality using the table for low, medium and high complexity in the Functional Complexity sheet following the instructions. | simple | 5 | 10 | 20
3 | Pad any financial functions by adding 20 requirements for the audit functionality | moderate | 15 | 20 | 30
4 | For each line of functionality, estimate the number of requirements based on the Requirements Complexity table in the Functional Complexity tab. Enter the high, moderate and low estimates for the numbers of requirements in each row and column. | complex | 25 | 35 | 45
5 | this will produce the range of time estimates based on the number of hours to complete each requirement. | critical | 10 | 20 | 30 | Add this number to the # of estimated requirements in the above matrix to get your total.

## Estimate
Unemployment Cost Management Future State Processes | Estimated # Requirements |  |  | Estimated Time / Requirement |  |  | No. of hours planned (Optimistic) |  |  | No. of hours planned (Average) |  |  | No. of hours planned (Pessimistic) |  |  | Requirements Gathering, Review and Rework
Functionality | Optimistic (L) | Average (M) | Pessimistic (H) | Optimistic (2) | Average (4) | Pessimistic (6) | Optimistic (L) | Average (M) | Pessimistic (H) | Optimistic (L) | Average (M) | Pessimistic (H) | Optimistic (L) | Average (M) | Pessimistic (H) | Number of resources | No of hours planned | Total person hours | 165
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3 months | 495
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Validate Estimate
List Future State Processes in this column | Estimated # Requirements |  |  | Estimated Time / Requirement |  |  | No. of hours planned (Optimistic) |  |  | No. of hours planned (Average) |  |  | No. of hours planned (Pessimistic) |  |  | Requirements Gathering, Review and Rework
Functionality | Optimistic (L) | Average (M) | Pessimistic (H) | Optimistic (2) | Average (4) | Pessimistic (6) | Optimistic (L) | Average (M) | Pessimistic (H) | Optimistic (L) | Average (M) | Pessimistic (H) | Optimistic (L) | Average (M) | Pessimistic (H) | Number of resources | No of hours planned | Total person hours | Number of resources | No of hours planned | 165
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 160 | 3 months | 495
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 50
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 144.44
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 22.22
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 166.66
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 55.55
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 25.55
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 25.55
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 50
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 33.33
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 105.55
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 25.55
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 25.55
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 50
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 88.88
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 25.55
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 50
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 50
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 25.55
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 25.55
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 25.55
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 166.66
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 166.66
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 133.33
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 94.44
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 94.44
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 94.44
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 94.44
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 94.44
Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 2170

## Complexity Analysis
| # Requirements | [5 empty] | Business Criticality |  | Audit Complexity
| low | medium | high |  |  |  | Valid Codes | Criteria | Valid Codes | Criteria
Simple | <5 | 6-16 | 17-27 |  |  |  | 1 – MANDATED | Will result in regulatory non-compliance and potential legal or financial penalties if not implemented | 1 – EXTERNAL | Mandatory external audits and traceability required for regulatory purposes.
Moderate | 28-48 | 49-69 | 70-90 |  |  |  | 2 – CRITICAL | Product will not meet customer needs if not implemented | 2 – ANALYTICS | Validates calculations and outputs and generates analytics using the outputs
Complex | 91-121 | 122-152 | 153-174 |  |  |  | 3 – IMPORTANT | May adversely affect customer or user satisfaction if not implemented | 3 – INTERNAL CONTROLS | Validates calculations and outputs, generates reports and controls the process
Adavnced | 175-205 | 206-236 | >207 |  |  |  | 4 - USEFUL | No significant customer or functional impact if not implemented | 4 - REPORTS | Validates calculations and outputs and generates management reports
criticality padding | 10 | 20 | 30 | Add this number to the # of estimated requirements in the above matrix to get your total. |  |  | 5 - WISH | No impact but will increase customer perception of value if implemented | 5 - SYSTEM | Simple calculation and outputs validation to verify and control process and reduce errors
Functional Complexity Matrix
Complexity Analysis
Simple-Low | Low | L-M | Moderate | M-H | High | Weighted Complexity Score | Max Weighted Item Score | Final Weighted Complexity Score
| 1 | 2 | 3 | 4 | 5 | 100% | 100% | 100%
Business Criticality | [5 empty] | 0 | 10% | 0
# Integration Points | [5 empty] | 0 | 2.5% | 0
# Users | [5 empty] | 0 | 2.5% | 0
# Processes | [5 empty] | 0 | 5% | 0
# Transactions | [5 empty] | 0 | 5% | 0
# Financial Calculations | [5 empty] | 0 | 15% | 0 |  | DO NOT CHANGE THESE CELLS!
# Calculations | [5 empty] | 0 | 10% | 0 |  | -Low
Safety | [5 empty] | 0 | 10% | 0 |  | Simple
Security | [5 empty] | 0 | 10% | 0
Audit | [5 empty] | 0 | 10% | 0
Integrated App Types | [5 empty] | 0 | 10% | 0
Transaction Types | [5 empty] | 0 | 10% | 0
Response Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0
Complexity Rating |  |  |  |  | High |  |  | 0
Functional Complexity Matrix
Complexity Analysis
| Low | L-M | Moderate | M-H | High
| 1 | 2 | 3 | 4 | 5 | Row Instructions:
Business Criticality | 5 | 4 | 3 | 2 | 1 | Select the most appropriate criticality rating using the table above and enter the corresponding column number in the appropriate colum to the left (blank matrix).
# Integration Points | 0-5 | 6-19 | 20-30 | 31-49 | 50+ | Select the range for the number of integration points for this step and enter the corresponding column number in the appropriate worksheet colum (blank matrix).
# Users | 1-150 | 151-299 | 300-500 | 501-999 | 1000+ | Select the range for the number of users of this system and enter the corresponding column number in the appropriate worksheet colum (blank matrix).
# Processes | 1-50 | 51-199 | 200-300 | 301-499 | 500+ | Select the range for the number of processes to be run by this system and enter the corresponding column number in the appropriate worksheet colum (blank matrix).
# Transactions | 0-499k | 500k-999k | 1m | 1m-50m | 50m+ | Select the range for the number of transactions for this system and enter the corresponding column number in the appropriate worksheet colum (blank matrix).
# Financial Calculations | 1-50 | 51-199 | 200-300 | 301-499 | 500+ | Select the range for the number of financial calculations for this system and enter the corresponding column number in the appropriate worksheet colum (blank matrix).
# Calculations | 1-50 | 51-199 | 200-300 | 301-499 | 500+ | Select the range for the number of calculations for this system and enter the corresponding column number in the appropriate worksheet colum (blank matrix).
Safety | 1 | 2 | 3 | 4 | 5 | Rate the impacts on safety from this system (will it create any safety risks if it fails?) and enter the corresponding column number in the appropriate worksheet colum (blank matrix).
Security | 1 | 2 | 3 | 4 | 5 | Rate the need for security on this system or the impacts of this system on security (will it reduce security if it fails?) and enter the corresponding column number in the appropriate worksheet colum (blank matrix).
Audit | 5 | 4 | 3 | 2 | 1 | Rate the need for audits on this system and enter the corresponding column number in the appropriate worksheet colum (blank matrix).
Integrated App Types | Word Processing | Performance | Reporting | Auditing | Financial | Select the best type of applications that will be integrated with this system. For Combintaions, use the highest complexity and enter the corresponding column number into your worksheet.
Transaction Types | Processing | Reporting | Exchanging Data | Transferring Data | Financial | Select the best type of applications that will be integrated with this system. For Combintaions, use the highest complexity and enter the corresponding column number into your worksheet.