## Guide
Agile Metrics Calculator Guide
The Agile Metrics Calculator provides some of the most popular measurements used in agile and hybrid agile environments. These tools can be used as is, or built upon to support more complex programs, projects, and teams.
Burndown Chart: Displays the amount of work completed over time. It allows the user to visualize how close they are to completing all of the tasks that were committed to. Begin with the total number of story points committed in the top left corner. Then, notate the story points completed during the requisite time period. Ideally, the burndown should have a downward sloping curve over time, and so the chart gives the user an idea of when progress may be slowing down
Velocity: Tracks the consistency of a team's estimates over time. The chart graphs the amount estimated against the amount actually completed. Velocity helps managers visualize how accurate a team's estimates are, how consistently they work, and how good they are at keeping comittments.
Defect Count: This straightforward defect chart displays the number of defects opened and closed for each time period specified . This chart notifies managers of spikes in defect creation and closure over time as a basic quality indicator. Defect count charts can be elaborated on by adding segmentation by severity and areas or components impacted.
Cycle Time: Calculates the mean time needed to complete a single work item. This helps track the consistency of a team's delivery performance and can serve as a leading indicator for such. Cycle times can be elaborated to segment tasks by category, or expanded to calculate entire release cycles as an organizational performance measure.
Cumulative Flow: Shows how much work aggregated by type is allocated to your team over time. It helps identify bottlenecks when a certain type of task is increasing faster than the others. In our example, the types of tasks are divided by state, such as tasks completed or to do. This helps visualize if/when teams have sudden increases in work or capacity. This chart could also be segmented by stage gate, such as tasks in requirements decomposition, development ,testing, or deployment. By identifying bottlenecks, managers are given the information necessary to shift resources to in crease output.
Earned Business Value: Displays how much of the anticipated business value has been delivered to date. Has enough value been achieved? Is enough focus being placed on the highest value features?
Note: To expand the charts and associated graphs, select the cell in the bottom right corner of the chart, and press the tab key.

## Burndown Chart
Story Points
Time | Story Points | Completed Story Points | Remaining
2018-05-12 14:00 | 12 | 3 | 9
2018-05-13 14:00 | 9 | 1 | 8
2018-05-14 14:00 | 8 | 2 | 6
2018-05-15 14:00 | 6 | 1 | 5
2018-05-16 14:00 | 5 | 0 | 5
2018-05-17 14:00 | 5 | 1 | 4
2018-05-18 14:00 | 4 | 2 | 2
2018-05-19 14:00 | 2 | 1 | 1
2018-05-20 14:00 | 1 | 1 | 0

## Velocity
Velocity
Sprints | Estimated story points | Actual story points | Average velocity
Sprint1 | 23 | 20 | Estimated | Actual
Sprint2 | 12 | 12 | 20 | 17.5
Sprint3 | 24 | 24
Sprint4 | 23 | 23
Sprint5 | 15 | 14
Sprint6 | 23 | 12

## Defect Counts
Defective Analysis
Start Week | End Week | Open Defect | Closed Defect
2018-06-11 | 2018-06-17 | 56 | 23
2018-06-18 | 2018-06-24 | 56 | 23
2018-06-25 | 2018-07-01 | 75 | 56
2018-07-02 | 2018-07-08 | 24 | 12
2018-07-09 | 2018-07-15 | 10 | 9
2018-07-16 | 2018-07-22 | 45 | 15
Formulas:
End Week = [Start Week]+6
Start Week = [End Week, row above]+1

## Cycle Time
Cycle Analysis
Task | Start Date | End Date | No of Hours task completed | Average Cycle Time
Task 1 | 2018-06-11 12:00 | 2018-06-11 21:00 | 9 | 38 | hours
Task 2 | 2018-06-11 12:00 | 2018-06-12 21:00 | 33
Task 3 | 2018-06-11 12:00 | 2018-06-13 21:00 | 57
Task 4 | 2018-06-11 12:00 | 2018-06-14 21:00 | 81
Task 5 | 2018-06-11 12:00 | 2018-06-11 22:00 | 10

## Cumulative Flow
Cumulative Flow
Date | Time frame | No of Total Task | No of Tasks completed | No of Tasks in progress | No of Tasks remaining |  | sum | rank
2018-06-15 | 21:45 | 40 | 20 | 15 | 5 | No of Total Task | 323 | 4
2018-06-16 | 22:45 | 42 | 21 | 11 | 10 | No of Tasks completed | 162 | 3
2018-06-17 | 23:45 | 44 | 22 | 12 | 10 | No of Tasks in progress | 98 | 2
2018-06-18 | 24:45 | 46 | 23 | 13 | 10 | No of Tasks remaining | 63 | 1
2018-06-19 | 25:45 | 47 | 24 | 14 | 9
2018-06-20 | 26:45 | 49 | 25 | 16 | 8
2018-06-21 | 27:45 | 55 | 27 | 17 | 11

## Earned Business Value
Business Value Points
Date | Week | Value per Week | Business value points
2018-06-12 | Week1 | 4 | 4
2018-06-13 | Week2 | 7 | 11
2018-06-14 | Week3 | 12 | 23
2018-06-15 | Week4 | 10 | 33
2018-06-16 | Week5 | 12 | 45
2018-06-16 | Week6 | 12 | 57