## Sheet1
Project Delta
No. | Scenario | ETC Formula | ETC | EAC* | VAC | %VAC
1 | Future cost performance will be at same level as current performance | (BAC - EV)/CPI | 152600 | 189700 | -7700 | -4.231%
2 | Future performance will be on target with original plan, irrespective of current performance | BAC - EV | 146500 | 183600 | -1600 | -0.8791%
3 | Project must be completed at or under the baseline budget (BAC) | BAC - AC | 144900 | 182000 | 0 | 0%
4** | New cost estimates need to be made for remainder of project | ETC | - | - | - | -
*EAC = ETC + AC; AC = $37,100 (Table 13-4)
**No formula for ETC, because new cost estimates are to be made for each individual task.
Therefore, EAC, VAC, and %VAC are also not available.