## Sheet1
Performance Indicators |  | Abbreviation | Formula
Current Performance
| Cost Variance | CV | EV - AC
| % Cost Variance | %CV | %(CV/EV)
| Cost Performance Index | CPI | EV/AC
| Schedule Variance | SV | EV - PV
| % Schedule Variance | %SV | %(SV/PV)
| Schedule Performance Index | SPI | EV/PV
| % Completion | --- | EV/BAC
Future Performance
| Estimate To Complete* | ETC | ---
| Estimate At Completion | EAC | ETC + AC
| Variance At Completion | VAC | BAC - EAC
| %Variance At Completion | %VAC | %(VAC/BAC)
*ETC formulas are provided in Table 13-6.