## Sheet1
A. Project Metrics | A. Project Metrics
|  | Current Performance | [7 empty] | Expected Future Performance
[7 empty] | Schedule | Cost |  | Estimate to | Estimate at | Variance at
| Project | % Completion |  | Critical Path Status |  |  | Variance | Variance | % Contingencies | Complete | Completion | Completion
| ID | Plan | Actual | On Track | Ahead | Behind | (SV) | (CV) | Used | (ETC) | (EAC) | (VAC)
Alpha
Bravo
Charlie
Delta
Echo
Business Case Status
| Project ID | Alignment Score |  | Financials | [5 empty] | Nonfinancial Value
|  |  |  | NPV |  | ROI |  | Payback Period |  | Score |  | Threat Score |  | Opportunity Score |  | Overall Score
|  | Initial | Current | Initial | Current | Initial | Current | Initial | Current | Initial | Current | Initial | Current | Initial | Current | Initial | Current
Alpha
Bravo
Charlie
Delta
Echo
B. Portfolio Metrics
| Total Budgeted Cost of Work Planned | [7 empty] | Project Category Allocation
| Total Budgeted Cost of Work Completed | [7 empty] | Category | Design, % | Actual, %
| Actual Cost of Work Completed | [7 empty] | 1
| Schedule Variance (SV) | [7 empty] | 2
| Schedule Performance Index (SPI) | [7 empty] | 3
| % Total Milestones Completed | [7 empty] | N
Cost Variance (CV)
Cost Performance Index (CPI)
Budget Remaining
Budget Required
% Contingencies Used
Contingencies Remaining
Total NPV