## Schedule Budget
Procurement Team
| Name | Role | Direct Labor Cost | Indirect Labor Cost | Total per hour
| Donna Smith (DS) | Strategic Sourcing Manager (SSM) | 39.2157 | 12.9412 | 52.1569
| Robert Golden (RG) | Director of Procurement (DP) | 47.8863 | 15.8025 | 63.6887
| James Brown (JB) | Financial Analyst (FA) | 20.6392 | 6.8109 | 27.4502
| Bill Green (BG) | SME | 31.3897 | 10.3586 | 41.7483
| John Q. Public (JQP) | Owner | 88.9706 | 29.3603 | 118.3309
| Samantha Grey (SG) | Attorney | 74.8422 | 24.6979 | 99.5401
WBS | Task Description | Predecessor | Owner | Role | Start Date | Finish Date | Effort (hours) | Duration (days) | Labor Costs | Percent Complete
0 | Procurement for Janitorial Services |  | DS | SSM | 2013-05-03 | 2013-10-31 | 321.75 | 182 | 34558.46
1 | Receive RFPS |  | DS | SSM, DP | 2013-05-03 | 2013-05-10 | 7.5 | 7 | 813.23
1.1 | Brainstorm | 1 | DS, RG | SSM, DP | 2013-05-07 | 2013-05-07 | 1.25 | 1 | 144.81
1.1.2 | Strategy | 1 | DS, RG | SSM, DP | 2013-05-07 | 2013-05-07 | 0.25 | 1 | 28.96
1.1.2.1 | Mutual Non-Disclosure Agreement (MNDA) | 1 | DS, RG | SSM, DP | 2013-05-07 | 2013-05-07 | 0.25 | 1 | 28.96
1.1.2.2 | Contract Type | 1 | DS, RG | SSM, DP | 2013-05-07 | 2013-05-07 | 0.25 | 1 | 28.96
1.1.2.3 | Length of Agreement | 1 | DS, RG | SSM, DP | 2013-05-07 | 2013-05-07 | 0.25 | 1 | 28.96
1.1.2.4 | Sourcing Approach | 1 | DS, RG | SSM, DP | 2013-05-07 | 2013-05-07 | 0.25 | 1 | 28.96
1.2 | Review current and historical supplier contracts | 1 | DS, RG | SSM, DP | 2013-05-06 | 2013-05-06 | 2 | 1 | 231.69
1.3 | Identify all stakeholders | 1 | DS, RG | SSM, DP | 2013-05-06 | 2013-05-06 | 1 | 1 | 115.85
1.4 | Establish the procurement team | 1 | DS, RG | SSM, DP | 2013-05-07 | 2013-05-10 | 1 | 1 | 115.85
1.4.1 | Decide what skills are required | 1 | DS, RG | SSM, DP | 2013-05-07 | 2013-05-07 | 0.2 | 1 | 23.17
1.4.2 | Find out who has those skills | 1.4.1 | DS, RG | SSM, DP | 2013-05-07 | 2013-05-07 | 0.2 | 1 | 23.17
1.4.3 | Find out availability of those people | 1.4.2 | DS, RG | SSM, DP | 2013-05-07 | 2013-05-07 | 0.2 | 1 | 23.17
1.4.4 | Get those people assigned to procurement team | 1.4.3 | DS, RG, JB, BG, JQP, SG | SSM, DP, FA, SME, Owner, Attorney | 2013-05-07 | 2013-05-10 | 0.2 | 4 | 80.58
1.4.5 | Define roles and responsibilities | 1 | DS | SSM | 2013-05-07 | 2013-05-07 | 0.2 | 1 | 10.43
1.5 | Silent period with existing supplier | 1 | DS, RG, JB, BG, JQP, SG | SSM, DP, FA, SME, Owner, Attorney | 2013-05-03 | 2013-10-31 | 0.25 | 182 | 100.73
1.6 | Establish a High Level Schedule | 1.1.2 | DS | SSM | 2013-05-07 | 2013-05-10 | 2 | 4 | 104.31
2 | Kick-off Meeting | 1.6 | DS | SSM | 2013-05-13 | 2013-05-17 | 6 | 4 | 594.24
2.1 | Decide on date for meeting | 2 | DS | SSM | 2013-05-13 | 2013-05-13 | 0.25 | 1 | 13.04
2.2 | Reserve meeting room | 2 | DS | SSM | 2013-05-13 | 2013-05-13 | 0.25 | 1 | 13.04
2.3 | Create agenda | 2 | DS | SSM | 2013-05-13 | 2013-05-13 | 0.5 | 1 | 26.08
2.4 | Send out agenda | 2 | DS | SSM | 2013-05-13 | 2013-05-13 | 0.5 | 1 | 26.08
2.4.1 | Receive comments/additons to agenda | 2.4 | DS | SSM | 2013-05-14 | 2013-05-14 | 0.5 | 1 | 26.08
2.4.2 | Resend amended agenda | 2.4.1 | DS | SSM | 2013-05-15 | 2013-05-15 | 0.5 | 1 | 26.08
2.5 | Hold meeting | 2.4 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-05-17 | 2013-05-17 | 1.5 | 1 | 359.53
2.6 | Develop action list and/or meeting minutes | 2.5 | DS | SSM | 2013-05-17 | 2013-05-17 | 0.5 | 1 | 26.08
2.7 | Send out action list/minutes | 2.6 | DS | SSM | 2013-05-17 | 2013-05-17 | 0.5 | 1 | 26.08
2.7.1 | Receive comments/additions to action list/minutes | 2.7 | DS | SSM | 2013-05-17 | 2013-05-17 | 0.5 | 1 | 26.08
2.7.2 | Resend action list/minutes | 2.7.1 | DS | SSM | 2013-05-20 | 2013-05-20 | 0.5 | 1 | 26.08
3 | Procurement Plan | 1 | DS | SSM | 2013-05-20 | 2013-05-24 | 27.75 | 4 | 7296.9
3.1 | Finalize procurement strategy | 1.1.2 | DS, JQP | SSM, Owner | 2013-05-20 | 2013-05-20 | 0.5 | 1 | 85.24
3.1.1 | Review strategy with team members | 3.1 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-05-23 | 2013-05-23 | 1 | 1 | 239.69
3.2 | Develop procurement WBS | 1 | DS, BG |  | 2013-05-20 | 2013-05-20 | 6 | 1 | 563.43
3.2.1 | Review WBS with team members | 3.2 | DS, RG, JB, BG, JQP, SG | SSM, DP, FA, SME, Owner, Attorney | 2013-05-23 | 2013-05-23 | 1 | 1 | 402.92
3.3 | Develop procurement schedule | 1.4 | DS, JQP |  | 2013-05-21 | 2013-05-21 | 4 | 1 | 1213.5
3.3.1 | Review schedule with team members | 3.2 | DS, RG, JB, BG, JQP, SG | SSM, DP, FA, SME, Owner, Attorney | 2013-05-23 | 2013-05-23 | 1 | 1 | 402.92
3.4 | Develop procurement budget | 1.4 | N/A
3.4.1 | Review budget with team members | 3.4 | N/A
3.5 | Develop procurement communications plan | 1.4 | DS | SSM | 2013-05-22 | 2013-05-22 | 2 | 1 | 104.31
3.5.1 | Review communications plan with team members | 3.5 | DS, RG, JB, BG, JQP, SG | SSM, DP, FA, SME, Owner, Attorney | 2013-05-23 | 2013-05-23 | 1 | 1 | 402.92
3.6 | Develop procurement risk plan | 1.4 | DS, JB, BG | SSM, FA, SME | 2013-05-22 | 2013-05-22 | 2 | 1 | 242.71
3.6.1 | Review risk plan with team members | 3.6 | DS, RG, JB, BG, JQP, SG | SSM, DP, FA, SME, Owner, Attorney | 2013-05-23 | 2013-05-23 | 1 | 1 | 402.92
3.7 | Review procurement plan with entire team | 3.2, 3.3, 3.4, 3.5, 3.6 | DS, RG, JB, BG, JQP, SG | SSM, DP, FA, SME, Owner, Attorney | 2013-05-23 | 2013-05-23 | 4 | 1 | 1611.66
3.8 | Finalize procurement plan | 3.6.1 |  | SSM, DP, FA, SME, Owner, Attorney | 2013-05-24 | 2013-05-24 | 4 | 1 | 1611.66
3.9 | Distribute procurement plan | 3.8 |  |  | 2013-05-24 | 2013-05-24 | 0.25 | 1 | 13.04
4 | Solicitation | 3 | DS | SSM | 2013-05-28 | 2013-06-10 | 73.75 | 14 | 6367.38
4.1 | Silent period with potential suppliers & existing supplier | 3.8 | DS, RG, JB, BG, JQP, SG | SSM, DP, FA, SME, Owner, Attorney | 2013-05-03 | 2013-10-31 | 0.25 | 182 | 100.73
4.2 | Draft RFP | 3.8 | DS | SSM | 2013-05-28 | 2013-06-07 | 73.5 | 13 | 5030
| Memorial Day holiday |  |  |  | 2013-05-27 | 2013-05-27 |  | 1
4.2.1 | RFP Schedule | 1.6 | DS | SSM | 2013-05-28 | 2013-05-28 | 4 | 1 | 208.63
4.2.1.1 | Review with team | 4.2.1 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-05-28 | 2013-05-28 | 2 | 1 | 479.37
4.2.2 | Statement of Work (Scope of Work) | 1.4.5 | BG, DS | SME, SSM | 2013-05-29 | 2013-05-30 | 8 | 2 | 751.24
4.2.2.1 | Review with team | 4.2.2 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-06-04 | 2013-06-04 | 2 | 1 | 479.37
4.2.3 | Determine Type of Agreement Document | 1.1 | DS, SG | SSM, Attorney | 2013-05-30 | 2013-05-30 | 1 | 1 | 151.7
4.2.3.1 | Sample Terms & Conditions | 4.2.3 | DS | SSM | 2013-05-30 | 2013-05-30 | 2 | 1 | 104.31
4.2.4 | Develop pricing model | 1.2 | JB, DS, BG | FA, SSM, SME | 2013-05-30 | 2013-05-30 | 1 | 1 | 121.36
4.2.5 | RFP General Instructions | 4.2.1 | DS | SSM | 2013-05-31 | 2013-05-31 | 4 | 1 | 208.63
4.2.6 | Mutual Nondisclosure Agreement (MNDA) | 4.2.3 | DS | SSM | 2013-05-31 | 2013-05-31 | 2 | 1 | 104.31
4.2.7 | Proposal Signature Page | 4.2.3 | DS | SSM | 2013-05-31 | 2013-05-31 | 0.5 | 1 | 26.08
4.2.8 | Develop weighted evaluation criteria | 4.2.2 | DS, BG | SSM, SME | 2013-06-03 | 2013-06-03 | 8 | 1 | 1480.35
4.2.8.1 | Review with evaluation team | 4.2.8 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-06-04 | 2013-06-04 | 2 | 1 | 479.37
4.2.9 | MWDBE Certification | 4.2.3 | DS | SSM | 2013-06-04 | 2013-06-04 | 0.5 | 1 | 26.08
4.2.10 | HUB Certification | 4.2.3 | DS | SSM | 2013-06-04 | 2013-06-04 | 0.5 | 1 | 26.08
4.2.11 | Form W-9 | 4.2.3 | DS | SSM | 2013-06-04 | 2013-06-04 | 0.5 | 1 | 26.08
4.3 | Review entire RFP with team | 4.2 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-06-05 | 2013-06-05 | 1 | 1 | 239.69
4.3.1 | Make changes as required | 4.3 | DS | SSM | 2013-06-06 | 2013-06-06 | 2 | 1 | 104.31
4.3.2 | Distribute to team for final review | 4.3.1 | DS | SSM | 2013-06-06 | 2013-06-06 | 0.25 | 1 | 13.04
4.4 | Commodity Strategy | 3 | JB | FA | 2013-05-28 | 2013-05-31 | 22.25 | 4 | 715.08
4.4.1 | Industry/Commodity Profile Analysis | 3 | JB | FA | 2013-05-28 | 2013-05-28 | 4 | 1 | 109.8
4.4.2 | Purchasing Profile | 4.4.1 | JB | FA | 2013-05-28 | 2013-05-28 | 2 | 1 | 54.9
4.4.3 | Supplier Financial Analysis | 4.4.2 | JB | FA | 2013-05-28 | 2013-05-29 | 8 | 2 | 219.6
4.4.4 | Total Cost of Ownership | 4.4.3 | JB | FA | 2013-05-30 | 2013-05-30 | 4 | 1 | 109.8
4.4.5 | Determine Qualified Supplier Bid List | 4.4.4 | JB, DS | FA, SSM | 2013-05-30 | 2013-05-30 | 2 | 1 | 159.21
4.4.5.1 | Contact names and information | 4.4.5 | JB | FA | 2013-05-31 | 2013-05-31 | 2 | 1 | 54.9
4.4.5.2 | Send all information to SSM | 4.4.5.1 | JB | FA | 2013-05-31 | 2013-05-31 | 0.25 | 1 | 6.86
4.5 | Finalize RFP | 4.3, 4.4 | DS | SSM | 2013-06-06 | 2013-06-07 | 8 | 2 | 417.25
4.6 | Send RFP out | 4.5 | DS | SSM | 2013-06-10 | 2013-06-10 | 2 | 1 | 104.31
5 | RFP Process | 4.6 | DS | SSM | 2013-06-10 | 2013-06-28 | 12.25 | 19 | 638.92
5.1 | RFP silent period with potential suppliers & existing supplier | 4.6 | DS | SSM | 2013-06-10 | 2013-10-31 | 0.25 | 133 | 13.04
5.2 | Receive questions on RFP | 5.1 | DS | SSM | 2013-06-10 | 2013-06-19 | 2 | 10 | 104.31
5.2.1 | Assemble questions and answers | 5.2 | DS | SSM | 2013-06-20 | 2013-06-21 | 8 | 2 | 417.25
5.2.2 | Send out assembled questions and answers to all participants | 5.2.1 | DS | SSM | 2013-06-24 | 2013-06-24 | 2 | 1 | 104.31
6 | Proposal Analysis | 5 | DS | SSM | 2013-06-28 | 2013-08-02 | 92.5 | 36 | 7432.63
6.1 | Receive proposals | 5.2.2 | DS | SSM | 2013-06-28 | 2013-06-28 | 8 | 1 | 417.25
6.1.1 | Reject all proposals that are not signed | 6.1 | DS | SSM | 2013-07-01 | 2013-07-01 | 4 | 1 | 208.63
6.1.2 | Reject all proposals submitted after the deadline | 6.1 | DS | SSM | 2013-07-01 | 2013-07-01 | 4 | 1 | 208.63
6.2 | Distribute all acceptable proposals to evaluation team | 6.1 | DS | SSM | 2013-07-02 | 2013-07-02 | 4 | 1 | 208.63
6.3 | Team evaluates all proposals independently | 6.2 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-07-02 | 2013-07-10 | 20 | 9 | 4793.72
| 4th of July holiday |  |  |  | 2013-07-04 | 2013-07-04 |  | 1
6.4 | Team returns all evaluations | 6.3 | DS | SSM | 2013-07-11 | 2013-07-11 | 2 | 1 | 104.31
6.5 | Review and collate all evaluations | 6.4 | DS | SSM | 2013-07-11 | 2013-07-12 | 8 | 2 | 417.25
6.6 | Distribute collated evaluations to team | 6.5 | DS | SSM | 2013-07-15 | 2013-07-15 | 2 | 1 | 104.31
6.7 | Evaluation team meets to decide on top proposals | 6.6 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-07-16 | 2013-07-16 | 6 | 1 | 239.69
6.8 | Collect questions on proposals for short listed potential suppliers | 6.7 | DS | SSM | 2013-07-16 | 2013-07-16 | 2 | 1 | 104.31
6.9 | Notify short list | 6.7 | DS | SSM | 2013-07-17 | 2013-07-17 | 2 | 1 | 104.31
6.1 | Schedule oral presentations | 6.9 | DS | SSM | 2013-07-17 | 2013-07-19 | 5 | 3 | 260.78
6.10.1 | Verify date and time with each company | 6.1 | DS | SSM | 2013-07-17 | 2013-07-18 | 4 | 2 | 208.63
6.10.2 | Reserve meeting room | 6.1 | DS | SSM | 2013-07-17 | 2013-07-17 | 0.5 | 1 | 26.08
6.10.3 | Notify evaluation team | 6.1 | DS | SSM | 2013-07-17 | 2013-07-18 | 0.5 | 2 | 26.08
6.11 | Oral presentations | 6.10.2 | DS | SSM | 2013-07-31 | 2013-08-01 | 16.5 | 2 | 2850.74
6.11.1 | Make sure someone greets presenters | 6.10.2 | DS | SSM | 2013-07-19 | 2013-07-19 | 1 | 1 | 52.16
6.11.2 | Make sure equipment is ready and working | 6.10.2 | DS | SSM | 2013-07-30 | 2013-07-30 | 1 | 1 | 52.16
6.11.3 | Make sure refreshments are ready | 6.10.2 | DS | SSM | 2013-07-30 | 2013-07-31 | 0.5 | 2 | 26.08
6.11.4 | Questions | 6.8 | DS | SSM | 2013-07-19 | 2013-07-26 | 7 | 8 | 365.1
6.11.4.1 | Prepared and who will ask each one | 6.8 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-07-19 | 2013-07-26 | 4 | 8 | 958.74
6.11.5.1 | As presentation is given | 6.11.4.1 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-07-31 | 2013-08-01 | 1.5 | 2 | 359.53
6.12 | Thank yous and walking presenters out | 6.11 | DS | SSM | 2013-07-31 | 2013-08-01 | 1.5 | 2 | 78.24
6.13 | Meeting to decide on contract awardee | 6.11 | DS, JB, BG, JQP | SSM, FA, SME, Owner | 2013-08-02 | 2013-08-02 | 4 | 1 | 958.74
7 | Negotiations | 6.13 | DS | SSM | 2013-07-19 | 2013-08-19 | 34 | 32 | 3503.29
7.1 | Develop negotiation strategy | 4.6 | DS, JB, BG | SSM, FA, SME | 2013-07-19 | 2013-08-02 | 8 | 15 | 970.84
7.1.1 | Where negotiation takes place | 4.6 | DS, JB, BG | SSM, FA, SME | 2013-07-19 | 2013-08-02 | 4 | 15 | 485.42
7.1.2 | Win-win or hard ball | 4.6 | DS, JB, BG | SSM, FA, SME | 2013-07-19 | 2013-08-02 | 4 | 15 | 485.42
7.2 | Identify negotiation team | 4.6 | DS, JB, BG | SSM, FA, SME | 2013-07-19 | 2013-08-02 | 1 | 15 | 121.36
7.2.1 | Fully identify and communicate roles | 7.2 | DS | SSM | 2013-07-19 | 2013-08-02 | 1 | 15 | 52.16
7.3 | Conduct Negotiations | 7.1 | DS, JB, BG | SSM, FA, SME | 2013-08-05 | 2013-08-16 | 8 | 12 | 970.84
7.3.1 | Finalize deal including terms and conditions | 7.3 | DS | SSM | 2013-08-19 | 2013-08-19 | 8 | 1 | 417.25
8 | Contract Finalization | 7.3 | DS | SSM | 2013-07-19 | 2013-09-09 | 62 | 54 | 4748.18
8.1 | Draft contract | 7.3.1 | DS | SSM | 2013-07-19 | 2013-08-02 | 12 | 15 | 625.88
8.1.1 | Review contract | 8.1 | RG, SG | DP, Attorney | 2013-08-20 | 2013-08-23 | 8 | 4 | 1305.83
8.2 | Obtain approval signatures | 8.1.1 | DS | SSM | 2013-08-26 | 2013-08-30 | 40 | 5 | 2086.27
| Labor Day holiday |  |  |  | 2013-09-02 | 2013-09-02 |  | 1
8.3 | Execute contract | 8.2 | DS | SSM | 2013-09-09 | 2013-10-31 | 2 | 53 | 104.31
9 | Notification of unsuccessful suppliers | 8.3 | DS | SSM | 2013-09-10 | 2013-09-12 | 6 | 3 | 312.94
9.1 | Preliminary notification | 8.3 | DS | SSM | 2013-09-10 | 2013-09-11 | 4 | 2 | 208.63
9.2 | Formal debriefing | 9.1 | DS | SSM | 2013-09-12 | 2013-09-12 | 2 | 1 | 104.31
10 | Contract Administration | 8.3 | DS | SSM | 2013-09-09 | End of contract term | N/A | N/A | N/A