## PMO Performance
Key:
Planning Input (Enter data at start of period)
Results Input (Enter data at end of period)
Output
text | Invalid
Name: |  | Your PMO
Position: |  | PMO Leader
Supervisor:
Planning Date: |  | 2001-12-28
Comments:
Performance Measurement for any PMO
Key Value Areas (KVA):
|  |  | Weight (%): | Contribution: | Performance: | Potential: | Conversion:
1 | Throughput Optimization |  | 10% | 3.1 | 0.31 | 0.4 | 77.5%
2 | Resource Optimization |  | 15% | 2.7 | 0.405 | 0.6 | 67.5%
3 | On Time |  | 25% | 3.6 | 0.9 | 1 | 90%
4 | On Budget |  | 25% | 2.7 | 0.675 | 1 | 67.5%
5 | On Scope |  | 25% | 3.1 | 0.775 | 1 | 77.5%
| SUMMARY |  |  |  | 3.065 | 4 | 76.62%
Performance Objectives
KVA - 1: | Throughput Optimization | [6 empty] | Evaluation Date:
Detail: | The Percentage of Completed Projects
| Contributing Value Area: |  | Weights: | Standard: |  | Contribution: | Potential: | Conversion:
1 | More Projects Completed Than Planned |  | 40% | 4 |  | 1.6 | 1.6 | 100%
2 | Projects Delivered Early |  | 30% | 3 |  | 0.9 | 1.2 | 75%
3 | Projects Underspent |  | 30% | 2 |  | 0.6 | 1.2 | 50%
4
5
| TOTAL: |  |  |  |  | 3.1 | 4 | 77.5%
More Projects Completed Than Planned
| 4 - Excellent | 10% or more
| 3 - Very Good | 5% or more
| 2 - Satisfactory | < 5%
| 1 - Unsatisfatory | Everything else
Projects Delivered Early
| 4 - Excellent | 10% More Than Planned
| 3 - Very Good | 5% or More
| 2 - Satisfactory | < 5%
| 1 - Unsatisfatory | Everything Else
Projects Underspent
| 4 - Excellent | 10% or more
| 3 - Very Good | 5% or more
| 2 - Satisfactory | <5%
| 1 - Unsatisfatory | Everything Else
4 - Excellent
3 - Very Good
2 - Satisfactory
1 - Unsatisfatory
0
4 - Excellent
3 - Very Good
2 - Satisfactory
1 - Unsatisfatory
KVA - 2: | Resource Optimization | [6 empty] | Evaluation Date:
Detail: | Resources are fairly allocated and assigned
| Contributing Value Area: |  | Weights: | Standard: |  | Contribution: | Potential: | Conversion:
1 | Key Strategic Resources Optimized |  | 40% | 3 |  | 1.2 | 1.6 | 75%
2 | Non-Productive Time |  | 30% | 2 |  | 0.6 | 1.2 | 50%
3 | Allocations |  | 30% | 3 |  | 0.9 | 1.2 | 75%
4
5
| TOTAL: |  |  |  |  | 2.7 | 4 | 67.5%
Key Strategic Resources Optimized
| 4 - Excellent | 95% of time
| 3 - Very Good | 87% or better
| 2 - Satisfactory | 80% or better
| 1 - Unsatisfatory | Everything Else
Non-Productive Time
| 4 - Excellent | Less Than 5% for Total Resource Average
| 3 - Very Good | Less than 10% for Total Resource Average
| 2 - Satisfactory | Less Than 30% for Total Resource Average
1 - Unsatisfatory
Allocations
| 4 - Excellent | > 90% & < 120% for Total Resource Average
| 3 - Very Good | > 85% & < 120% for Total Resource Average
| 2 - Satisfactory | > 75% & < 150% for Total Resource Average
| 1 - Unsatisfatory | Everything Else
4 - Excellent
3 - Very Good
2 - Satisfactory
1 - Unsatisfatory
4 - Excellent
3 - Very Good
2 - Satisfactory
1 - Unsatisfatory
KVA - 3: | On Time | [6 empty] | Evaluation Date:
Detail: | Project completed on-time
| Contributing Value Area: |  | Weights: | Standard: |  | Contribution: | Potential: | Conversion:
1 | Projects |  | 40% | 4 |  | 1.6 | 1.6 | 100%
2 | Resources |  | 40% | 3 |  | 1.2 | 1.6 | 75%
3 | Reporting |  | 20% | 4 |  | 0.8 | 0.8 | 100%
4
5
| TOTAL: |  |  |  |  | 3.6 | 4 | 90%
Projects
| 4 - Excellent | Less than 5% late
| 3 - Very Good | Less than 10% late
| 2 - Satisfactory | Less than 20% late
| 1 - Unsatisfatory | Everything Else
Resources
| 4 - Excellent | Less than 5% of all resources released late from assignments
| 3 - Very Good | Less than 10% of all resources released late from assignments
| 2 - Satisfactory | Less than 20% of all resources released late from assignments
| 1 - Unsatisfatory | Everything Else
Reporting
| 4 - Excellent | All projects status reporting on time
| 3 - Very Good | < 3% reporting status late
| 2 - Satisfactory | <10%reporting status late
| 1 - Unsatisfatory | Everything Else
4 - Excellent
3 - Very Good
2 - Satisfactory
1 - Unsatisfatory
0
4 - Excellent
3 - Very Good
2 - Satisfactory
1 - Unsatisfatory
KVA - 4: | On Budget | [6 empty] | Evaluation Date:
Detail: | Projects are completed within budgetary limits
| Contributing Value Area: |  | Weights: | Standard: |  | Contribution: | Potential: | Conversion:
1 | Projects Underbudget |  | 40% | 3 |  | 1.2 | 1.6 | 75%
2 | Projects Accelerated Fiscally |  | 30% | 3 |  | 0.9 | 1.2 | 75%
3 | Projects Started from Unspent Money |  | 30% | 2 |  | 0.6 | 1.2 | 50%
4
5
| TOTAL: |  |  |  |  | 2.7 | 4 | 67.5%
Projects Underbudget
| 4 - Excellent | 10% or More of all Projects
| 3 - Very Good | 5% or More of all Projects
| 2 - Satisfactory | < 5% or More of all Projects
| 1 - Unsatisfatory | Everything Else
Projects Accelerated Fiscally
| 4 - Excellent | 10% of all projects receiving unspent monies from other projects that resulted in accleration
| 3 - Very Good | 5% of all projects receiving unspent monies from other projects that resulted in acceleration
| 2 - Satisfactory | < 5%
| 1 - Unsatisfatory | Everything Else
Projects Started from Unspent Money
| 4 - Excellent | 10% or More of Total Project Portfolio funded from Unspent Budgets
| 3 - Very Good | 5% or More of Total Project Portfolio funded from Unspent Budgets
| 2 - Satisfactory | < 5%
| 1 - Unsatisfatory | Everything Else
4 - Excellent
3 - Very Good
2 - Satisfactory
1 - Unsatisfatory
0
4 - Excellent
3 - Very Good
2 - Satisfactory
1 - Unsatisfatory
KVA - 5: | On Scope | [6 empty] | Evaluation Date:
Detail: | Projects are completed on scope
| Contributing Value Area: |  | Weights: | Standard: |  | Contribution: | Potential: | Conversion:
1 | On Scope, Time and Budget |  | 40% | 4 |  | 1.6 | 1.6 | 100%
2 | Resources Optimized |  | 30% | 3 |  | 0.9 | 1.2 | 75%
3 | Customer Satisfaction |  | 30% | 2 |  | 0.6 | 1.2 | 50%
4
5
| TOTAL: |  |  |  |  | 3.1 | 4 | 77.5%
On Scope, Time and Budget
| 4 - Excellent | 95% of all completed projects on scope, early and underspent
| 3 - Very Good | 88% of all completed projects on scope, early and underspent
| 2 - Satisfactory | 80% or better of all completed projects
| 1 - Unsatisfatory | everything else
Resources Optimized
| 4 - Excellent | Resources released from assignments early 10% or better from all completed projects
| 3 - Very Good | 5%+
| 2 - Satisfactory | < 5%
| 1 - Unsatisfatory | Everything Else
Customer Satisfaction
| 4 - Excellent | 95%+ for all completed projects
| 3 - Very Good | 90%+ for all completed projects
| 2 - Satisfactory | 80%+ for all completed projects
| 1 - Unsatisfatory | Everything Else
4 - Excellent
3 - Very Good
2 - Satisfactory
1 - Unsatisfatory
4 - Excellent
3 - Very Good
2 - Satisfactory
1 - Unsatisfatory
Training Objectives
| Short-Term | Teach project teams how to manage inter/intra-dependencies on critical path
| Long-Term | Teach team members how to recognize project delivery opportunities and threats for completing work earlier
Performance Factors
| Employee | Transparaency
| Supervisor | Accountability
Promotability |  | More projects are activated and completed with fewer resources