## Project Settings
WIR Project Settings
WIR Project Name: Project Diamond
WIR Company Name: ABC Oil and Gas Company (ABC)
WIR Project Settings Info:
-Enter project name and company name for use in the WIR system. - Default settings - A Kongsberg WIR representative will go through these options together with the company representative before project startup.

## Diamond CPC Network
Diamond Client Prime Contratcor (CPC) Network is a communication interaction network for the Diamond Project client's (ABC Corporation) main contractors to interact on interface related to issues along their shared scope of work boundaries.
Contractors | Name to use in WIR | Abbriviation
Topside EPC | Topside EPC (DGO)
Jacket EPC | Jacket EPC (SupSys)
Transport & Install | Transport & Install (Marigo)
Living Quarters | Living Quarters (Hotel)
Hook-Up | Hook-Up (Joiners)
Drilling & Wells | Drilling & Wells (Yarko)
Interface Groups
Lead Interface Contractor | Topside EPC | Jacket EPC | Transport & Install | Living Quarters | Hook-Up | Drilling & Wells
Interface Contractor
Topside EPC
Jacket EPC
Transport & Install
Living Quarters
Hook-Up
Drilling & Wells
WIR Contractors Info:
Enter name of the known contractors, name to use in the WIR system, and a abbriviation to be entered into the system.
WIR Interface Groups Info:
Try to set up a matrix / table as seen in example A or B to show the interface groups on the project.

## Diamond Internal CIP Network
The Diamond Project Internal Network is established for the Client's (ABC Corporation) sub-project teams to formally communicate and agreed on issues affecting their areas of responsibility and those that impact their contractors scopes of work. This network is intended for the Client's management teams to align toward risk mitigation staregties, scope changes, and other issues affecting multiple parts of the project. This ensures alignment of repsective company personbnel prior to Client teams issuing formal correspondence to their respectvie contractors.
Contractors | Name to use in WIR | Abbriviation
Contractor 1 | Contractor 1
Contractor 2 | Contractor 2
Contractor 3 | Contractor 3
Contractor 4 | Contractor 4
Contractor 5 | Contractor 5
Contractor 6 | Contractor 6
Contractor 7 | Contractor 7
Contractor 8 | Contractor 8
Contractor 9 | Contractor 9
Contractor 10 | Contractor 10
Interface Groups
Lead Interface Contractor | Contractor 1 | Contractor 2 | Contractor 3 | Contractor 4 | Contractor 5 | Contractor 6 | Contractor 7 | Contractor 8 | Contractor 9 | Contractor 10
Interface Contractor
Contractor 1
Contractor 2
Contractor 3
Contractor 4
Contractor 5
Contractor 6
Contractor 7
Contractor 8
Contractor 9
Contractor 10
WIR Contractors Info:
Enter name of the known contractors, name to use in the WIR system, and a abbriviation to be entered into the system.
WIR Interface Groups Info:
Try to set up a matrix / table as seen in example A or B to show the interface groups on the project.

## Diamond Industry (PSI) Network
The Diamond Project Sponsor to Industry (SPI) Network is established for the Diamond Project sponsor to interact with the industry safety agency, and other associated projects in the field development, to ensure alignment between the project and compliance to indystry health, safety and environmental regulations. This network is used as a supplemental tool to futher clarify design and development aspects of the respectvie projects leading to safety agency audits and verifications.
Contractors | Name to use in WIR | Abbriviation
Industry Safety (PSA) | Industry Safety (PSA)
Project Diamond (ABC) | Project Diamond (ABC)
Project Sapphire (XYZ) | Project Sapphire (XYZ)
Project Oil Pipe (POL) | Project Oil Pipe (POL)
Project Gas Pipe (PGP) | Project Gas Pipe (PGP)
Contractor 6 | Contractor 6
Contractor 7 | Contractor 7
Contractor 8 | Contractor 8
Contractor 9 | Contractor 9
Contractor 10 | Contractor 10
Interface Groups
Lead Interface Contractor | Industry Safety (PSA) | Project Diamond (ABC) | Project Sapphire (XYZ) | Project Oil Pipe (POL) | Project Gas Pipe (PGP)
Interface Contractor
Industry Safety (PSA)
Project Diamond (ABC)
Project Sapphire (XYZ)
Project Oil Pipe (POL)
Project Gas Pipe (PGP)
WIR Contractors Info:
Enter name of the known contractors, name to use in the WIR system, and a abbriviation to be entered into the system.
WIR Interface Groups Info:
Try to set up a matrix / table as seen in example A or B to show the interface groups on the project.

## Diamond_Sapphire (P2P) Network
The Diamond Project-to-Project (P2P) interface network is established to conduct interface cordination with Project Sapphire (XYZ Corporation) for which Project Diamond must integrate into. Project Diamond is envisioned to send its hydrocarbons (oil and gas) through pipelines to Project Sapphire, who will process and further send the combined hydrocarbons to onshore processing facilities. Also, Project Sapphire will provide power to Project Diamond through a subsea power cable. Oil and gas pipelines to deliver hydrocarbons to onshore facilities is being developed by POL industries and PGP incorporated.
Contractors | Name to use in WIR | Abbriviation
Project Diamond (ABC) | Project Diamond (ABC)
Project Sapphire (XYZ) | Project Sapphire (XYZ)
Project Oil Pipe (POL) | Project Oil Pipe (POL)
Project Gas Pipe (PGP) | Project Gas Pipe (PGP)
Interface Groups
Lead Interface Contractor | Project Diamond (ABC)
Interface Contractor
Project Diamond (ABC)
Project Sapphire (XYZ)
Project Oil Pipe (POL)
Project Gas Pipe (PGP)
0
0
0
0
0
0
WIR Contractors Info:
Enter name of the known contractors, name to use in the WIR system, and a abbriviation to be entered into the system.
WIR Interface Groups Info:
Try to set up a matrix / table as seen in example A or B to show the interface groups on the project.

## Diamond_Sapphire (O2O) Network
The Diamond Project Organization-to-Organization (O2O) interface network is established to conduct interface cordination between companies iwhose projects are involved in the field development (Project Diamond (ABC), Project Sapphire (XYZ Corporation), Project Oil Pipeline (POL), and Project Gas Pipeline (PGP). This group is established for the purpose of coordinatign and agreeing to details related to the field development coopertion agreement established between the four companies.
Organizations | Name to use in WIR | Abbriviation
ABC Corporation | Project Diamond (ABC)
XYZ Corporation | Project Sapphire (XYZ)
POL Industries | Project Oil Pipe (POL)
PGP Incorporated | Project Gas Pipe (PGP)
Interface Groups
Lead Interface Contractor | ABC Corp (Diamond) | XPY Corp (Sapphire) | POL (Oil Pipe)
Interface Contractor
Project Diamond (ABC)
Project Sapphire (XYZ)
Project Oil Pipe (POL)
Project Gas Pipe (PGP)
Discipines
|  |  | CM | Commercial
|  |  | AL | Allocation
|  |  | OP | Operations
|  |  | CO | Commissioning
|  |  | AG | Cooperation Agreement
|  |  | PR | Processes
|  |  | PO | Procedures
|  |  | A | Adminsitrative
|  |  | B | Procurment
|  |  | LI | License
WIR Contractors Info:
Enter name of the known contractors, name to use in the WIR system, and a abbriviation to be entered into the system.
WIR Interface Groups Info:
Try to set up a matrix / table as seen in example A or B to show the interface groups on the project.

## Diamond Prime Internal Network
Diamond Project Prime Contractor (PCI) Network is a communication interaction network established to coordinate interafces internal to the Topside EPC (Engineering, Procurmenet, and Construction) team. The Topside EPC team consists of four (4) different constractors; engineering, procurement, constrcution and SAS. This network was mandated by the Client due to assessment of high risk since these companies have no previous experience working together and as a result of each company using different management ystems. Given the inportance of this part of the project, this network is critical to ensuring good communication beteween the Topside EPC team.
Contractors | Name to use in WIR | Abbriviation
Colbalt Engineering Inc. | Topside Engineering (CEI)
Project Procurement Services (PPS) | Topside Procurement (PPS)
Waverton Construction Limited (WCL) | Topside Construction (WCL)
Safety Automation System Inc (SASI) | Topside SAS (SASI)
Interface Groups
Lead Interface Contractor | Topside Engineering (CEI) | Topside Pocurement (PPS) | Topside Construction (WCL) | Topside SAS (SASI)
Interface Contractor
Topside Engineering (CEI)
Topside Procurement (PPS)
Topside Construction (WCL)
Topside SAS (SASI)
WIR Contractors Info:
Enter name of the known contractors, name to use in the WIR system, and a abbriviation to be entered into the system.
WIR Interface Groups Info:
Try to set up a matrix / table as seen in example A or B to show the interface groups on the project.

## Users
WIR Users
Contractor | First Name | Last Name | E-mail Address | Read / Write | Read | Discipline(s)
WIR Users Info:
Enter information on the users that will have access to the system.
Information needed is:
Contractor
First Name
Last Name
Email
Discipline
Write or Read Access
Email Interface Notifications

## Disciplines
WIR Disciplnes
Discipline Code | Discipline | Lead Contractor 1 | Lead Contractor 2 | Lead Contractor 3 | Lead Contractor X
A | Administration
B | Procurement
C | Civil/architect
D | Drilling
E | Electrical
F | Project control/cost/economy
G | Geology
H | HVAC
I | Instrumentation/metering
J | Marine operation
K | Inspection
L | Piping/layout
M | Material technology
N | Structural
O | Operation
P | Process
Q | Quality management
R | Mechanical
S | Health, safety and environment (HSE)
T | Telecommunication
U | Subsea
W | Weight control
X | Reservoir
Y | Pipeline
Z | Multidiscipline
..
WIR Discipline Info:
Enter information on the disciplines to be used by the different lead contractors.

## Config (hidden)
WIR Configuration
Default Settings - (Can be changed before and during project) | Default Parameter | Description of setting
Interface Contractors (IC) are allowed to Add / Edit Interfaces. | Yes | Allows for IC to create new interface items with the status identified.
Interface Contractors may Open Interfaces | Yes | Allows for IC to create an interface item from Identified to Open
Automatic Interface First Issue Planned(IFI)Date, based on Interface Approved Issue Date (IAI) | No | Automatic Interface First Issue Planned(IFI)Date, based on Interface Approved Issue Date (IAI)
Receiving Time Limit (In Days) | 9 | Amount of days the Receiving Contractor have to submit a response
Responsible Time Limit (In Days) | 9 | Amount of days the Responsible Contractor have to submit a response
IAI Email Reminder | Yes | Enable email send out before and on IAI Overdue
Send IAI Email Reminder X days before IAI date | X | Amount of days before the IAIA reminder email will be sent out.
Company To Approve Interface Items Open on an Interaface Group | Initially No | Company must approve all items raised in an interface group, before they are accepted in the WIR system
Company To Approve Interface Items Close on an Interaface Group | Initially No | Company must approve all items Closedin an interface group, before they are accepted in the WIR system
"System" tagging | Project Specific | Posibility to tag Interface items with a "System"
"Disciplines" tagging | Project Specific | Posibility to tag Interface items with a "Discipline"
Automated numbering of interface items | Yes | Possible settings: Numbering on Project level, Interface Group level, Discipline Level and manual entering of numbers. System will prevent duplicates to be created.
Data Maturity | No | Function to allow an interface item go through the three phases. Preliminary, Approved for Design & Approved for Contruction before it is closed out.
Enable Need Date | No | Add a "Need Date" column in the Interface register.
Enable Priority on Interface Items | Yes | Allows to give piority on interfaec items. Thh range is Normal, Low, Medium, High.
Display Discipline Numbers in Interface Register | Yes | Displays the Discipline
Company access to reports | Yes | Company to have access to reports in system
Contractors access to reports | Yes | Contractors to have access to reports in system
Time Zone | Project Specific | Select server time zone
Enable Dual Disciplines on Interface Items | No | Allow for both contractors to specify individual disciplines within each interface group.
Company Logo Visible | Yes | Have Company logo visble in header or menu area of WIR