## EVA
Earned Value Analysis | Today (mm/dd/yyyy)
Budget at Completion (BAC) – Initial Budget |  | Budget at Completion (BAC) – Initial Budget | 100000
Project Start Date (mm/dd/yyyy) |  | Project Start Date (mm/dd/yyyy) | 2012-01-02
Planned End Date (mm/dd/yyyy) |  | Planned End Date (mm/dd/yyyy) | 2013-12-30
Actual Cost (AC) - Actual Cost of Work |  | Actual Cost of the Work Performed (AC) | 550000
Earned Value (EV) - Value of Completed Work |  | Budgeted Cost of the Work Performed (EV) | 450000
Planned Value (PV) - Planned Cost of Work |  | Budgeted Cost of the Work Scheduled (PV) | 500000
Cost Variance (CV=EV – AC) |  | Cost Variance (CV=EV – AC) | -100000 | Over the budget
Schedule Variance (SV=EV-PV) |  | Schedule Variance (SV=EV-PV) | -50000 | Behind the schedule
Cost Performance Index (CPI=EV/AC) |  | Cost Performance Index (CPI=EV/AC) | 0.81818
Schedule Performance Index (SPI=EV/PV) |  | Schedule Performance Index (SPI=EV/PV) | 0.9
Estimate At Completion (EAC=BAC/CPI) |  | Estimate At Completion (EAC=BAC/CPI) | 122222.2222
Variance at Completion (VAC=BAC-EAC) |  | Variance at Completion (VAC=BAC-EAC) | -22222.2222
Estimated Completion Date |  | Estimated Completion Date | 2014-03-20
Developed by Dan Epstein, 2010