## Start
Risk Assessment
(For Small and Medium Projects Under $1M)
Client Name:
Project Name:
Date (mm/dd/yy):
Copyright © Daniel Epstein, 2010

## Risks A
Common Risk Statements 1-6
Client Name:
Project Name:
Date (mm/dd/yy):
Score: E - Exceptional, H - High, M - Medium, L - Low Copyright © Daniel Epstein
Risk Identification | Select Risk | Risk Score
1. Business Requirements
<N/A> Not Applicable |  |  | L | 0 | 0
<L> Business Requirements Document is signed off by due date. |  |  | L | 4 | 0
<M> Business Requirements Document available, but not signed off yet by due date |  |  | M |  | 0
Ensure that business requirements are signed off by all parties and estimates are agreed.
Ensure that a project charter is received and a kick off meeting has taken place
Ensure all PM processes are established and mandatory.
<H> Business Requirements Document is not available and requirements are not complete by due date |  |  | H |  | 0
Produce business requirements and have it signed. Ensure that estimates are produced and agreed by all parties.
Ensure that a project charter is received and a kick off meeting has taken a place
Ensure that all PM processes are enforced.
2. The delivery team familiarity with similar projects
<L> The Delivery Team is familiar with similar projects. |  | L | L | 1 | 2
<M> Some members of Delivery Team are familiar with the project, but most of them don't. |  |  | M |  | 0
Assign the most experienced team member to guide the team for the duration of the project
Propose different implementation method
<H> The Delivery Team has no experience with similar projects. |  |  | H |  | 0
Find an expert with the required experience to guide the team for the duration of the project
Use different, more familiar approach for the project.
Hire external resources to develop less familiar parts of the project.
3. Project complexity
<L> The project is straightforward with no obvious complexities. |  | L | L | 1 | 2
<M> The project is not straightforward or the integration with another unit is required. |  |  | M |  | 0
Attempt using more familiar approach and methods.
Run quality review and the technical walkthrough of the existing approach.
Analyze integration to other units with clients who are familiar with the issue.
Confirm the approach with the subject matter expert.
<H> The project has considerable complexity or the integration with several external units is required. |  |  | H |  | 0
Develop and propose to client the standard approach to reduce the complexity, even if some minor requirements can't be implemented.
Run quality review and the technical walkthrough of the existing approach.
Analyze integration to other units with the clients familiar with the issue.
Confirm the approach with the subject matter expert.
Include the subject matter expert into the team.
4. The Statement of Work |  |  |  | 1
<L> The Statement of Work uses the provided in the book template and signed off by all parties. |  | L | L | 1 | 2
<H> The Statement of Work does not includes all parts of the provided in the book template or not signed off by all parties. |  |  | H |  | 0
Complete the Statement of Work as required and have it signed off.
5. Project Plan Package
<L> The project plan package is complete, achievable and agreed to by the client and the delivery team. |  | L | L | 2 | 2
<M> There are some doubts that the project can be delivered on time or the project budget may exceed the plan by 10% or more. |  |  | M |  | 0
Validate your concerns with the client and obtain client acceptance
Adjust the planned risk contingency and obtain client's acceptance.
<H> There are serious doubts that the project will be delivered on time or the project budget is questionable (more than 10% above the plan). |  |  | H |  | 0
Run a troubled project assessment and resolve the issue.
After resolving the issue, adjust the project plan, validate it with the client and obtain client acceptance.
Consider reducing requirements, and get client's consent.
6. The reputation and financial risks of the project developing organization.
<L> The contract with the client assures that the client is legally limited to sue the developing organization. |  | L | L | 2 | 2
<H> The project cost case is not based on the time & material principle. |  |  | H |  | 0
Try to modify the cost case to include the time & material principle and have the client agree.
Have the contract clause, that risk assessment may modify the project schedule and costs.

## Risks B
Common Risk Statements 7-10
Client Name:
Project Name:
Date (mm/dd/yy):
Score: E - Exceptional, H - High, M - Medium, L - Low Copyright © Daniel Epstein
Risk Identification | Select Risk | Risk Score
7. Human resources
<L> Project Team has been formed and no skill gaps exist. |  | L | L | 1 | 2
<M> Project Team has been formed but some skill gaps exist. |  |  | M |  | 0
Allocate a subject matter expert to work with the team.
Modify project plan to account for unsufficient project resources.
<H> Project Team has not been formed and/or required resources are not available. |  |  | H |  | 0
Allocate a subject matter expert to work with the team.
Delay project implementation until such time when experienced resources are available.
Provide training to team members to reduce the knowledge gap
8. Client commitment
<L> Client is committed to work with the delivery team and has allocated skilled resources. |  | L | L | 3 | 2
<M> Client has not yet allocated skilled resources, but documented their commitment to work with the delivery team. |  |  | M |  | 0
Respectfully remind client about their mutually agreed and documented commitments
<H> Client has not allocated skilled resources and has no documented commitment to work with the delivery team. |  |  | H | 0 | 0
Respectfully remind client about their resposibility to allocate resources. Request compliance by specific date.
Assist customer to acquire needed resources externally, if possible.
9. Standard / Non Standard Contract
<L> The documented contract is standard for your organization, the same for most of your projects |  | L | L | 1 | 2
<M> The documented contract is standard, but may contain several minor specifics to the project clauses. |  |  | M |  | 0
<H> The proposed by the client contract is not standard for your organization and is not signed yet by your legal counsel. |  |  | H |  | 0
The cost of the project must be adjusted by the cost analyst to include the risk of new type of contract, which must be approved by legal counsel
<E> The proposed by the client contractual obligations are not standard for your organization and are opposed by your legal counsel. |  |  | E | 1 | 0
Do not sign off and do not start the project until terms and conditions are approved by the legal department.
Do not sign off and do not start the project until the new cost case is developed and approved by the financial manager.
10. Type of Contract
<L> The "body shop" time and material services with no responsibilities, except for supplying resources. |  | L | L | 1 | 2
<M> The time and material services with responsibilities for the project delivery. |  |  | M |  | 0
<M> Fixed price contract, where prices are agreed on frame by frame basis before starting each new frame. |  |  | M |  | 0
Update project plan before beginning each new frame.
Estimate each new frame and include new estimates in the cost case for each frame.
Ensure that all project management processes are followed by all and new change requests are processed in accordance with guidelines.
<H> Fixed price project for the entire contract. |  |  | H
Sign off contract only if the significant delivery team experience available in similar projects
Include the extra risk contingency
Ensure that all project management processes are followed by all and new change requests are processed in accordance with guidelines

## Risks C
Common Risk Statements 11-14
Client Name:
Project Name:
Date (mm/dd/yy):
Score: E - Exceptional, H - High, M - Medium, L - Low Copyright © Daniel Epstein
Risk Identification | Select Risk | Risk Score
11. Project Dependencies
<L> Minimum level or no dependencies on the third party deliverables or suppliers. Workaround is available. |  | L | L | 1 | 2
<M> Project depends on the third party deliverable, but workaround is available. |  |  | M |  | 0
Develop contingency plan for risk mitigation.
<H> Project depends on the third party deliverables with no available alternative. |  |  | H |  | 0
Make client aware of the existing dependency.
Client contract or SOW must state that the project cost and schedule are based on assumption that the third party delivers on time.
Have contingency plan ready in the event of the risk occurrence.
12. Quality Management
<L> Quality Management Audits and Reviews have been scheduled and conducted on time |  | L | L | 1 | 2
<L> Quality Conrol Reviews have confirmed the correctness of the each solution |  |  | L |  | 0
<M> Quality Managements audits and reviews were conducted and deficiencies found, but all concerns were closed. |  |  | M |  | 0
Verify that all audits and reviews were documented.
<H> Quality audits and reviews were conducted but some issues still exist. |  |  | H |  | 0
Close all open items and run the follow up audits and reviews.
<E> Some quality audits or reviews have not been conducted. |  |  | E |  | 0
Complete all audits and reviews.
13. Project Pricing
<L> The project price was established by a pricer or financial analyst. |  | L | L | 2 | 2
<M> The project price was established by a pricer or financial analyst, but some issues are still open and no price sign off complete. |  |  | M |  | 0
Obtain price sign off by a pricer or financial analyst
<H> The project price was not established by a pricer or financial analyst. |  |  | H |  | 0
Raise the issue with senior management that project price must be established by a pricer or financial analyst.
Obtain evidence that the project price is established by a pricer or financial analyst.
14. Offshore/onshore subcontractors involvement
<N/A> No parts of the project are subcontracted |  |  | N/A | 3 | 0
<L> Less than 25% of the project has been subcontracted |  | L | L |  | 2
<M> More than 25% of the project has been subcontracted |  |  | M |  | 0
Make sure that the agreed communication plan with subcontractors establish weekly status reporting.
Make sure that the agreed payment schedule to subcontractors is based upon acceptance of deliverables.
<H> More than 50% of the project has been subcontracted |  |  | H |  | 0
Make sure that the agreed communication plan with subcontractors establish weekly status reporting.
Make sure that the agreed payment schedule to subcontractors is based upon acceptance of deliverables.

## Risks D
Common Risk Statements 15-18
Client Name:
Project Name:
Date (mm/dd/yy):
Score: E - Exceptional, H - High, M - Medium, L - Low Copyright © Daniel Epstein
Risk Identification | Select Risk | Risk Score
15. Project Estimates
<L> The project estimates were made using methods described in the book and confirmed by the alternate method. |  | L | L | 2 | 2
<H> The project estimates were made using methods described in the book or estimates weren't documented. |  |  | H |  | 0
Develop estimates using methods described in the book.
Ensure that WBS contains very detailed hierarchy of activities decomposed to the elementary task level.
16. Delivery team experience with the client.
<L> Delivery team has previous positive experience with this client. There is mutual trust and cooperation between them. |  | L | L |  | 2
<M> Delivery team does not have previous experience with this client, but the client is cooperating with the delivery team. |  |  | M |  | 0
<H> The client is difficult, interferes with the team work or shows little interest in the project. |  |  | H | 3 | 0
Draw client's attention to the clients responsibilities as defined in SOW.
Make client aware of the status meetings, the client response time to questions and sign offs as defined in the communications plan.
Explain possible effects of the client's behaviour on the project. If necessary, escalate to senior management.
17. Non-functional or service levels requirements, such as reliability, time between failures etc, that cannot be tested directly.
<N/A> Not applicable |  | N/A | N/A |  | 0
<L> Indirect test show project compliance. No penalties established for non compliance. |  |  | L |  | 0
<M> Indirect tests show project compliance. There are moderate penalties for non compliance. |  |  | M |  | 0
Renegotiate penalties with the client. Project cost reflects possible penalties.
<H> Indirect tests cannot prove the project compliance. There are agressive penalties for non compliance. |  |  | H | 4 | 0
Renegotiate penalties with the client. Project cost reflects possible penalties.
Propose changes to moderate those requirements that cannot be indirectly tested during the project course.
The negotiated changes to requirements are signed off by the service management.
18. Product interface to external products
<N/A> No interface to external products is required. |  | N/A | N/A |  | 0
<L> Only one interface with the standard product is required. |  |  | L | 4 | 0
<M> More than one interface with the standard products or interface with a non-standard product is required. |  |  | M |  | 0
An ample time should be allocated to complete interfaces.
Develop a risk contingency plan if no interface is possible.
<H> Significant or unknown work is required to interface with a non existent yet product. |  |  | H |  | 0
An ample time should be allocated to complete interfaces.
Develop a risk contingency plan if no interface is possible.
Have a written agreement to support the delivery team by the on-standard or new product developer.
Make customer aware that the interface to the new product may not be possible to design.

## Risks E
Common Risk Statements 19-20
Client Name:
Project Name:
Date (mm/dd/yy):
Score: E - Exceptional, H - High, M - Medium, L - Low Copyright © Daniel Epstein
Risk Identification | Select Risk | Risk Score
19. Project Management Processes
<L> All project management processes are clearly documented and adhered to. |  | L | L | 1 | 2
<M> The project management processes will be documented before the project start. It is intended to make the adherence to them compulsory. |  |  | M |  | 0
Do not start the project until all project management processes are documented and signed off by management.
<H> The project management processes won't be established before start of the project, or client's organization request adherence to their own processes. |  |  | H |  | 0
Establish significant contingency plan in case if PM processes do not ensure quality standards of the developed product.
20. Project Manager
<L> A skilled project manager is assigned to manage the project. |  | L | L | 1 | 2
<M> Skilled project managers are available, but not assigned yet to the project. |  |  | M |  | 0
Make sure the skilled project manager is assigned to manage the project.
<H> There are no skilled project managers available to manage the project. |  |  | H |  | 0
Consider hiring the skilled consulting project manager.
Assign a skilled mentor to project manager and provide PM with the additional training.
<H> No Project manager has been identified and none available. |  |  | H |  | 0
Consider hiring the skilled consulting project manager.
Do not start the project until a skilled project manager is available.

## Unique Risks
Risk Statements - Unique Risks |  |  |  |  | Y | Exceptional | Except | Except | High | High | N/A
Client Name: |  |  |  |  | ILIT | High | Except | High | High | Medium | N/A
Project Name: |  |  |  |  | BAB | Medium | High | High | Medium | Medium | N/A
Date (mm/dd/yy): |  |  |  |  | PRO | Low | High | Medium | Medium | Low | N/A
[6 empty] | N/A | N/A | N/A | N/A | N/A | N/A
Copyright © Daniel Epstein | [6 empty] | Exceptional | High | Medium | Low | N/A
S E V E R I T Y
Risk Identification | Severity of Risk if Occurrs | Probability of Occurance | Resulting Risk Score
Risk Description |  |  | N/A | 5 | 5 | 0
Risk Remediation
Risk Description |  |  | N/A | 5 | 5 | 0
Risk Remediation
Risk Description |  |  | N/A | 5 | 5 | 0
Risk Remediation
Risk Description |  |  | N/A | 5 | 5 | 0
Risk Remediation
Risk Description |  |  | N/A | 5 | 5 | 0
Risk Remediation
Risk Description |  |  | N/A | 5 | 5 | 0
Risk Remediation
Risk Description |  |  | N/A | 5 | 5 | 0
Risk Remediation
Risk Description |  |  | N/A | 5 | 5 | 0
Risk Remediation
Risk Description |  |  | N/A | 5 | 5 | 0
Risk Remediation
Risk Description |  |  | N/A | 5 | 5 | 0
Risk Remediation

## Ref Table
Risk Assessment Reference Table
Y | Exceptional | High | High | Except | Except
I L I T | High | Medium | High | High | Except
B A B | Medium | Medium | Medium | High | High
P R O | Low | Low | Medium | Medium | High
|  | Low | Medium | High | Exceptional
S E V E R I T Y

## Summary
|  | Risk Summary |  |  | 10 | 5
[5 empty] | 8 | 4
|  | Client Name: |  |  | 8 | 4
|  | Project Name: |  |  | 4 | 2
|  | Date (mm/dd/yy): |  |  | 4 | 2
[5 empty] | 0 | 0.001
|  | Copyright © Daniel Epstein |  |  | 34 | 17.001
Known Risks | # of Risks | Normalized Risk Score | Overall Risk | Normalized Project Risk Scoring: |  | 19.9988
TOTAL PROJECT | 17.001 | 19.9988 | LOW | 1 Rate the severity of each risk event
Exceptional | 0 |  |  | - Risk Event Score = 2 (Low), 5 (Medium), 9 (High), 14 (Exceptional)
High | 0 |  |  | 2 Sum Risk Scores for all risk events
Medium | 0 |  |  | 3 Normalize
Low | 17 |  |  | - Normalized Score = Sum of Risk Scores x 10 / Number of Risk Events
4 Determine the Risk
- 21-40 (Low), 41-60 (Medium), 61-80 (High), 80+ (Exceptional)