## Sheet1
| Simple |  |  | Average |  |  | Complex
| weight factor | How many? | Product | weight factor | how many? | product | weight factor | how many? | product
External Input | 3 | 0 | 0 | 4 | 0 | 0 | 6 | 0 | 0
External Output | 4 | 0 | 0 | 5 | 0 | 0 | 7 | 0 | 0
User Inquiry | 3 | 0 | 0 | 4 | 0 | 0 | 6 | 0 | 0
External File | 7 | 0 | 0 | 10 | 0 | 0 | 15 | 0 | 0
Internal File | 5 | 0 | 0 | 7 | 0 | 0 | 10 | 0 | 0
Total | 0 |  |  | 0 |  |  | 0
Number of FPs | 0
0-5
Reliable backup and recovery needed |  |  | 0
data communication needed |  |  | 0
distributed functions required |  |  | 0 |  | Complexity Factor (CF)= 0.65+0.01*S |  |  | 0.65
performance required |  |  | 0
heavily used configuration |  |  | 0 |  | Adjusted FP = FP * CF |  |  | 0
real-time data entry needed |  |  | 0
ease of use |  |  | 0 |  | Effort in Days f exp 3*j / 27 / 20 |  |  | 0 | j 0.39 to 0.48
real-time update needed |  |  | 0 |  | Cost per Day in $ |  |  | 400
complexity of the interfaces |  |  | 0 |  | Total estimated cost |  |  | 0
complexity of processing |  |  | 0
reusability |  |  | 0 |  | Java lines of code (LOC) 65*AFP |  |  | 0
ease of installation |  |  | 0
multiple sites |  |  | 0 |  | Function Point
easy to change |  |  | 0
Technical Factor |  |  | 0 |  | Estimation Calculator