## Project_Survey
External Dependencies |  |  |  | Moderate Risk
EDF ID | EDF Issue | EDF Response | EDF Score | EDF Resolution
EDF01 | Does your project have multiple vendors/contractors? | Y | 2 | Coordination is key. Ensure adherence to standards, both technical and managerial. Emphasize the importance of regular status reporting.
EDF02 | Does this project have poor client support? | Y | 1 | Establish working norms or a team working agreement. Do not waste time waiting for a response to queries or rework arising from mistaken assumptions made by the project team in the interim. Impose contractual constraints/safeguards. Requesting documentation in advance ensures effective account management. Consider adding a contingency to your project. Negotiate for a client acceptor if there is more than one stakeholder you consider a client.
EDF03 | Does this project have poor vendor support? | Y | 1 | Identify a user group with your clients. Establish working norms or a team working agreement. Do not waste time waiting for a response to queries or rework arising from mistaken assumptions made by the project team in the interim. Impose contractual constraints/safeguards — request documentation in advance.
EDF04 | Does this project have poor sponsor support? | Y | 1 | Make sure the sponsor has time for this project. Establish time boundaries and plan around them. Establish working norms with the sponsor. When a problem arises, the sponsor may not have the authority, or perspective, to support the project adequately. Review the project's threats to make sure the sponsor has the authority necessary to resolve potential risks to the business analysis plan. Extend project board to include a more appropriate sponsor.
EDF05 | What is the number of project dependencies (external and internal)? | 6 | 5 | Do not waste time waiting for the completion of other projects, not within your control. Create a new critical path schedule that provides coordination between the various project. Recommend a strategic/architectural plan.
EDF06 | Does this project's scope overlap with other projects? | Y | 3 | Be aware of parallel or duplicate, development of similar areas with different approaches causing confusion and irritation to the team. Establish cross-project standards to ensure consistency. Establish change control procedures to manage the different changes proposed by different systems. Recommend a strategic/architectural plan.
EDF07 | What is the total number of affected Users ? | 2001 | 5 | The complexity of requirements and the possibility of conflicts will affect the business analysis approach: training requirements and implementation logistics. Consider a more adaptive approach, such as a phased implementation. Plan the releases as early as possible.
EDF08 | What is the number of affected User areas (the mimium value must be one)? | 1 | 1 | Obtain consensus by identifying key representatives. Establish a decision-making process/responsibilities. Use a RACI or other responsibility and assignment matrix.
EDF09 | What is the number of decision-makers per affected User area (the mimium value must be one)? | 1 |  | Obtain consensus by identifying key representatives. Establish a decision-making process/responsibilities. Use a RACI or other responsibility and assignment matrix.
EDF10 | What is the number of external implementation sites (the mimium value must be one)? | 1 | 1 | In combination with the number of geographical areas affected, the project requires time to distribute deliverables and coordinate activities. Select a pilot implementation site then a phase in the implementation. Establish a focal point for development activities.
EDF11 | What is the number of geographical areas affected (the mimium value must be one)? | 1 |  | In combination with the number of external implementation sites, the project requires time to distribute deliverables and coordinate activities. As the ratio between these two factors increases, so will the risk. Consider adding a contingency to your business analysis plan.
EDF12 | Do the external stakeholders (including vendors) have prior experience with this project's solution approach? | N | 1 | Do not set unrealistic expectations — lack of communication. Lack of knowledge of roles and commitment will undermine success. Do not keep team members at arm's length — especially vendors and external clients. Schedule briefing and training sessions early in the project and increase user involvement/participation.
EDF13 | Will Key External SMEs be available? | N | 5 | Subject matter experts are essential to project success. They hold crucial information required to analyze, design, build, test, deploy, and assess a solution or any of its components.
EDF14 | Are key users available for this project? | N | 5 | Lack of understanding of requirements or lack of involvement of users in the production of deliverables will consequently lead to apathy and lack of commitment to the project. Users are a significant stakeholder for any project; in terms of their impact and participation. A project IS its stakeholders. Use techniques that are less dependent on user input, e.g., relational data analysis rather than data modeling. Use user representatives on the Project Board to encourage participation. Extend review activities.
EDF15 | Are organizational changes required (in terms of reporting, structure, or responsibility)? | Y | 2 | Plan the change as soon as the project begins. Begin the change as soon as the solution designs begin. Anticipate and plan for resistance. Identify change champions and put them to work, spreading the value of the adjustment. Hold briefings throughout the project with all stakeholders. Increase user involvement. Obtain top management commitment. Use the ADKAR process to manage the awareness, desire, required abilities of the change. Remember to plan to reinforce the shift. It can take more than a month for some people to adapt.
EDF16 | What is the level of changes required to user procedures? | H | 3 | The more change required at one time, the more resistant a stakeholder may be — phase changes in small doses. Users inadequately prepared for successful implementation and handover will revert to old behaviors. Increase the level of user training, use of prototypes, and presentations of the new procedures. Identify early adopters within the user-base and train the trainer.
EDF17 | Will this project involve users in project management and execution, as in building the deliverables schedule? | N | 3 | Lack of commitment to assuring the quality of deliverables increases rework and defects. Increase user participation in all solution related activities by use of JAD, and other interactive sessions. Use workshops to elicit information and create models. Manage workshops correctly by having its participants provide the information through activities such as process modeling or use case diagrams. Determine user roles in the project organization with RACI charts or some other responsibility assignment matrix. RAMs are useful at all levels of your business analysis plan, from high-level deliverables to activities and elements of work or work products.
EDF18 | What is the level of training required for this project? | H | 3 | Make sure there are adequate budget and time for training. Include a prior walkthrough of the training sessions and materials to gain commitment from user management. Plan the training with an experienced trainer. If a vendor is providing the solution or any of its components, be sure to include training in the contract and statement of work (SOW).
42
Internal Planning Factors |  |  |  | Moderate Risk
IPF ID | IPF Issue | IPF Response | EDF Score | IPF Resolution
IPF01 | Is this project dependent on scarce resources/skills? | Y | 5 | The project will experience competition for resources or personnel with appropriate skills. Make resource requirements known as early as possible.
IPF02 | Is this project dependant on complex task dependencies? | Y | 3 | If critical dependencies are unknown, there is an increased chance of schedule slippage. Increase the level of planning and tighten project control.
IPF03 | What is the number of inter-project dependencies? | 33 | 5 | Do not waste time awaiting completion of other projects not within the project manager's control. Create a coordination project with the critical identified. Recommend a strategic/architectural plan.
IPF04 | Does the project plan require extensive recruitment of resources? | Y | 2 | Plan time and expense to train resources. Plan gradual transition to critical deliverables to allow for team resources to reach high production. Investigate the viability of using short term experienced contractors.
IPF05 | Is there a critical implementation date? | Y | 5 | Consider reducing quality or functionality. Be sure to verify the significance of the project or requirement's due date. What is the cost of missing the due date? Allocate solution requirements, selecting which module in which portions of the solution they belong; and release accordingly.
IPF06 | Are there sufficient control/governance procedures in place? | N | 5 | Plan to ensure decisions execute consistently and adequately. Define a process that allows decision-makers to have the information they need. Examples of this include requirements management, business analysis risk management, and allocation of business analysis resources.
IPF07 | What is the number of significant subsystems? | 5 | 3 | There is an increased chance of project slippage due to possible changes in requirements or scope over longer elapsed time.Create a plan to manage each interface. Involve solution architects to aid in threat reduction. Minimize project interdependencies by adding other business analysts or project coordinators.
IPF08 | Has more than three years elapsed on the management of these subsystems? | Y | 2 | There is an increased chance of project slippage due to possible changes in requirements or scope over longer elapsed time.Create a plan to manage each interface. Involve solution architects to aid in threat reduction. Minimize project interdependencies by adding other business analysts or project coordinators.
IPF10 | What is your overall level of confidence for this project (out of a score of five where five is the most confident and one is the least)? | 5 | 1 | The level of planning experience of unknowns within the project plan may make estimates low. Ensure management tolerances and contingencies are identified using established tools such as declining order of magnitudes for cost and time estimates, rolling wave planning (RWP) earned value management (EVM), program evaluation review technique (PERT), and expected monetary value (EMV). Be sure to fully define the business analysis plan (BAP).
IPF11 | Were key deliverable dates set by the team based on the project plan? | N | 3 | Is the mandated date arbitrary? Create a forward business analysis plan. Identify gaps between the required and honest completion date. Verify the significance and justification for the deliverables dates. Review the cost of missing deliverables. Review the critical path and ensure the best resources are on track. Produce a plan. If the team has no control over deliverables, it is hard to maintain a commitment to the project plan. If the date is unachievable, motivation is challenging, and quality will suffer. Expect rework, requirements, and solution defects to be high and costly in time and money. Integration, change management, training, and testing suffer under these conditions.
IPF12 | What is the overall experience of the project manager? | L | 4 | Plans may not exist. Control procedures may not be adequate. Provide training and support from an experienced project manager. Increase involvement by Project Board.
IPF13 | Are the required resources available and ready to work? | N | 5 | If the resources (all stakeholders whom the project will meet expectations, work with jointly, partner, consult, inform, or otherwise engage), then the project will fail. The project may require a new plan or baseline to fit with maximum resource constraints. A rebaselined project is considered a bankrupt project and follows the same psychological path.

## Threat_Analysis
Analysis of Project Threats Using Bayes' Theorem
ID | Threat | Initial Evidence | Degree of Belief the Threat is True Given Initial Evidence | Inverse of Belief the Threat Event is True Given Condition | First Conditional Outcome | Evidence for First Conditional Outcome | First Conditional Outcome Given Its Evidence | Degree of Belief of First Conditional Outcome Given Its Evidence | Probability of First Conditional Outcome Given Its Evidence | Second Conditional Outcome | Evidence for Second Conditional Outcome | Second Conditional Outcome Given Its Evidence | Degree of Belief of Second Conditional Outcome Given Its Evidence | Joint Belief Given Threat Event AND First Conditional Outcome | Joint Belief Given Threat Event AND Second Conditional Outcome | Probability of Second Conditional Outcome Given Its Evidence
TR001 | client did not receive a refund for extra services rendered | client bank statement does not show a transaction record | 80% | 20% | our client withdraws support for our project | we missed payments to client | Because we missed payments to client our client withdraws support for our project given client did not receive a refund for extra services rendered | 35% | 62.22% | client does not withdraw their support for our project | our teams have a strong working relationship | Because our teams have a strong working relationship client does not withdraw their support for our project given client did not receive a refund for extra services rendered | 85% | 28% | 17% | 37.78%
TR002 | the threat | some initial evidence | 10% | 90% | this is the first conditional outcome | this is the evidence for the first conditional outcome | Because this is the evidence for the first conditional outcome this is the first conditional outcome given the threat | 20% | 6.897% | this is the second conditional outcome | this is the evidence for the second conditional outcome | Because this is the evidence for the second conditional outcome this is the second conditional outcome given the threat | 30% | 2% | 27% | 93.1%
TR003
TR004
TR005
TR006
TR007
TR008
TR009
TR010
TR011
TR012
TR013
TR014
TR015
TR016
TR017
TR018
TR019
TR020
TRnn

## BA_Activities
Work Product |  | Responsibility Assignment Matrix (RASCI) |  |  |  |  | Estimated Uninterrupted Effort Hours |  |  | Hide | Hide | Hide | Hide | Hide | Adjustments | [6 empty] | Range of Compleation in Hours |  |  |  |  | Reporting
ID | BA Activity | R | A | S | C | I | Worst | ML | Best | Mean (of the number set) | Variance (of the number set) | (x-mean)^2 | sigma | z-score | Availability | Efficiency Adjustment | Proficiency Adjustment | X | Y | Adjusted Effort Hours | Adjusted Duration in Hours | −2σ | −1σ | 0σ | +1σ | +2σ | Priority | Status | Start Date | Due Date | % Complete | Date Completed | Days Overdue
BA-1.1 | Plan Business Analysis Approach | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 41 | 24 | 16 | 27 | 108.6667 | 326 | 10.4243 | -0.28779 | 90% | Efficient | Experienced | 0.8 | 0.85 | 28.6875 | 31.875 | 11.0263 | 21.4507 | 31.875 | 42.2993 | 52.7237 | Normal | On Schedule | 2019-10-01 | 2019-10-02 | 40% | 2019-10-03 | 71
BA-1.2 | Plan Stakeholder Engagement Plan | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 72 | 25 | 15 | 37.3333 | 617.5556 | 1852.6667 | 24.8507 | -0.4963 | 60% | Average | Inexperienced | 0.7 | 1.24 | 66.1333 | 110.2222 | 60.5209 | 85.3716 | 110.2222 | 135.0729 | 159.9236 | High | On Schedule | 2019-10-03 | 2019-10-10 | 20% |  | 63
BA-1.3 | Plan Business Analysis Governance Plan | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 53 | 24 | 20 | 32.3333 | 216.2222 | 648.6667 | 14.7045 | -0.56672 | 75% | Efficient | Average | 0.8 | 1 | 40.4167 | 53.8889 | 24.4799 | 39.1844 | 53.8889 | 68.5934 | 83.2979 | Low | On Schedule |  |  | 0%
BA-1.4 | Plan Business Analysis Information Management Plan | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 55 | 23 | 5 | 27.6667 | 427.5556 | 1282.6667 | 20.6774 | -0.22569 | 61.07% | Inefficient | Experienced | 0.6 | 0.85 | 39.1944 | 64.1745 | 22.8196 | 43.4971 | 64.1745 | 84.8519 | 105.5293 | Normal | On Schedule |  |  | 0%
BA-1.5 | Business Analysis Performance Improvement Plan | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 26 | 23 | 24 | 24.3333 | 1.5556 | 4.6667 | 1.2472 | -1.069 | 50% | Efficient | Average | 0.8 | 1 | 30.4167 | 60.8333 | 58.3389 | 59.5861 | 60.8333 | 62.0806 | 63.3278 | Normal | On Schedule |  |  | 0%
BA-2.1 | Stakeholder Analysis and Collaboration Plan | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 42 | 23 | 7 | 24 | 204.6667 | 614 | 14.3062 | -0.0699 | 68.15% | Average | Inexperienced | 0.7 | 1.24 | 42.5143 | 62.3802 | 33.7679 | 48.074 | 62.3802 | 76.6864 | 90.9926 | High | On Schedule |  |  | 0%
BA-2.2 | Form Requirements Team | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 41 | 22 | 37 | 33.3333 | 66.8889 | 200.6667 | 8.1786 | -1.3857 | 65.31% | Average | Experienced | 0.7 | 0.85 | 40.4762 | 61.9774 | 45.6203 | 53.7988 | 61.9774 | 70.156 | 78.3345 | Normal | On Schedule |  |  | 0%
BA-2.3 | Create and Approve Requirements Team Charter | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 22 | 28 | 6 | 18.6667 | 86.2222 | 258.6667 | 9.2856 | 1.0051 | 50% | Efficient | Experienced | 0.8 | 0.85 | 19.8333 | 39.6667 | 21.0955 | 30.3811 | 39.6667 | 48.9523 | 58.2379 | High | On Schedule |  |  | 0%
BA-2.4 | Prepare Elicitation Plans | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 54 | 23 | 5 | 27.3333 | 409.5556 | 1228.6667 | 20.2375 | -0.21412 | 69.52% | Inefficient | Average | 0.6 | 1 | 45.5556 | 65.5286 | 25.0536 | 45.2911 | 65.5286 | 85.7661 | 106.0036 | Low | On Schedule |  |  | 0%
BA-2.5 | Conduct all Elicitation Activities and Sessions | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 64 | 22 | 18 | 34.6667 | 432.8889 | 1298.6667 | 20.806 | -0.6088 | 29.53% | Efficient | Average | 0.8 | 1 | 43.3333 | 146.7207 | 105.1087 | 125.9147 | 146.7207 | 167.5266 | 188.3326 | Normal | On Schedule |  |  | 0%
BA-2.6 | Confirm all Elicitation Results | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 41 | 24 | 16 | 27 | 108.6667 | 326 | 10.4243 | -0.28779 | 49.1% | Average | Average | 0.7 | 1 | 38.5714 | 78.5528 | 57.7042 | 68.1285 | 78.5528 | 88.9772 | 99.4015 | Normal | On Schedule |  |  | 0%
BA-2.7 | Verify and Validate all Stated Requirements | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 66 | 28 | 33 | 42.3333 | 284.2222 | 852.6667 | 16.8589 | -0.85019 | 43.52% | Average | Experienced | 0.7 | 0.85 | 51.4048 | 118.1092 | 84.3914 | 101.2503 | 118.1092 | 134.9681 | 151.827 | High | On Schedule |  |  | 0%
BA-2.8 | Baseline all Stated Requirements | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 20 | 29 | 9 | 19.3333 | 66.8889 | 200.6667 | 8.1786 | 1.182 | 31.43% | Average | Experienced | 0.7 | 0.85 | 23.4762 | 74.6949 | 58.3378 | 66.5164 | 74.6949 | 82.8735 | 91.0521 | Normal | On Schedule |  |  | 0%
BA-3.1 | Ongoing Trace of Requirements | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 71 | 25 | 20 | 38.6667 | 526.8889 | 1580.6667 | 22.9541 | -0.59539 | 60.71% | Efficient | Average | 0.8 | 1 | 48.3333 | 79.613 | 33.7048 | 56.6589 | 79.613 | 102.567 | 125.5211 | High | On Schedule |  |  | 0%
BA-3.2 | Ongoing Maintain Requirements | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 66 | 32 | 20 | 39.3333 | 379.5556 | 1138.6667 | 19.4822 | -0.37641 | 36.51% | Efficient | Inexperienced | 0.8 | 1.24 | 60.9667 | 166.9962 | 128.0318 | 147.514 | 166.9962 | 186.4784 | 205.9605 | Low | On Schedule |  |  | 0%
BA-3.3 | Prioritize all Requirements | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 35 | 30 | 24 | 29.6667 | 20.2222 | 60.6667 | 4.4969 | 0.074125 | 34.25% | Average | Experienced | 0.7 | 0.85 | 36.0238 | 105.1904 | 96.1966 | 100.6935 | 105.1904 | 109.6874 | 114.1843 | Normal | On Schedule |  |  | 0%
BA-3.4 | Ongoing Assessment of Requirement Changes | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 22 | 29 | 18 | 23 | 20.6667 | 62 | 4.5461 | 1.3198 | 15.4% | Inefficient | Average | 0.6 | 1 | 38.3333 | 248.9525 | 239.8604 | 244.4065 | 248.9525 | 253.4986 | 258.0446 | Normal | On Schedule |  |  | 0%
BA-3.5 | Approve Requirements at all Levels and Stages | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 44 | 27 | 6 | 25.6667 | 241.5556 | 724.6667 | 15.5421 | 0.085789 | 35.01% | Efficient | Inexperienced | 0.8 | 1.24 | 39.7833 | 113.6405 | 82.5563 | 98.0984 | 113.6405 | 129.1825 | 144.7246 | High | On Schedule |  |  | 0%
BA-4.1 | Analyze Current State | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 70 | 32 | 15 | 39 | 528.6667 | 1586 | 22.9928 | -0.30444 | 80.27% | Inefficient | Average | 0.6 | 1 | 65 | 80.9796 | 34.9941 | 57.9869 | 80.9796 | 103.9724 | 126.9651 | Normal | On Schedule |  |  | 0%
BA-4.2 | Define Future State | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 72 | 29 | 35 | 45.3333 | 361.5556 | 1084.6667 | 19.0146 | -0.85899 | 34.73% | Average | Average | 0.7 | 1 | 64.7619 | 186.4902 | 148.4609 | 167.4755 | 186.4902 | 205.5048 | 224.5194 | High | On Schedule |  |  | 0%
BA-4.3 | Assess Requirements Risks | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 24 | 24 | 17 | 21.6667 | 10.8889 | 32.6667 | 3.2998 | 0.70711 | 24.87% | Average | Experienced | 0.7 | 0.85 | 26.3095 | 105.7963 | 99.1966 | 102.4965 | 105.7963 | 109.0961 | 112.396 | Low | On Schedule |  |  | 0%
BA-4.4 | Define Change Strategy | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 63 | 26 | 15 | 34.6667 | 421.5556 | 1264.6667 | 20.5318 | -0.42211 | 3.202% | Average | Experienced | 0.7 | 0.85 | 42.0952 | 1314.6686 | 1273.6049 | 1294.1367 | 1314.6686 | 1335.2004 | 1355.7322 | Normal | On Schedule |  |  | 0%
BA-5.1 | Prepare Analysis Plans | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 46 | 32 | 18 | 32 | 130.6667 | 392 | 11.431 | 0 | 86.74% | Efficient | Experienced | 0.8 | 0.85 | 34 | 39.1975 | 16.3356 | 27.7665 | 39.1975 | 50.6284 | 62.0594 | Normal | On Schedule |  |  | 0%
BA-5.2 | Conduct all Analysis Activities and Sessions | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 55 | 30 | 36 | 40.3333 | 113.5556 | 340.6667 | 10.6562 | -0.9697 | 79.69% | Average | Average | 0.7 | 1 | 57.619 | 72.3002 | 50.9878 | 61.644 | 72.3002 | 82.9565 | 93.6127 | High | On Schedule |  |  | 0%
BA-5.3 | Confirm all Analysis Results | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 34 | 23 | 20 | 25.6667 | 36.2222 | 108.6667 | 6.0185 | -0.44308 | 12.81% | Inefficient | Experienced | 0.6 | 0.85 | 36.3611 | 283.8342 | 271.7972 | 277.8157 | 283.8342 | 289.8527 | 295.8712 | Normal | On Schedule |  |  | 0%
BA-5.4 | Specify and Model all Requirements | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 34 | 29 | 27 | 30 | 8.6667 | 26 | 2.9439 | -0.33968 | 92.25% | Efficient | Average | 0.8 | 1 | 37.5 | 40.6487 | 34.7609 | 37.7048 | 40.6487 | 43.5926 | 46.5365 | High | On Schedule |  |  | 0%
BA-5.5 | Define all Design Options | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 68 | 22 | 19 | 36.3333 | 502.8889 | 1508.6667 | 22.4252 | -0.63916 | 64.74% | Efficient | Average | 0.8 | 1 | 45.4167 | 70.1521 | 25.3018 | 47.727 | 70.1521 | 92.5773 | 115.0025 | Low | On Schedule |  |  | 0%
BA-5.6 | Analyze all Potential Value and Recommend Solution | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 48 | 26 | 23 | 32.3333 | 124.2222 | 372.6667 | 11.1455 | -0.56824 | 52.74% | Average | Average | 0.7 | 1 | 46.1905 | 87.5802 | 65.2892 | 76.4347 | 87.5802 | 98.7257 | 109.8712 | Normal | On Schedule |  |  | 0%
BA-5.7 | Verify all Requirements | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 21 | 32 | 13 | 22 | 60.6667 | 182 | 7.7889 | 1.2839 | 18.99% | Average | Experienced | 0.7 | 0.85 | 26.7143 | 140.6802 | 125.1024 | 132.8913 | 140.6802 | 148.4691 | 156.258 | Normal | On Schedule |  |  | 0%
BA-5.8 | Validate all Requirements | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 56 | 26 | 6 | 29.3333 | 422.2222 | 1266.6667 | 20.548 | -0.16222 | 85.5% | Inefficient | Experienced | 0.6 | 0.85 | 41.5556 | 48.603 | 7.5069 | 28.0549 | 48.603 | 69.151 | 89.6991 | High | On Schedule |  |  | 0%
BA-5.9 | Prepare all Requirements Packages | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 34 | 30 | 17 | 27 | 52.6667 | 158 | 7.2572 | 0.41338 | 35% | Efficient | Average | 0.8 | 1 | 33.75 | 96.4286 | 81.9142 | 89.1714 | 96.4286 | 103.6858 | 110.9429 | Normal | On Schedule |  |  | 0%
BA-5.10 | Baseline all Analyzed Requirements | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 21 | 28 | 18 | 22.3333 | 17.5556 | 52.6667 | 4.1899 | 1.3524 | 64.68% | Average | Average | 0.7 | 1 | 31.9048 | 49.3239 | 40.944 | 45.1339 | 49.3239 | 53.5138 | 57.7037 | High | On Schedule |  |  | 0%
BA-6.1 | Measure Solution Performance | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 33 | 27 | 18 | 26 | 38 | 114 | 6.1644 | 0.16222 | 55.31% | Average | Experienced | 0.7 | 0.85 | 31.5714 | 57.0783 | 44.7494 | 50.9138 | 57.0783 | 63.2427 | 69.4071 | Low | On Schedule |  |  | 0%
BA-6.2 | Analyze Performance Measures | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 20 | 27 | 9 | 18.6667 | 54.8889 | 164.6667 | 7.4087 | 1.1248 | 56.08% | Efficient | Average | 0.8 | 1 | 23.3333 | 41.6043 | 26.7869 | 34.1956 | 41.6043 | 49.013 | 56.4217 | Normal | On Schedule |  |  | 0%
BA-6.3 | Assess Solution Limitations | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 60 | 25 | 21 | 35.3333 | 306.8889 | 920.6667 | 17.5182 | -0.58986 | 25% | Average | Average | 0.7 | 1 | 50.4762 | 201.9048 | 166.8683 | 184.3865 | 201.9048 | 219.423 | 236.9413 | Normal | On Schedule |  |  | 0%
BA-6.4 | Assess Enterprise Limitations | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 27 | 30 | 8 | 21.6667 | 94.8889 | 284.6667 | 9.7411 | 0.85548 | 48.88% | Average | Average | 0.7 | 1 | 30.9524 | 63.325 | 43.8429 | 53.584 | 63.325 | 73.0661 | 82.8072 | High | On Schedule |  |  | 0%
BA-6.5 | Recommend Actions to Increase Solution Value | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | Resource Full Name | 66 | 28 | 35 | 43 | 272.6667 | 818 | 16.5126 | -0.9084 | 61.99% | Efficient | Average | 0.8 | 1 | 53.75 | 86.7118 | 53.6866 | 70.1992 | 86.7118 | 103.2244 | 119.7371 | High | On Schedule |  |  | 0%
Formulas:
Days Overdue = IF(ISBLANK(tbl_BA_activities[[#This Row],[Due Date]]),"",IF(TODAY()>tbl_BA_activities[[#This Row],[Due Date]],TODAY()-tbl_BA_activities[[#This Row],[Due Date]],0))

## UC_Analysis
Actor Complexity Analysis |  |  |  | Use Case Hours
Actor ID | Actor Complexity | Actor Name |  | Contition | Hours | Days (7.5)
1 | Simple |  |  | Total Use Case Points | 196.4669 | 733.4763
2 | Average |  |  | Total Derived Hours | 5501.0725
3 | Complex
4 | Complex |  |  | Use Case Analysis Report |  | Actor Analysis Report
5 | Simple |  |  | Use Case | Count | Actor | Count
6 | Complex |  |  | Simple | 8 | Simple | 4
7 | Complex |  |  | Average | 7 | Average | 2
8 | Average |  |  | Complex | 5 | Complex | 4
9 | Simple |  |  | Total Use Cases | 20 | Total Actors | 10
10 | Simple
Unadjusted Actor Weight (UAW) (Hidden) |  | 20
Use Case Complexity Analysis
UC ID | Use Case Complexity | Use Case Name
1 | Simple
2 | Average
3 | Complex
4 | Complex
5 | Average
6 | Simple
7 | Complex
8 | Complex
9 | Complex
10 | Simple
11 | Simple
12 | Simple
13 | Simple
14 | Simple
15 | Simple
16 | Average
17 | Average
18 | Average
19 | Average
20 | Average
Unadjusted Use Case Weight (UAW) (Hidden) |  | 185
Technical Complexity Analysis
Question | Importance | Description | Technical Complexity Factor (TCF) Score (Hidden)
Distributed System Required | 1 | The architecture of the solution may be centralized or single-tenant , or it may be distributed (like an n-tier solution) or multi-tenant. Higher numbers represent a more complex architecture. | 2
Response Time Is Important | 4 | The quickness of response for users is an important (and non-trivial) factor. For example, if the server load is expected to be very low, this may be a trivial factor. Higher numbers represent increasing importance of response time (a search engine would have a high number, a daily news aggregator would have a low number). | 4
End User Efficiency | 3 | Is the application being developed to optimize on user efficiency, or just capability? Higher numbers represent projects that rely more heavily on the application to improve user efficiency. | 3
Complex Internal Processing Required | 4 | Is there a lot of difficult algorithmic work to do and test? Complex algorithms (resource leveling, time-domain systems analysis, OLAP cubes) have higher numbers. Simple database queries would have low numbers. | 4
Reusable Code Must Be A Focus | 5 | Is heavy code reuse an objective or goal? Code reuse reduces the amount of effort required to deploy a project. It also reduces the amount of time required to debug a project. A shared library function can be re-used multiple times, and fixing the code in one place can resolve multiple bugs. The higher the level of re-use, the lower the number. | 5
Installation Ease | 5 | Is ease of installation for end users a key factor? The higher the level of competence of the users, the lower the number. | 2.5
Usability | 2 | Is ease of use a primary criteria for acceptance? The greater the importance of usability, the higher the number. | 1
Cross-Platform Support | 3 | Is multi-platform support required? The more platforms that have to be supported (this could be browser versions, mobile devices, etc. or Windows/OSX/Unix), the higher the value. | 6
Easy To Change | 4 | Does the customer require the ability to change or customize the application in the future? The more change / customization that is required in the future, the higher the value. | 4
Highly Concurrent | 5 | Will you have to address database locking and other concurrency issues? The more attention you have to spend to resolving conflicts in the data or application, the higher the value. | 5
Custom Security | 1 | Can existing security solutions be leveraged, or must custom code be developed? The more custom security work you have to do (field level, page level, or role based security, for example), the higher the value. | 1
Dependence On Third-Party Code | 2 | Will the application require the use of third party controls or libraries? Like re-usable code, third party code can reduce the effort required to deploy a solution. The more third party code (and the more reliable the third party code), the lower the number. | 2
User Training | 3 | How much user training is required? Is the application complex, or supporting complex activities? The longer it takes users to cross the suck threshold (achieve a level of mastery of the product), the higher the value. | 3
Technical Complexity Factor (TCF) Score (Hidden) |  | 1.025
Environmental Use Case Analysis
Question | Importance | Description | Environmental Complexity Factor (ECF) (Hidden)
Familiarity With The Project | 4 | How much experience does your team have working in this domain? The domain of the project will be a reflection of what the software is intended to accomplish, not the implementation language. In other words, for an insurance compensation system written in java, you care about the team’s experience in the insurance compensation space - not how much java they’ve written. Higher levels of experience get a higher number. | 6
Application Experience | 2 | How much experience does your team have with the application. This will only be relevant when making changes to an existing application. Higher numbers represent more experience. For a new application, everyone’s experience will be 0. | 1
OO Programming Experience | 1 | How much experience does your team have at OO? It can be easy to forget that many people have no object oriented programming experience if you are used to having it. A user-centric or use-case-driven project will have an inherently OO structure in the implementation. Higher numbers represent more OO experience. | 1
Lead Analyst Capability | 1 | How knowledgeable and capable is the person responsible for the requirements? Bad requirements are the number one killer of projects - the Standish Group reports that 40% to 60% of defects come from bad requirements. Higher numbers represent increased skill and knowledge. | 0.5
Motivation | 3 | How motivated is your team? Higher numbers represent more motivation. | 3
Stable Requirements | 3 | Changes in requirements can cause increases in work. The way to avoid this is by planning for change and instituting a timing system for managing those changes. Most people don’t do this, and some rework will be unavoidable. Higher numbers represent more change (or a less effective system for managing change). | 6
Part Time Staff | 1 | Note, the multiplier for this number is negative. Higher numbers reflect team members that are part time, outside consultants, and developers who are splitting their time across projects. Context switching and other intangible factors make these team members less efficient. | -1
Difficult Programming Language | 1 | This multiplier is also negative. Harder languages represent higher numbers. We believe that difficulty is in the eye of the be-coder (groan). Java might be difficult for a fortran programmer. Think of it in terms of difficulty for your team, not abstract difficulty. | -1
Environmental Complexity Factor (ECF) Score (Hidden) |  | 0.935
Note on B3: Actor Complexity Analysis (Unadjusted Actor Weight) Following a use case or scenario based requirements analysis and design definition and development method requires us to analyze the use cases and scenarios using the Use Case Points Method or UCP. Our first step is to examine and classify our actors The UAW contributes to the size of the software being developed. It is calculated based on the number and complexity of the actors for the system. Each of the actors must be identified and classified as Simple, Average or Complex based on the type of actor. We generally classify actors in the following mannor: Simple: External systems that must interact with the solution under consideration using a well-defined application programming interface. An API is a subroutine definition, protocol, predefined method or other programatic tool used to help various software components communicaite with each other. Average: External system that must interact with the system using standard communication protocols (e.g. TCP/IP, FTP, HTTP, database). Conplex: Human actor using a GUI application interface.
Note on C4: Actor Complexity Analysis
Note on B17: Unadjusted Use Case Weight (UUCW) The UUCW is one of the factors that contribute to the size of the software being developed. It is calculated based on the number and complexity of the use cases for the system. To find the UUCW for a system, each of the use cases must be identified and classified as Simple, Average or Complex based on the number of transactions the use case contains. A use case transaction is defined as the number of steps in a use case flow, which describes the interaction between an actor and the system or a round trip between the user to the system and back to the user again. Here is an an examle: Simple: 1 to 3 transactions Average: 4 to 7 transactions Complex: 8 or more transactions Start of transaction User does something System responds System changes state Actor does something else End of transaction Start of new transaction User does something System responds ...
Note on B41: Technical Complexity Analysis The TCA is one of the factors applied to the estimated size of the software in order to account for technical considerations of the system. It is determined by assigning a score between 0 (factor is irrelevant) and 5 (factor is essential) to each of the 13 technical factors listed in the table below. Use the descriptions provided to help evaluate your answer.